Table of contents

# Modernization Project Plan

## 1. Overview

This plan describes how the modernization project will move from the current state (implicit governance encoded in legacy directories and fragmented stores) to a target state defined by a single authoritative origin for structure and claims, attribute-driven constructs, explicit drift detection, and controlled, evidence-producing change.

It follows the approach in the Project Charter: Assess → Define target → Plan waves → Execute under control → Validate and sustain.

The plan is organized by phases. Each phase has objectives, key activities, deliverables, entry/exit criteria, and notes on risks or dependencies. Domain workstreams (identity, policy, services/addressing, compute/device, access plane) run inside the later phases and can be sequenced or parallelized according to organizational priorities.

## 2. Guiding Constraints

- Changes originate from a designated authoritative source and close with provenance.

- Elevated privilege is time-bounded and scoped (just-in-time).

- Derived copies and subordinate systems remain explicitly non-authoritative.

- Drift between intended and observed state is classified and visible.

- No full rip-and-replace is required to make progress.

## 3. Phases

### Phase 0 — Charter and Alignment

Objective: Confirm scope, stakeholders, success criteria, and decision rights.

Key activities - Review and finalize the Project Charter. - Identify sponsor, project lead, and domain leads. - Confirm in-scope domains and any organizational constraints (data residency, existing tools, timeline pressure). - Agree on the evidence and provenance expectations that will apply to all later changes.

Deliverables - Signed or accepted Project Charter. - Stakeholder and role list. - Initial risk register.

Supporting material - Why Modernization Is Hard — leadership framing of the problem - Principles — the rules the charter commits to - Chapter 00 — The Problem Nobody Talks About - Chapter 10 — Leadership Takeaway

Exit criteria - Leadership can state the problem, the target outcome, and how success will be measured.

### Phase 1 — Current-State Assessment

Objective: Make the existing governance model and hidden dependencies explicit.

Key activities - Inventory major directory and identity dependencies (organizational structure, delegation, policy, service accounts, certificates, naming, addressing). - Document how structure and authority are currently encoded (hierarchical containers, group membership, policy inheritance, etc.). - Identify sources of truth (or competing sources) for human and non-human identity lifecycle events. - Capture known fragmentation points and reconciliation pain. - Produce a dependency and risk map that highlights migration hazards.

Deliverables - Current-state assessment report. - Dependency and hidden-surface inventory. - List of candidate authoritative origins for key object classes. - Initial normalization recommendations (what must be cleaned or rationalized before migration).

Supporting material - Read-Only AD Assessment Guide — discovery without changing the directory - Chapter 02 — Analyzing the Client/Server Estate - Identity and Directory Transformation Inventory - GPO-to-Cloud Governance Gaps - Old AD vs New Entra ID — reference for the assessment team

Exit criteria - The team can describe, in concrete terms, what the directory currently “knows” about the organization and what would break if that knowledge disappeared.

### Phase 2 — Target Architecture Definition

Objective: Define the attribute-oriented structure and control-plane model that will replace implicit hierarchy.

Key activities - Specify the attributes that will represent organizational position, lifecycle, and security context. - Define how dynamic membership and scoped policy will be driven from those attributes. - Describe the layered model (Identity → Structure → Policy → Governance) and the role of each layer. - Identify control planes (identity, addressing, policy, telemetry, etc.) and their boundaries. - State the rules for authoritative origin versus derived/subordinate copies. - Document the drift classes that will be monitored (schema, semantic, provenance, authorization, identity, and contention on the authoritative source).

Deliverables - Target architecture description (conceptual, not implementation-specific). - Attribute model and mapping guidance from current structures. - Control-plane diagram or narrative. - Drift taxonomy and detection approach outline. - Provenance and evidence expectations for changes.

Supporting material - Single Source of Truth - From Attributes to Access (dynamic groups) - Delegation Matrix - Change Control and Provenance - Architecture Series

Exit criteria - Domain leads can explain how a given organizational fact will be expressed, how policy will attach to it, and how drift will be detected, without relying on internal decision-record numbers.

### Phase 3 — Domain Playbooks and Wave Planning

Objective: Produce executable playbooks for each in-scope domain and sequence them into waves.

Key activities - For each domain (identity structure, policy, services/addressing, compute/device, access plane): - Define objectives and success measures. - Map current constructs to target constructs. - Identify bridging or coexistence patterns. - Specify entry criteria, exit criteria, and rollback conditions. - Define the evidence that must be produced for each change. - Sequence the domains into waves that respect dependencies (structure before policy, identity before compute, etc.). - Identify any organization-specific constraints that affect sequencing.

Deliverables - Domain playbooks (one per major domain). - Wave plan with sequencing, gates, and rollback triggers. - Evidence checklist applicable to every wave.

Supporting material - Chapter 03 — Analysis → Plan → Delivery - Chapters 04–08 — identity, policy, services, compute and access playbooks - GPO Sunset Program and GPO Parse and Crosswalk - Conditional Access Policy Library - Intune + Azure Arc Modernization - DNS Modernization Guide and PKI Modernization Guide - Test Plans — evidence checklist inputs

Exit criteria - At least the first wave has a complete playbook that a team could execute with existing tools and processes.

### Phase 4 — Pilot / First Wave Execution

Objective: Execute a controlled first wave and validate the change-control and evidence pattern.

Key activities - Select a limited, representative scope for the first wave (recommended: identity structure and dynamic membership for a subset of the organization). - Originate the changes from the designated authoritative source. - Execute under least-privilege / just-in-time elevation. - Close each change with provenance and collect the required evidence. - Detect and classify any drift that appears during or after the wave. - Conduct a lessons-learned review.

Deliverables - Executed first-wave changes with provenance records. - Evidence package. - Drift findings (if any) and remediation notes. - Updated playbooks and wave plan based on lessons learned.

Supporting material - Chapter 09 — Migration Roadmap: Phased Plan, Gates, Rollback - PIM Self-Request with Approval — just-in-time elevation for wave execution - HR-Driven Identity — originating changes from the authoritative source - End User Training Guide

Exit criteria - The organization has demonstrated that a change can originate from the authoritative source, execute under controlled privilege, close with provenance, and be validated against the intended state.

### Phase 5 — Progressive Rollout and Steady-State Governance

Objective: Extend the pattern across remaining domains and establish ongoing drift detection and evidence practices.

Key activities - Execute subsequent waves according to the updated plan. - Expand the attribute model and dynamic constructs as additional domains are brought under the target architecture. - Stand up or refine continuous drift detection against the authoritative origin. - Transition from project-mode change control to steady-state operational governance. - Capture residual risks and any items that remain outside the modernization scope.

Deliverables - Completed domain transformations (or documented residual scope). - Operational drift detection and evidence process. - Final project report with outcomes against success criteria. - Recommendations for ongoing ownership.

Supporting material - Continuous Monitoring Strategy - Gap Closure Register - Training Program and Education Program

Exit criteria - Success criteria from the charter are met or explicitly deferred with rationale. - Ownership for the authoritative origin and drift detection has transferred to steady-state operations.

## 4. Domain Workstreams (Summary)

| Domain | Primary Focus | Typical Dependencies | Suggested Position | Detailed project |
| --- | --- | --- | --- | --- |
| Identity structure | Attribute model, dynamic membership, lifecycle origin | Assessment complete | Early (Wave 1) | Identity Lifecycle & Provisioning |
| Policy | Mapping of existing policy to attribute-driven scope | Identity structure | After identity | Playbooks: GPO Sunset Program, Conditional Access Policy Library |
| Services / Addressing | Naming, IP management, related dependencies | Assessment; may bridge | Parallel or mid | Network & Access Modernization |
| Compute / Device | Device identity and management alignment | Identity structure | Mid to late | Endpoint & Device Modernization |
| Access plane | Token-based / application-aware access patterns | Identity and policy | Later | Network & Access Modernization |

Further detailed projects that run alongside these workstreams: Privileged Access & Administrative Identity, Data Platform Identity Transformation, Continuous Monitoring & Evidence Fabric, and Supply Chain & Software Bill of Materials. Each has a charter and a plan; see Complementary Modernization Projects.

## 5. Governance and Decision Rights

- Sponsor approves scope changes, major sequencing shifts, and acceptance of residual risk.

- Project lead owns the overall plan, wave sequencing, and cross-domain dependencies.

- Domain leads own playbook content, execution readiness, and domain-specific evidence.

- All material changes to the target architecture or authoritative-origin rules require project-lead and sponsor concurrence.

## 6. Risks and Mitigations (Selected)

| Risk | Mitigation |
| --- | --- |
| Incomplete discovery of hidden dependencies | Structured assessment checklist; pilot wave designed to surface unknowns early |
| Competing sources of truth persist | Explicit designation of authoritative origin per object class; drift class for contention |
| Organizational resistance to making authority explicit | Early stakeholder alignment; pilot that demonstrates controlled rather than disruptive change |
| Tooling leads the design | Target architecture and change-control pattern defined before tool selection or configuration |
| Physics / residency limits on centralization | Logical centralization of truth; physical distribution of subordinate copies only |

## 7. Success Measures (Project Level)

- Current-state assessment completed and accepted.

- Target architecture documented and understood by domain leads.

- First wave executed with full provenance and evidence.

- Drift detection approach operational for the domains in scope.

- Residual risks documented and ownership assigned.

- Leadership can describe the modernization path and outcomes without reference to internal technical decision records.

## 8. Immediate Next Actions

- Review and accept this plan against the Project Charter.

- Confirm Phase 0 stakeholders and decision rights.

- Scope the Phase 1 assessment (data sources, access, timeline).

- Identify the candidate authoritative origin(s) for human identity lifecycle events.

- Draft the outline of the target attribute model.

This plan is a project artifact. It incorporates the modernization concepts of authoritative origin, attribute-driven structure, explicit drift, and controlled evidence-producing change. It contains no internal architectural decision record identifiers or substrate-specific document numbers.