# Federal Civilian AD → Entra ID + SQL Estate — Reference Deployment Pattern

End-to-end substrate walkthrough for a mid-size federal agency with two AD forests, a sprawling SQL estate, and a GCC-Moderate destination

Table of contents

# Federal Civilian AD → Entra ID + SQL Estate — Reference Deployment Pattern

Framing pattern, not a fabricated engagement

This page is the canonical engagement pattern for a federal civilian agency migrating Active Directory and its dependent SQL estate to Microsoft Entra ID + M365 GCC-Moderate, end-to-end through the Federal Modernization Program substrate. Specific metrics, agency identifiers, contractor names, and calendar dates are intentionally absent until real engagement material is reviewed and externally releasable. The narrative below is the substrate’s behavior against the archetype, not a deployed-and- attested reference. Status badge in the family index: Framing-Pattern per the Whitepapers status conventions.

## Engagement archetype

A federal civilian agency of approximately fifty thousand users operates two Active Directory forests — one for the agency proper, one inherited from a component organization absorbed in a prior reorganization — joined by a transitive trust that nobody fully documented and that nobody currently owns. The forests collectively hold roughly seventy thousand computer accounts, twelve thousand groups, several thousand orphaned service accounts whose original owners have rotated out, and a SQL Server estate of approximately ninety instances spread across regional offices, the agency headquarters data center, and three relocated workloads now running on Azure Arc-enrolled hardware. The agency is under explicit modernization pressure from OMB M-22-09 (Zero Trust), CISA BOD 25-01 (logging and visibility), and a forthcoming FedRAMP 20x continuous-monitoring expectation. It has chosen Microsoft 365 GCC-Moderate as the destination identity plane and is committed to consolidating its data estate around the Fabric + OneLake + Purview Azure SSOT stack.

The agency’s compliance posture today is recognizable. Its previous ATO package was assembled retrospectively over a twelve-month window by a system integrator who is no longer on contract. The directory’s SPN inventory exists only in spreadsheets that were last refreshed two years ago. The SQL estate’s lineage and ownership are documented in component-level binders that disagree with each other on basic attribution questions. The agency has the right tools — Entra Connect, Intune, Defender, Purview Premium — but no shared canon for what those tools should be told about the agency’s organizational structure.

This is the engagement pattern the Federal Modernization Program is built for, and the substrate’s behavior across the five phases below is what this case study illustrates. For the federal mandate alignment that makes this work necessary, see the Federal SSOT Alignment whitepaper.

## Phase 1 — Discover

The first substrate action is to make the current state of the agency’s identity infrastructure honest. The AD survey adapter at src/fmp/adapters/modernization/active_directory/survey.py reads both forests in read-only mode and emits an ADSurveyReport that enumerates the eleven AD object types catalogued in src/fmp/modernization/directory-migration/ad-dependency-inventory.md: users, computers, service accounts, security groups, GPOs, DNS and DHCP records, PKI artifacts, RADIUS configurations, LDAP-dependent applications, Kerberos SPNs, and the trust relationships between the two forests. The survey is the same one that produced the substrate’s test fixtures; it is not a per-engagement script.

The service-account scan codified in Spec3-D1.1 (FMP_139) runs as part of the discovery pass. It produces a service-accounts inventory with delegation classification, AdminCount status, and a per- account risk score that flags ADCS-dependent SPNs and unconstrained Kerberos delegation as critical pre-migration findings. The agency in this archetype has roughly four hundred service accounts with at least one SPN registration; the survey flags approximately sixty of them as critical and another hundred as high-risk.

The SPN inventory artifact introduced in PR #395 captures the agency’s MSSQLSvc/* registrations with a phase: pre_migration tag, the discovery timestamp, and the organizational attribution resolved via the service- account principal (preferred) or the hosting computer (fallback). Approximately eighty of the agency’s ninety SQL instances resolve cleanly; ten emit DRIFT-IDENTITY findings because their service accounts predate any organizational attribution the agency can defend. These ten are flagged as P2 conditions that must be remediated through explicit owner reassignment before migration begins.

The discovery phase ends with a readiness bundle, HMAC- signed, ready to be consumed by the next phase. The bundle’s provenance section names the substrate canon documents it derives from and binds the bundle to the agency’s specific run.

## Phase 2 — Normalize

The discovery output is not yet authoritative. The agency’s two forests carry overlapping organizational hierarchies — both have an “Operations” OU at the top level, but the Operations group in forest A is a completely different population than Operations in forest B, and the merged tenant cannot tolerate that ambiguity. The organizational registry, populated from the discovery output and refined through the agency’s organizational chart of record, becomes the source of truth for organizational position. The collision is resolved in the registry, not at the group level.

The normalization phase emits DRIFT-IDENTITY findings for principals that the registry cannot attribute. In the archetype, roughly two thousand users and several hundred service accounts fall into this bucket on the first pass. Each finding includes a suggested organizational attribution candidate derived from OU placement, manager chain, or computer-account attribution; the substrate does not auto-assign because organizational attribution is load-bearing for every downstream policy decision. The agency’s governance team resolves these findings through the change-request workflow before the next phase begins.

## Phase 3 — Map

Mapping translates the X.500 / LDAP governance model encoded in AD into the attribute-driven model Entra ID requires. The eight adapter interfaces under src/fmp/modernization/directory-migration/adapters/ each carry an explicit contract for one of the AD-adjacent surfaces that must be re-governed: IPAM, PKI, RADIUS, LDAP-proxy, sync-engine, device-management, NTP, DFS, and the SQL Server workload adapter introduced in PR #397 (adapters/sql-server/sql-server-adapter-interface.md). Each adapter declares its class, mission-class, and gcc-boundary in migration-adapter-registry.yaml and is schema-validated in CI.

For this archetype, the most operationally significant adapters are PKI (the agency’s ADCS hierarchy hosts dozens of templates whose auto-enrollment must move to Intune SCEP without expiring certificates mid-cutover) and the SQL Server adapter (the ninety instances need SPN re-registration coordinated with service-account migration). The LDAP-proxy adapter covers the agency’s approximately forty LDAP-bound internal applications. RADIUS is critical because the agency’s network access requires 802.1X EAP-TLS that depends on the same ADCS hierarchy PKI governs.

## Phase 4 — Migrate

The migration itself is executed as a sequence of provenance-chained events. Each adapter operation carries an immutable record of the principal that requested the change, the source of authority, the canon document version the change was made against, and the verification hash of the resulting state. The schema contract ssot-mutation: never is enforced: adapters consume and emit against the canon, never replace it. The certificate-anchored: true contract requires every operation to be signed by an identity certificate; the agency’s deployment uses the same ADCS hierarchy the PKI adapter governs for substrate operations as well as user authentication.

During migration, drift findings emerge in real time. The drift taxonomy formalized in 16_DriftDetectionStandard §2 surfaces five classes:

- DRIFT-SCHEMA — a recently-migrated computer object has an attribute encoding that does not match the canon schema version

- DRIFT-SEMANTIC — an organizational attribute value drifts into a deprecated geographic OU encoding pattern

- DRIFT-PROVENANCE — a state change appears with no recorded provenance event in the chain (this is a P1 condition — the migration is halted and the change is investigated before resuming)

- DRIFT-AUTHZ — a Conditional Access policy in Entra ID contradicts the NIST 800-63 AAL requirement encoded for that principal in the COR

- DRIFT-IDENTITY — a principal exists in the migrated tenant with no resolvable canon counterpart (orphan migration artifact)

The agency in this archetype encounters approximately three hundred drift findings across the migration window, the majority P3 and P4 (auto-remediated per §4 of the drift standard). The single P1 event in a representative cycle is a DRIFT-AUTHZ against a Finance service account whose post-migration role assignment exceeds the AAL-3 requirement the canon records; the substrate halts the migration of the dependent SQL instance until the role assignment is reduced.

## Phase 5 — Validate

Post-migration, the SPN inventory is captured a second time, this time with phase: post_migration. The substrate’s drift comparison applies the four SPN-drift conditions catalogued in 16_DriftDetectionStandard §7.1:

| Condition | Drift class | Severity | Detection |
| --- | --- | --- | --- |
| SPN present pre-migration, absent post-migration | DRIFT-IDENTITY | P1 | Set-difference between phase-tagged inventories |
| SPN host or port changed without provenance | DRIFT-PROVENANCE | P2 | Same (service_class, principal_name) key, different host or port |
| SPN owner changed without recorded migration event | DRIFT-AUTHZ | P1 | Same SPN, different principal, no transition record |
| SPN in AD but no Entra Kerberos delegation | DRIFT-IDENTITY | P2 | Cross-reference fails between AD and workload-identity federation |

For this archetype, approximately three SPNs surface as P1 DRIFT-IDENTITY findings (SPNs whose re-registration step was skipped during the SQL Server adapter’s migration sequence). These become halt-and-alert conditions per the severity model in 16_DriftDetectionStandard §3; the agency’s operations team re-registers the SPNs against the migrated principals and re-runs the post-migration inventory until zero P1 findings remain.

## The Azure SSOT bridge

With the identity migration complete, the agency’s data plane joins the substrate.

On the user plane, the existing Adaptive Policy Scopes target each segment’s labels, DLP rules, retention schedules, and eDiscovery custodian queries. On the data plane, Fabric Domains are created to mirror the organizational hierarchy; the agency provisions one domain per FabricDomainBoundary-flagged node, and each Fabric workspace is assigned to the domain that matches the workspace’s owning segment. The ninety SQL instances are registered into the Purview data map under collections keyed on custom metadata; the eighty-five that completed migration cleanly are mirrored into OneLake under the matching Fabric Domain workspaces. The remaining five — instances whose post-migration drift is still being remediated — are deferred until the drift cycle closes.

The Purview Information Protection telemetry constraint catalogued in B.1.1 §3 applies: every sensitivity-label trust assertion in the GCC-Moderate tenant inherits the boundary’s verification gap. The substrate’s role at this boundary is not to remediate it (it is structural) but to record the compensating controls the agency has put in place and verify them continuously.

## The Evidence Bundle the assessor consumes

At any point after Phase 2 begins, the agency can produce an Evidence Bundle from the substrate’s accumulated artifacts. The bundle includes:

- The readiness bundle from each phase, HMAC-signed

- Both phase-tagged SPN inventories (pre- and post-migration) with drift comparison results

- The provenance chain of every adapter operation

- All drift findings, each with severity, drift class, and remediation evidence per the contract in 16_DriftDetectionStandard §4

- The B.1.1 three-way GCC-Moderate compliance-conflict finding (GCC-BOUNDARY-3WAY-001) with the agency’s specific compensating- controls catalogue

- The Purview collection registration state with attribution per asset

- The Fabric Domain assignment state with per-workspace attribution

This is the artifact the 3PAO consumes during the next FedRAMP cycle. It is produced as a byproduct of operations rather than assembled retrospectively in a twelve-month window. The agency’s authorizing official sees the substrate’s state at any moment, not a stale snapshot.

## What survives the engagement

The deliberate point of the substrate is that the canon, the schemas, the drift findings, and the Evidence Bundle do not belong to whichever system integrator delivered the migration. They belong to the agency. The next FedRAMP cycle consumes the existing canon rather than rebuilding it. A subsequent SI engagement — for the next modernization program, the next directory consolidation, the next data-governance expansion — anchors on the substrate’s state rather than starting from zero. This is the cost-shape inversion the Federal SSOT Alignment whitepaper §6 describes: re-engagement consumes canon; it does not rediscover it.

The substrate behaviors a real engagement would document and that this framing pattern is structured to receive:

- Time-to-evidence under the substrate vs. the prior twelve-month baseline

- Drift-finding rate over the migration window, decomposed by class and severity

- SPN drift incidence per ten instances migrated

- B.1.1 compensating-controls verification cadence and false-positive rate

- Purview policy-decision count whose trust assertion is now backed by continuously-verified identity state

When real engagement material becomes externally releasable, those metrics replace the prose-level claims above. Until then this page is the canonical archetype the substrate is built against and the shape the Evidence Bundle is produced into.

## Cross-references

- Federal SSOT Alignment whitepaper — federal mandate alignment over the identity layer

- B.1 GCC-Moderate Boundary Model — abstract boundary model

- B.1.1 Three-Way GCC-Moderate Compliance Conflict — TIC 3.0 × Zero Trust × FedRAMP 20x finding

- Drift Detection Standard — drift taxonomy, severity model, and §7.1 SPN drift detection

- Directory Migration README — discovery and inventory artifacts

- SQL Server Adapter Interface — DM_090 adapter contract

- Identity Modernization — Case Study — identity-plane case-study companion

- Cloud Boundary — Case Study — GCC-Moderate boundary establishment companion