# Directory Migration Adapters

Everything Active Directory Was Holding Together

2026-04-19

Table of contents

## The Hidden Surface

When people say “migrate off Active Directory,” they mean move users to Entra ID. But Active Directory was not just an identity store. It was the implicit governance model for every network service in the enterprise:

- DNS — AD-integrated DNS zones, SRV records for domain controllers

- DHCP — Scope-to-subnet-to-OU mappings

- PKI — Active Directory Certificate Services, auto-enrollment via GPO

- RADIUS — Network Policy Server authenticating against AD groups

- LDAP — Hundreds of applications doing LDAP binds to domain controllers

- Device Management — SCCM collections querying AD, GPO-based device policy

- Time Services — Every domain-joined machine syncing NTP from the PDC emulator

- File Services — DFS namespaces resolving through AD domain names

Migrating users to Entra ID without migrating these services is not a migration — it is a liability. The Directory Migration canon provides a governed adapter interface for each of these eight service categories.

## Adapter Priority Matrix

| ID | Adapter | Priority | Risk If Ignored |
| --- | --- | --- | --- |
| DM_010 | IPAM (DNS/DHCP) | HIGH | DNS resolution failure, rogue DHCP |
| DM_020 | PKI / Certificate Services | CRITICAL | Silent auth failure weeks post-migration |
| DM_030 | RADIUS / 802.1X / VPN | CRITICAL | Network access failure |
| DM_040 | LDAP Proxy | CRITICAL | Silent application auth failure — largest hidden surface |
| DM_050 | Sync Engine (Entra Connect) | HIGH | Permanent AD dependency |
| DM_060 | Device Management | HIGH | Non-deterministic policy application |
| DM_070 | NTP / Time Services | MEDIUM | Kerberos clock skew failures |
| DM_080 | DFS / File Services | MEDIUM | Silent UNC path failure |

Three adapters are CRITICAL — they must be addressed before any AD infrastructure can be decommissioned: PKI, RADIUS, and LDAP.

## IPAM (DNS / DHCP / IP Management)

Document: DM_010 | Priority: HIGH

AD-integrated DNS is the most visible dependency. Every domain-joined machine resolves domain controller locations through SRV records (_kerberos._tcp, _ldap._tcp, _gc._tcp). AD retirement requires migrating these zones to standalone DNS.

Required capabilities:

- Full zone export as canonical snapshot for drift detection baseline

- SRV record migration (_kerberos, _ldap, _gc)

- Side-by-side operation with AD-integrated DNS during hybrid window

- DHCP scope inventory and rogue DHCP detection

Registered implementations: InfoBlox NIOS (FedRAMP authorized), BlueCat Address Manager, Generic RFC-compliant IPAM

## PKI / Certificate Services

Document: DM_020 | Priority: CRITICAL | Risk: Silent auth failure weeks post-migration

Active Directory Certificate Services (ADCS) is deeply embedded in federal environments. Smart card / PIV / CAC authentication depends on it. Auto-enrollment policies flow through Group Policy. The entire certificate chain is anchored in AD.

The failure mode is insidious: certificates work fine until they expire. If the replacement CA is not operational before the first expiry wave, authentication fails silently across the organization — weeks or months after the migration was declared “complete.”

Required capabilities:

- Full certificate inventory (issued, pending, revoked, expired)

- Certificate-to-identity binding (who owns each cert)

- Expiry timeline export (90/180/365-day windows)

- CA hierarchy mapping (root, issuing, subordinate chains)

- Smart card / PIV / CAC certificate inventory (federal critical)

- Auto-enrollment migration from GPO to Intune/SCEP/EST

Migration sequence:

- Inventory all issued certificates and expiry dates

- Map certificates to identity objects

- Establish replacement CA before any AD retirement begins

- Migrate auto-enrollment to Intune/SCEP/EST

- Validate certificate chain through new CA

- Retire ADCS only after all renewals confirmed through new CA

Registered implementations: ADCS (migration source), DigiCert, Entrust, Entra CBA

## RADIUS / Network Policy Server

Document: DM_030 | Priority: CRITICAL | Risk: Network access failure pre-migration completion

Windows Network Policy Server (NPS) authenticates 802.1X wired/wireless, VPN, and dial-up connections against Active Directory groups. Every access point, VPN concentrator, and managed switch that uses RADIUS is an AD dependency.

If NPS goes down before the replacement RADIUS is validated, users cannot connect to the network. This is not a degraded experience — it is a total access failure.

Required capabilities:

- Inventory all NPS policies (Connection Request, Network, Health)

- Map NPS policies to AD group dependencies

- Identify all RADIUS clients (APs, VPN concentrators, switches)

- 802.1X certificate profile and EAP method inventory

- Policy translation from AD groups to Entra ID dynamic groups

- Side-by-side validation before cutover

Migration sequence:

- Inventory all RADIUS clients and NPS policies

- Map all NPS AD group dependencies to Entra ID equivalents

- Deploy replacement RADIUS (Cisco ISE / ClearPass / Entra proxy)

- Validate in parallel — both NPS and replacement serving simultaneously

- Cut over RADIUS clients to new server

- Decommission NPS only after 30-day validation window

Registered implementations: NPS (migration source), Cisco ISE, Aruba ClearPass, Entra RADIUS Proxy

## LDAP Proxy

Document: DM_040 | Priority: CRITICAL | Risk: Silent application auth failure — largest hidden surface

LDAP is the largest hidden AD dependency. Applications that were deployed 10-15 years ago do LDAP binds to domain controllers for authentication. Nobody maintains an inventory of these applications because nobody had to — AD was always there.

The discovery phase for LDAP is the longest of any adapter because you cannot migrate what you cannot see, and you cannot see LDAP dependencies without passive traffic analysis.

Required capabilities:

- Network traffic analysis: identify all hosts making LDAP binds to DCs

- Service account inventory for LDAP binds

- Application-to-LDAP dependency map

- Query analysis (what attributes are being read)

- Bind type inventory (simple, SASL, certificate-based)

- Attribute mapping (AD names to Entra ID equivalents)

Migration sequence:

- Deploy passive LDAP traffic monitor on DC network segment

- Run 30-day discovery window — capture all LDAP bind sources

- Build application-to-LDAP-dependency map

- Deploy LDAP proxy (Entra Domain Services or standalone)

- Validate each application against proxy

- Cut over applications in waves — never all at once

Registered implementations: Entra Domain Services, Generic LDAP Proxy

## Sync Engine (Entra Connect)

Document: DM_050 | Priority: HIGH | Risk: Permanent AD dependency if lifecycle unmanaged

The sync engine is the bridge between AD and Entra ID — and it is also the tether that keeps AD alive. As long as the sync engine runs, AD is a production dependency. The sync engine is not retired until every other adapter has been migrated.

Retirement criteria (ALL must be true):

- All users provisioned from authoritative HR source (not AD sync)

- All groups migrated to dynamic or Entra-managed

- All applications off on-prem AD authentication

- All devices managed by Intune (no AD dependency)

- All service accounts migrated to Entra service principals

- ADCS replaced; DNS migrated; RADIUS migrated; LDAP apps validated

## Device Management

Document: DM_060 | Priority: HIGH

SCCM collections query AD. Group Policy Objects flow through the OU tree. Co-management workloads split responsibility between SCCM and Intune. The device adapter governs the transition from AD-dependent device policy to Intune-native management.

Key capability: Run Group Policy Analytics to identify GPO settings without Intune equivalents before migrating any workload.

## NTP / Time Services

Document: DM_070 | Priority: MEDIUM

Every domain-joined machine syncs time from the PDC emulator. Kerberos allows a maximum 5-minute clock skew. If domain controllers are decommissioned without redirecting NTP, Kerberos authentication fails across the environment.

Fix: Deploy Intune policy redirecting w32tm to external NTP sources (time.windows.com) before any DC decommission.

## DFS / File Services

Document: DM_080 | Priority: MEDIUM

DFS namespaces resolve through AD domain names. Domain-based DFS namespaces (\\domain\share) fail silently when the domain is retired. Migration targets: SharePoint Online, Azure Files, or standalone DFS with non-AD names.

## Post-Migration Validation

After all adapters are migrated, the [Validation Checklist (DM_090)] provides a comprehensive pass/fail gate for each service category before AD infrastructure decommission is authorized.

Source

Full adapter interface specifications with vendor manifests: src/fmp/modernization/directory-migration/adapters/