# Book 02 — Identity & Directory

Active Directory to Entra ID — Modernization Workbook, combined edition

Table of Contents

Book 02 — Identity & Directory: Active Directory to Entra ID

Status — draft book

Why, what, who, how

Reading paths

Where this book sits in the workbook

Chapter 01 — Why Identity Matters

In this chapter

The access decision moved to identity

What twenty-five years of Active Directory accumulated

Why the move to Entra ID is forced

What a lift-and-shift puts at risk

An illustrative starting point

The argument in brief

Continue the book

Chapter 02 — The Structural Problem

In this chapter

Hierarchy is the governance model

Two limits decide whether the mapping works

Every delegation concept needs an explicit counterpart

The session-versus-telemetry divide

Why it breaks at the FedRAMP boundary

Why nobody wants to own it

The migration is a governance event

Continue the book

Chapter 03 — Active Directory and Entra ID, Side by Side

In this chapter

The shift in one paragraph

The two worlds at a glance

Protocols: what each side speaks

Where the old protocols stand in 2026

Cryptography

Languages and tooling

Illustrative code

Infrastructure, pipelines, and compliance as code

The eight core concepts of directory migration

Why the shift matters

Continue the book

Chapter 04 — The Hidden Migration Surface

In this chapter

The eleven AD dependency object types

The adapter interface

The adapter priority matrix

Adapter by adapter

Illustrative code

The six migration phases

Adapter registration

Post-migration validation

The transformation inventory

Continue the book

Chapter 05 — Delegation Without OUs

In this chapter

What administrative units are

The three-tier model

Administrative unit registry

Role assignment matrix

Illustrative code

Restricted management: a per-AU decision

Delegation principles

Drift detection

Continue the book

Chapter 06 — Who Owns the Migration

In this chapter

The people

The tools

Ownership in practice

Continue the book

Chapter 07 — Read-Only Discovery

In this chapter

What a standard account can read

Where the default read boundary sits

Recording what read-only discovery couldn’t see

The delegation request

Running the assessment safely

Checklist

Continue the book

Chapter 08 — Assessing the Forest

In this chapter

What the assessment covers

Prerequisites

Illustrative code

Forest and domain topology

OU hierarchy and delegation

Group Policy inventory and analysis

DNS infrastructure

Certificate Services (AD CS)

Computer objects

Users, groups and service accounts

Trust relationships

The assessment pipeline

Git integration for assessment data

Security and least privilege

Troubleshooting

Output schema reference

Quick reference

Continue the book

Chapter 09 — Building the Entra ID Target

In this chapter

Purpose and scope

Decomposing the Active Directory identity landscape

Design principle: placement versus attributes

The Entra ID identity architecture

Licensing assumption

Choosing and configuring the sync engine

Recommendation: Cloud Sync unless a Connect-only requirement applies

One active Connect Sync server per tenant

Recommendation: PHS everywhere

Migrating groups

Illustrative code

Modernizing service accounts

Privileged access

The Conditional Access framework

The full library is in Book 04

Never enforce untested policies on all users

Continue the book

Chapter 10 — Migrating and Governing

In this chapter

Identity governance and lifecycle

Cross-tenant and B2B collaboration

Authentication modernization

Illustrative code

The compliance amendment: phishing-resistant authenticators and privileged access

Monitoring, audit, and compliance

The migration execution playbook

Git-based drift detection

Troubleshooting reference

Continue the book

Chapter 11 — Reference Deployment

In this chapter

A framing pattern, not a real engagement

The archetype

Phase 1 — Discover

Phase 2 — Normalize

Phase 3 — Map

Phase 4 — Migrate

Phase 5 — Validate

Illustrative commands

The Azure SSOT bridge

The evidence bundle the assessor consumes

What survives the engagement

Where to go next

Continue the book

Appendix A — Federal Requirements Crosswalk

In this appendix

The assessment in one paragraph

The baseline

The three filters

How to read the crosswalk

The crosswalk: identity controls

Sequencing

Federal mandates behind the baseline

The identity modernization specification

NIST SP 800-53 Rev. 5 control mapping

Continue the book

Appendix B — Forest Assessment Module

In this appendix

Illustrative code

Corrections to the source design

C.1 Module manifest (FMPADAssessment.psd1)

C.2 Module file (FMPADAssessment.psm1)

C.3 Installation

C.4 Output schema reference

Continue the book

Appendix C — Identity Assessment Module

In this appendix

Attribute mapping reference

Conditional Access policy templates

Placeholders and endpoints

Illustrative code

The FMPIdentityAssessment module

Continue the book

# Book 02 — Identity & Directory: Active Directory to Entra ID

## Status — draft book

This book consolidates twenty-two earlier workbook pages on identity and directory modernization (whitepapers, operational guides, reference architecture, learning pages and framing case studies) into one ordered book. Every external claim was checked against a primary source on October 20, 2026 and carries a footnote. The earlier pages are kept in the repository’s archive/b02-identity/ folder, and their old addresses forward to the chapters that replaced them.

15-minute presentation: the Why / What / Who / How deck and its narrated, self-running version are in the repository under presentations/b02-identity/.

Every access decision in a modern federal estate starts with a question about identity: who is this, is the claim about them still true, and what is this device or workload allowed to do? For twenty-five years Active Directory answered those questions inside the network perimeter, and it quietly took on much more: DNS, certificates, Wi-Fi and VPN authentication, file shares, time, application logins, and the organization chart encoded as OUs. Zero Trust moves the decision to the identity provider and evaluates it on every request. Moving from Active Directory to Entra ID is therefore not a directory upgrade. It decides whether every later control works.

## Why, what, who, how

|  | Question | Chapters |
| --- | --- | --- |
| Why | Why does identity matter, and why can’t AD simply be lifted into the cloud? | 01, 02 |
| What | What actually changes: the concepts, the hidden dependencies, the delegation model | 03, 04, 05 |
| Who | Who decides, who does the work, and which tools do what | 06 |
| How | Discover, assess, build the target, migrate and govern, with a reference deployment | 07, 08, 09, 10, 11 |

Appendices: A — Federal requirements crosswalk · B — Forest assessment module · C — Identity assessment module

## Reading paths

- Executives (20 minutes): Chapters 01, 02 and 06, or the 15-minute presentation.

- Architects: Chapters 01–06, then 11, then Appendix A.

- Engineers running the work: Chapters 03–05 for the model, then 07–10 with Appendices B and C at hand.

## Where this book sits in the workbook

This is Book 02 of the Modernization Workbook. The workforce side of identity, with HR as the source of authority, is in HR-Driven Identity. The SQL Server estate’s move off Windows authentication is in the SQL Server Identity Transformation series.

# Chapter 01 — Why Identity Matters

Once the network stops deciding who gets in, the directory decides, and most directories were never built to carry that decision.

## In this chapter

Why federal Zero Trust policy makes identity, not the network, the place where every access decision is made. What more than twenty-five years of Active Directory accumulated, and why nobody owns it. Why the move to Microsoft Entra ID is forced, and what exactly is doing the forcing. What is at stake if the forest is synchronized into the cloud as it stands.

## The access decision moved to identity

For most of the directory era, the network made the first access decision. A user inside the perimeter reached what the perimeter allowed, and the directory’s job was to answer “who is this?” for systems that were already on the same network. Federal direction has moved that decision off the network and onto identity.

- OMB M-22-09 sets the federal Zero Trust strategy. It requires agencies to use centralized identity management systems for agency users, to enforce multifactor authentication at the application layer rather than the network layer, to require phishing-resistant MFA for staff, contractors and partners, and to consider at least one device-level signal alongside identity when authorizing access. It states that federal applications can’t rely on network perimeter protections, and that users should log into applications rather than networks. It also directs agencies to consolidate identity systems so that protections and monitoring apply consistently.

- NIST SP 800-207 defines the architecture. Zero trust grants no implicit trust based on network location or asset ownership. Access to each resource is granted per session, decided by dynamic policy that includes the client’s identity and the attributes the enterprise assigns to it, and authentication and authorization are re-evaluated continually rather than once at the door.

- CISA’s Zero Trust Maturity Model makes identity the first of its five pillars (Identity, Devices, Networks, Applications and Workloads, Data) and defines an identity as an attribute or set of attributes that uniquely describes a user or entity. At its optimal level, an agency validates identity continuously, not only when access is first granted.

M-22-09 is explicit about where the data behind those decisions comes from. Zero Trust needs metadata about the user at the policy enforcement point, and the enterprise identity system maintains that metadata and keeps it correct when a person leaves or changes position, drawing on human resources, contract management and personnel security systems. The identity provider becomes the policy decision point for the whole estate. Whatever it believes about a person, a group or a device is what the estate enforces.

Identity is the control plane: federal Zero Trust policy moves the access decision from the network to the identity provider, which decides each request from the directory data behind it.

That is the sense in which identity is the control plane. A wrong attribute used to produce a wrong entry in the phone book. Under Zero Trust it produces a wrong group, a wrong policy match and the wrong access, enforced consistently everywhere. A stale account used to be reachable only from inside the building. Under Zero Trust it is a valid identity that can be used from anywhere the applications are published. The workforce side of that dependency, the employee data that identity attributes are projected from, is the subject of HR-Driven Identity. This book is about the directory those attributes land in.

## What twenty-five years of Active Directory accumulated

Active Directory arrived with Windows 2000, and with it the organizational unit: a hierarchical container inside a domain, used to group users, computers and groups so that administrative rights could be delegated and policies applied to them as a unit. That design worked, and organizations built on it for a quarter of a century. Most of them, federal agencies included, never ended up with a clean, well-governed directory. What they have is decades of organic growth.

| What accumulated | How it looks today | Why it matters now |
| --- | --- | --- |
| Regional domain controllers and domains | Never fully consolidated; some exist because a region once needed its own | Each is a separate administrative boundary to discover and reconcile |
| OUs that mirror old organization charts | Containers named for offices, programs and reorganizations that no longer exist | Delegation and policy still follow the old structure |
| Group Policy layered on Group Policy | Inherited settings whose original purpose nobody can state | Policy intent has to be recovered before it can be rebuilt |
| Service accounts nobody remembers creating | Enabled, often privileged, frequently with non-expiring passwords | Each is a dependency or a standing risk, and usually both |
| Trusts created to make something work quickly | Cross-forest and cross-domain trusts with no current owner | Entra ID has no equivalent concept to carry them into |

The consolidation projects that followed often didn’t clean this up. They moved it behind a load balancer and added a layer on top. And nobody wants to own it. Active Directory became infrastructure that everything depends on and nobody champions. It runs until it doesn’t.

It is also the target. CISA, with the Australian Signals Directorate and other partners, published joint guidance in September 2024 on detecting and mitigating Active Directory compromises. It describes Active Directory as the most widely used authentication and authorization solution in enterprise networks and explains how attackers use it to escalate privilege toward the most sensitive objects in the directory. An estate whose access decisions now flow from identity can’t treat its oldest identity store as background plumbing.

## Why the move to Entra ID is forced

The usual worry is that Microsoft will retire Active Directory and force the migration. That isn’t what is happening, and planning against the wrong threat leads to the wrong plan. Microsoft states that it continues to support and enhance Windows Server Active Directory for on-premises identity. The forcing comes from two directions at once: federal policy, described above, and the direction of Microsoft’s own identity investment, which is moving every hybrid component toward the cloud.

| Signal | What Microsoft states | What it means for the migration |
| --- | --- | --- |
| Synchronization | Cloud Sync is replacing Entra Connect Sync, which will be retired once Cloud Sync reaches full functional parity. Microsoft announced that, beginning in July 2026, it would notify each customer of its own transition window, in phases that start with tenants whose needs Cloud Sync already meets. | The sync engine most hybrid estates run today is on a published replacement path |
| Federation | Microsoft recommends migrating from AD FS to cloud authentication and recommends password hash synchronization for it. It identifies federation trusts as one of the two main paths by which an on-premises compromise reaches the cloud. | AD FS is a dependency to retire, not a component to modernize in place |
| Legacy protocols | All versions of NTLM were deprecated in June 2024. NTLMv1 is removed in Windows 11 version 24H2 and Windows Server 2025. Microsoft’s cloud-first guidance says new applications that use NTLM, Kerberos or LDAP should be exceptions. | Applications that depend on the oldest protocols are on a clock |
| Source of authority | Converting synced users from Active Directory to cloud-managed users became generally available in January 2026, supported by both Connect Sync and Cloud Sync. Groups can be converted the same way. | Moving authority to the cloud is now a supported, object-by-object operation, not a rebuild |
| Target posture | Microsoft models the journey as five states (cloud attached, hybrid, cloud first, AD minimized, 100% cloud) and describes it as a multi-year effort for large organizations. | The question is no longer whether to move, but how far and in what order |

There is precedent for this pattern, and it is more precise than “Microsoft forces migrations.” Skype for Business Online was retired on July 31, 2021, after two years’ notice, while on-premises Skype for Business Server remained supported. Exchange Server 2016 and 2019 reached end of support on October 14, 2025. The options Microsoft lists are migrating to Microsoft 365 or upgrading on-premises to Exchange Server Subscription Edition. In each case the on-premises path narrowed and the new capability went to the cloud, and organizations that had already cleaned up their environments made the transition far more easily than those that hadn’t.

What makes the identity version harder is that the gap is structural, not only technical. An organization whose authority model depends on the OU hierarchy can’t script its way into a flat tenant. It has to rebuild that model in a different paradigm, and it can only do that if it knows what the old model was. In most estates that knowledge is tribal, if it exists at all. Chapter 02 explains the structural mismatch in detail.

## What a lift-and-shift puts at risk

The tempting plan is to install a sync engine, synchronize the forest as it stands, and call the identity layer migrated. The sync works. What it carries across is the problem.

Two ways out of the forest: a lift-and-shift synchronizes the accumulated estate and its risks into the tenant, while a governed migration discovers what Active Directory encodes and rebuilds it explicitly in Entra ID.

| Carried across as it stands | Consequence in Entra ID |
| --- | --- |
| OU-based delegation and Group Policy | Neither has a landing place. Entra ID has no OU tree, so delegation and policy have to be rebuilt as administrative units, scoped roles, dynamic groups and Conditional Access, or they are simply lost (Chapter 05) |
| Privileged accounts mastered on-premises | If a synchronized account holds cloud privileges, an attacker who gets its on-premises credentials can use them in the cloud. Microsoft’s guidance is that privileged cloud roles use cloud-only accounts and that synchronized objects hold no privileges beyond those of a user |
| Groups and attributes that drive access | On-premises membership or attribute manipulation can change cloud group membership, including dynamic groups, so owners of groups used for access have to be treated as privileged |
| Federation through AD FS | A compromised token-signing certificate lets its holder impersonate any user in the cloud tenant |
| Stale and orphaned accounts | Accounts that were reachable only from inside the perimeter become valid cloud identities, usable wherever the applications are published |
| Undocumented dependencies | Kerberos-dependent services, Windows-authenticated SQL Server, LDAP-bound applications and certificate chains break silently when the directory underneath them changes (Chapter 04) |

The last risk is the quiet one. If the program moves the objects but not the governance, it inherits the OU-driven model in a platform that can’t express it. The organization pays for a cloud identity platform and runs it as a copy of the old directory, losing most of what made the move worth doing: access computed from attributes, scoped and time-bound privilege, and evidence of who has access and why.

## An illustrative starting point

The workbook’s case studies are framing patterns, not real engagements. They describe the situation a program should expect, with no agency names or metrics. Two patterns frame this book.

- A large, multi-forest directory. An agency runs Active Directory at scale: more than 100,000 identities, a multi-forest topology, and an OU hierarchy that is a decade old and runs to several thousand OUs. Group memberships are maintained by hand, and movers are handled by ticket-driven re-permissioning. SIEM, the identity provider, IP address management and the authorization package each consume identity claims inconsistently. The authorization package describes the intended controls, but nobody can reproduce what the directory actually enforces at a given moment. The program has chosen its migration tooling. It hasn’t addressed the inversion from placement in a hierarchy to access computed from attributes.

- A twenty-year forest with SQL Server sprawl. A civilian agency runs a twenty-year-old forest alongside twenty years of SQL Server instance and database growth. Service principal names, service accounts and LDAP-dependent applications have never been inventoried, and evidence that services kept working through past changes was assembled after the fact. The directory and the database estate share one authentication boundary, so neither can move safely without the other.

Neither pattern is unusual. Both show why the migration can’t be scoped as a directory project, and both reappear in the How chapters as the estate that discovery (Chapter 07) and assessment (Chapter 08) are built to read.

## The argument in brief

- Federal Zero Trust policy moves the access decision from the network to identity, and the identity provider enforces whatever it believes about people, groups and devices.

- The identity data most agencies hold is a twenty-five-year accumulation of OUs, policy layers, service accounts and trusts that nobody owns and few have documented.

- Active Directory isn’t being retired, but Microsoft’s synchronization, federation, protocol and source-of-authority direction all point to the cloud, and federal policy requires the outcome that direction delivers.

- A lift-and-shift synchronizes the accumulated risk into the tenant and discards the governance that the hierarchy carried.

- The migration therefore has to be treated as a governance event: discover what the directory encodes, rebuild it explicitly, and prove it survived. Chapter 02 shows why that rebuild is structural, and Chapter 06 assigns who owns it.

## Continue the book

Book index · Next: Chapter 02 — The Structural Problem →

# Chapter 02 — The Structural Problem

Active Directory governs an object by where it sits; Entra ID governs it by what the object says about itself, and nothing translates one into the other automatically.

## In this chapter

How the forest, domain, OU and Group Policy hierarchy carries an organization’s governance, and what a flat tenant offers in its place. The two limits that decide whether the mapping works. The session-versus-telemetry divide that makes hybrid identity break at a continuous-verification boundary such as FedRAMP’s. Why the migration is a governance and single-source-of-truth event, and the capabilities that treatment requires.

## Hierarchy is the governance model

Active Directory’s structure isn’t only technical. Forests and domains form the outer layers of the hierarchy, and within each domain the organizational unit, introduced with Windows 2000, groups users, computers and groups so that administrative rights can be delegated and policies applied to them as a unit. Kerberos ticket policy is defined per domain and enforced by the domain’s key distribution center. Group Policy objects are linked to sites, domains and OUs, and by default their settings are inherited and cumulative down the tree, with the container closest to the object taking precedence. Their contents are stored in the directory and in each domain controller’s SYSVOL folder and replicate between domain controllers.

The result is that an object’s position decides how it is governed. Move a user into a different OU and its delegated administrators, inherited policies and often its access all change, without anyone editing the user. Over twenty-five years, organizations built operational process on that property: help desk scope by regional OU, server baselines by OU, service accounts parked in a protected OU, and the organization chart itself encoded as the tree.

Entra ID has no tree to put an object in. A tenant holds users, groups, devices and service principals side by side, and governs them by what they carry: attributes, group memberships, role assignments and policy conditions. Microsoft notes that because Active Directory and Entra ID are separate products for different environments, they don’t have like-for-like features, and Entra ID has no notion of Active Directory domain and forest trusts.

Placement versus attributes: in Active Directory an object inherits delegation and policy from where it sits in the forest, domain and OU tree; in Entra ID an object’s attributes are evaluated by rules that place it in administrative units, dynamic groups and Conditional Access policies.

So the gap between the two isn’t a missing feature that a later release will fill. It is a different idea of where governance lives. An OU tree carries governance by containment. A tenant carries it by predicate. Every piece of governance that relied on containment has to be found and rewritten as an explicit predicate, an explicit role assignment or an explicit policy.

## Two limits decide whether the mapping works

Microsoft’s usual answer to “where do my OUs go?” is administrative units. That answer is right, but two limits determine how far it gets you.

### Administrative units can’t nest

Microsoft lists this as the first constraint on administrative units. An OU tree doesn’t become an administrative-unit tree. It becomes a flat set of administrative units, each with its own membership. Governance that depended on inheritance down the tree has to be expressed as a separate predicate for each unit. Several related constraints shape the design:

- A user, group or device can be a member of no more than 30 administrative units.

- An administrative unit with dynamic membership rules can contain users or devices, but not both, and dynamic rules for groups aren’t supported. Adding a group to an administrative unit brings the group into scope, not its members.

- Dynamic membership requires a Microsoft Entra ID P1 license for each unique member, and Microsoft documents dynamic administrative units for the global Azure cloud, not for specialized clouds such as Azure Government.

### The attributes that drive membership are mastered in Active Directory

For a user synchronized from Active Directory, Microsoft Graph treats the on-premises extension attributes as read-only: their source of authority is the on-premises directory. For a cloud-only user, including one whose source of authority has been converted to the cloud, they can be set directly. Device extension attributes are managed only in Entra ID. In a hybrid estate where every user is synchronized, the values that administrative-unit and dynamic-group rules match on are written in Active Directory and reach the tenant through directory sync. That has two consequences. The migration can’t stamp the attributes cloud-side for synced users, and every membership change waits on a synchronization cycle. The device plane and the user plane behave differently for the same reason.

Source-of-authority conversion, generally available for users since January 2026, changes this one object at a time: a converted user stops being synchronized and becomes cloud-managed. It doesn’t remove the need to decide which attributes are authoritative and where they come from. It moves that decision earlier. Chapter 05 works through the administrative-unit design, and HR-Driven Identity covers the upstream source for the attributes themselves.

## Every delegation concept needs an explicit counterpart

The reconstruction isn’t guesswork. Each Active Directory delegation concept has an Entra ID counterpart, but it has to be built rather than inherited. The table is the starting map; Chapter 03 compares the two platforms in full and Chapter 05 turns this map into a design.

| Active Directory concept | Entra ID counterpart | What changes |
| --- | --- | --- |
| Organizational unit | Administrative unit | Membership is assigned or computed from attributes, not from containment. No nesting. |
| OU-scoped delegation | A Microsoft Entra role assigned at administrative-unit scope | Same kind of role, different scope binding. Only roles that act on users, groups or devices can be scoped this way, for example User Administrator, Helpdesk Administrator, Authentication Administrator and Groups Administrator. |
| Help desk delegation on a leaf OU | Helpdesk Administrator or Authentication Administrator scoped to an administrative unit | The unit’s membership rule matches organizational attributes. Scoped roles act only on non-administrator users in the unit. |
| Security group creation by a department administrator | Groups Administrator scoped to the department’s administrative unit | Role plus scope replace the OU’s access control list. |
| Group Policy inherited down the OU tree | Device-management policy assigned to dynamic groups | A group rule replaces OU position (program design position; device policy is covered in its own book) |
| Site-linked Group Policy for network behavior | Conditional Access with named locations | Evaluated per sign-in from token and signals, not from network proximity |
| Domain Admins | Global Administrator, eligible through Privileged Identity Management, never permanently active | Microsoft recommends just-in-time activation with phishing-resistant authentication for privileged roles. |
| OU read delegation for a service account | Microsoft Graph application permissions with least privilege | Explicit scope; no implicit traversal of a tree |
| Privileged service accounts parked in a protected OU | Application Administrator or Cloud Application Administrator, eligible through Privileged Identity Management, or roles scoped to a single application | No containment; every privilege is an explicit role binding. |

The mapping step in the How chapters operationalizes this table. For each delegation record found in discovery it produces the administrative-unit definition, its membership rule and the role assignment Entra ID needs, so the output is executable guidance rather than a spreadsheet.

## The session-versus-telemetry divide

The governance gap has a deeper root, and it explains why hybrid identity fails in ways that look like application bugs.

The typical federal network was built on an assumption of proximity. Users were near their data. Domain controllers were near users. Then the servers and the data moved to consolidated data centers and the cloud, and the architecture didn’t move with them. Users in field offices now reach centralized systems with protocols designed for a local network.

Those protocols are session-oriented. Trust is established once and carried forward:

- A Kerberos ticket-granting ticket is good for 10 hours by default and renewable for 7 days, under the Default Domain Policy. Every service ticket the user obtains in that window rests on the original sign-in.

- Group Policy is applied at startup and logon and refreshed in the background every 90 minutes, plus a random offset of up to 30 minutes. A change reaches a desktop only after it replicates to the domain controller that client talks to. When no domain controller can be located, processing fails.

- Windows-authenticated SQL Server connections, thick clients and file shares assume the session they opened stays intact.

Zero Trust inverts that model. NIST SP 800-207 describes authentication and authorization as dynamic and strictly enforced before access, with continual monitoring and possible reauthentication throughout a user’s transactions. CISA’s maturity model puts the optimal state at validating identity continuously, not only when access is first granted. Entra ID implements this with short-lived tokens and event-driven revocation. Access tokens are valid for one hour by default. Continuous access evaluation lets services such as Exchange Online, SharePoint Online and Teams act on critical events (an account disabled or deleted, a password reset, a high user risk) in near real time, with Microsoft noting latency of up to 15 minutes for event propagation.

|  | Client/server era: sessions | Cloud and Zero Trust era: continuous verification |
| --- | --- | --- |
| When trust is established | Once, at sign-in | On every request, and again when conditions change |
| What carries trust forward | A ticket or an open session | A short-lived token, revocable on events |
| Inputs to the decision | Credentials and domain membership | Identity, device health, location, risk and behavior |
| Where policy comes from | A domain controller the client can reach | The identity provider, evaluated at sign-in and at the resource |
| What failure looks like | Expired tickets, unreachable domain controllers, broken sessions | A denied request with a stated reason |

The bridge between the two trust models rests on a single source of truth: the session-based estate and the continuously verified target are joined by a governance substrate rather than by forcing one model to imitate the other.

The two models aren’t compatible. A session-based application can’t pass through a continuous-verification enforcement point without its session model breaking: the inspection point sits in the path the session assumed was uninterrupted, adds latency, and re-evaluates trust the application believed was settled. Many applications with a web front end are still client/server at the protocol level, and they fail. The symptoms look like user error, WAN trouble or application defects, which is why they get diagnosed one at a time.

## Why it breaks at the FedRAMP boundary

The program’s reading is that FedRAMP’s boundary and monitoring expectations were written for cloud-native services that never had long-lived sessions: stateless, token-based, short-lived authentication, every component reachable from the cloud, telemetry flowing continuously to a SIEM. FedRAMP’s own direction reinforces that reading. FedRAMP 20x is a new approach to assessment and authorization, and its early pilots validated security decisions automatically through Key Security Indicators.

Impose those expectations on a hybrid estate that still runs on-premises domain controllers, Kerberos, Windows Server Update Services, Windows-authenticated SQL Server and thick clients, and defense in depth becomes defense in conflict. Each control added for the boundary breaks something that worked before, because the controls and the estate assume different trust models. Hybrid identity lives on that fault line, and FedRAMP is where federal environments meet it most sharply. The same mechanism applies to any client/server application pushed through a Zero Trust or SASE enforcement point.

## Why nobody wants to own it

Fixing this correctly means admitting that the problem isn’t one system or one team. It is the architecture. In federal IT, saying “we need to re-architect” is career risk, so the easier path is to patch the symptom, write a plan of action and milestones, add a proxy and move on. The people who understand the problem well enough to fix it are pushed aside because the fix sounds too large, and the people deciding often lack the depth to judge whether the diagnosis is right, so they default to incremental change. Chapter 06 assigns the ownership this chapter says is missing.

## The migration is a governance event

A conventional migration moves users. A governance-aware migration moves the entire identity namespace and every dependency attached to it.

| Domain | What moves or changes | Migration risk |
| --- | --- | --- |
| Identity | User accounts, service accounts, service principal names | Orphaned accounts, broken dependencies |
| Network | DNS, DHCP, DFS namespaces | Namespace drift, split-horizon DNS |
| Security | PKI, RADIUS, certificate templates | Broken authentication chains |
| Policy | Group Policy, and the Conditional Access that replaces it | Policy gap |
| Applications | LDAP-dependent applications, legacy single sign-on | Silent authentication failures |
| Devices | Domain-joined endpoints, hybrid management | Device trust drift |

Conventional engagements manage that surface by hand. No shared, tamper-evident record of the pre-migration state, the migration events or the post-migration posture survives the engagement, so each one starts from scratch, findings aren’t reusable, and evidence is assembled afterward. Chapter 04 inventories this surface in detail.

### The data-governance obligations it already sits under

Federal agencies already carry data-governance law. The Foundations for Evidence-Based Policymaking Act of 2018, whose Title II is the OPEN Government Data Act, requires each agency to designate a Chief Data Officer, to develop and maintain a comprehensive data inventory, and to make data open by default. The program’s reading is that none of these authorities mandates a single source of truth as such. SSOT is the architectural response agencies adopt to meet them, because a credible data inventory can’t be maintained from sources that disagree about the same fact.

Agencies almost always run that data-governance program and the directory migration as two unrelated efforts. They shouldn’t. Directory and identity infrastructure is the domain data-governance programs have historically left out, and it is the layer under every one of the decisions those programs care about. The program’s position is to run them as one: treat the identity namespace as the root of the SSOT hierarchy, put governance in place before any identity object moves, and give the Chief Data Officer and the identity team one shared register of which system is authoritative for which fact.

### What that treatment requires

The program’s design rests on four mechanisms, applied to the identity layer:

- Authoritative origin. Every principal has one authoritative representation. Downstream systems reference it or synchronize from it. They don’t keep independent copies.

- Provenance chain. Every change records who made it, from what source, when and under which policy authority: the identity-layer equivalent of data-catalog lineage.

- Drift detection. Differences between the authoritative state and what systems actually hold are classified (schema, semantic, provenance, authorization, identity and source-of-truth contention), each with a severity and a remediation commitment.

- Governance domains. Identity, authorization, compliance, migration, evidence and operations each have a named owner.

Together they make the bridge in the figure above concrete. An agency can’t move from sessions to continuous verification without knowing its authoritative identity state, can’t implement Zero Trust unless identity is the root namespace that every decision resolves against, and can’t run an access plane that enforces policy against named services unless addressing is deterministic.

The migration itself then becomes five capabilities rather than one tool:

| Capability | What it answers |
| --- | --- |
| Discovery | What governance does the current directory actually encode, whether or not it was set up well? (Chapter 07, Chapter 08) |
| Normalization | What is the clean authority model, decided before the migration rather than after? |
| Mapping | Which administrative units, scoped roles, access packages and Conditional Access policies express that model in Entra ID? (Chapter 05, Chapter 09) |
| Continuity | What governed transition path do Kerberos-dependent services, SQL Server, legacy applications and on-premises systems get, instead of a cliff? (Chapter 04) |
| Validation | What evidence shows that the governance model survived the move? (Chapter 10) |

The phased posture follows from it: assess, govern, migrate, validate, operate, with governance in place before the first identity object moves.

### The pattern, illustrated

The framing case studies show what this looks like across an engagement. They describe the pattern a program should expect, not the outcome of a real engagement.

- Model first. Define the canonical attribute set (for example assignment scope, organizational role and clearance), the group rules computed from combinations of those attributes, and the provenance carried with each identity claim. Validate the model before any runtime change.

- Connect the sources. Stand up read connections to Entra ID, Active Directory, Conditional Access targeting and the attribute sources, such as the PIV credential system and the agency’s HR system. Each emits claims with full provenance from day one, including during parallel running.

- Clean up before cutover. Pre-cutover runs surface inherited inconsistencies (stale attributes, group rules that reference retired values, broken provenance chains) as drift findings, and each is remediated on a set timetable. Orphaned accounts and broken dependencies are found before cutover, and silent authentication failures become explicit findings.

- Cut over. The identity plane’s authoritative source switches from on-premises Active Directory to Entra ID, and the model is already in place to interpret claims afterward. Where SQL Server shares the authentication boundary, its move from Windows authentication to token-based authentication runs in parallel with the directory.

- Operate. Drift findings keep surfacing inconsistencies, deterministic fixes are automated, and changes to the model go through the program’s decision process.

A real engagement would report, with metrics, how often provenance broke during cutover, how many identities passed validation before and after, whether the same person resolves identically across PIV, Entra ID and HR, and what share of access decisions are computed from attributes rather than administered by hand. Those measures are what a releasable case study would have to show. The lessons the patterns carry are already clear: findings must be reusable so that each engagement doesn’t start from scratch, and the SQL Server estate and the directory must be governed together because they share one authentication boundary. Evidence then becomes a byproduct of the migration instead of something reconstructed after it.

## Continue the book

← Previous: Chapter 01 — Why Identity Matters · Book index · Next: Chapter 03 — Active Directory and Entra ID, Side by Side →

# Chapter 03 — Active Directory and Entra ID, Side by Side

The scripts mostly survive the move; the protocols, the session unit, and the policy plane don’t.

## In this chapter

The two identity worlds at a glance, and the protocols each one speaks. Where the old protocols stand in Windows as of late 2026, and how the cryptography changes. Which languages and tools carry over and which modules are gone. The eight core concepts the program uses to frame directory migration, and why treating the move as a tooling swap keeps the old failure modes alive.

## The shift in one paragraph

Microsoft identity has moved from a directory-and-tickets world to a token-and-API world. In the old world, the on-premises Active Directory domain controller is the trust root. It issues Kerberos tickets, answers LDAP queries, and replicates SYSVOL to its peers. Clients talk to domain controllers directly over Kerberos, NTLM, LDAP, and MS-RPC, and administrators automate against those same interfaces. In the new world, the Microsoft Entra ID tenant is the trust root. It issues OAuth 2.0 access tokens and OpenID Connect ID tokens, exposes the directory through the Microsoft Graph REST API, and federates with SaaS applications over SAML 2.0 and OpenID Connect. Around it sits an operating layer that barely existed around Active Directory: infrastructure as code, pipelines as code, and compliance as code.

Active Directory and Microsoft Entra ID differ in trust root, session unit, and policy plane, and Kerberos or NTLM sessions never reach Conditional Access.

The figure carries the chapter’s main point. A Kerberos ticket or an NTLM exchange is settled between a client and a domain controller. Microsoft Entra Conditional Access is enforced after first-factor authentication to Entra ID completes, and when a cloud-native device reaches an on-premises file server or printer, the domain controller still returns a Kerberos ticket-granting ticket or an NTLM response. Every access decision that rides on those protocols sits outside the cloud policy engine. That gap is the silent-failure surface that Chapter 04 inventories.

## The two worlds at a glance

The two identity worlds at a glance

| Dimension | Active Directory | Microsoft Entra ID |
| --- | --- | --- |
| Trust root | On-premises domain controllers and the Key Distribution Center (KDC) | The Entra ID tenant |
| Primary authentication protocol | Kerberos v5, with NTLM as fallback through Negotiate | OpenID Connect sign-in; OAuth 2.0 for authorization |
| Directory wire protocol | LDAP and LDAPS; Active Directory Web Services for the PowerShell module | Microsoft Graph REST API over HTTPS |
| Federation | SAML and WS-Federation through Active Directory Federation Services (AD FS) | SAML 2.0 and OpenID Connect directly to the tenant |
| Strong authentication | Smart card logon with certificates from an enterprise CA | Certificate-based authentication with PIV/CAC, FIDO2 passkeys, Windows Hello for Business, Microsoft Authenticator |
| Stored password form | NT hash (MD4) | For synced users, a PBKDF2-HMAC-SHA256 hash of the NT hash |
| Session unit | Kerberos ticket-granting ticket and service tickets | JWT access tokens, ID tokens, and refresh tokens |
| Policy plane | Group Policy Objects linked to sites, domains, and OUs | Conditional Access, the Authentication methods policy, and device-management policy |
| Account lifecycle | Manual tools and scripts against the directory | Lifecycle workflows, entitlement management, access reviews |
| Provisioning to applications | LDAP binds and custom connectors | SCIM 2.0 from the Entra provisioning service |
| Audit pipeline | Windows Security event log, forwarded to a SIEM | Entra sign-in and audit logs, streamed to a SIEM through diagnostic settings |
| Infrastructure as code | Little native support | Bicep templates with the Microsoft Graph extension, alongside other declarative tools |
| Compliance authoring | Word and Excel system security plans | OSCAL models (catalog, profile, control mapping, component definition, SSP, assessment plan, assessment results, POA&M) |

Each row is covered in the sections below or in a later chapter. Two rows need a caveat now. Entra ID stores a password hash only for users in scope of password hash synchronization: Microsoft Entra Connect never sends the original MD4 hash; it sends a PBKDF2 derivation of it, salted per user and run through 1,000 iterations of HMAC-SHA256. And the policy plane doesn’t map one to one. Group Policy configures domain-joined machines. Conditional Access decides whether a sign-in gets a token. Device configuration moves to a device-management service, part of the target build in Chapter 09.

## Protocols: what each side speaks

### The Active Directory protocol stack

- Kerberos v5 (RFC 4120) is the default authentication protocol for domain accounts. Clients reach it through SPNEGO, the Simple and Protected GSS-API Negotiation Mechanism (RFC 4178), which Windows exposes as the Negotiate package.

- NTLM (NTLMv1, NTLMv2, and LANMAN) is the challenge-response fallback when Kerberos can’t be used: no line of sight to a domain controller, a local account, or a missing service principal name.

- LDAP and LDAPS carry directory reads and writes. Binds can be signed, sealed, or wrapped in TLS, and channel binding ties a SASL bind to its TLS session.

- MS-RPC and SMB carry replication, Netlogon, the legacy SAM password-change calls, and Group Policy file delivery from SYSVOL.

- SAML and WS-Federation reach SaaS applications through AD FS, a separate federation server the agency runs.

### The Entra ID protocol stack

- OAuth 2.0 (RFC 6749) is the authorization framework that issues access tokens to applications.

- OpenID Connect Core 1.0 adds an ID token and user sign-in on top of OAuth 2.0.

- SAML 2.0 remains supported for applications that need it, now federated directly to the tenant.

- SCIM 2.0 (RFC 7643 for the schema, RFC 7644 for the protocol) is how the Entra provisioning service creates, updates, and removes accounts in applications. Entra ID acts as a SCIM client for outbound app provisioning and can also expose a SCIM service endpoint for inbound provisioning.

- Proof-of-possession tokens bind a token to a key the client holds. Microsoft’s authentication libraries describe two target variants, mutual-TLS certificate-bound tokens (RFC 8705) for service-to-service calls and DPoP (RFC 9449) for public clients, with the older signed-HTTP-request form being phased out. Separately, Conditional Access Token Protection accepts only device-bound sign-in session tokens such as the Primary Refresh Token.

- FIDO2/WebAuthn passkeys and certificate-based authentication are the phishing-resistant user credentials. Entra certificate-based authentication validates X.509 certificates, including PIV and CAC smart cards and derived PIV credentials, directly against the tenant, without a federation server.

### The protocol mapping

For each job the directory performs, the Active Directory protocol and the Entra ID protocol that replaces it.

The mapping is a planning aid, not a promise of equivalence. Some Active Directory jobs have no cloud equivalent that applications can use without change. An application that binds to LDAP or expects a Kerberos service ticket keeps needing a domain controller, or a bridge such as Microsoft Entra application proxy with Kerberos constrained delegation, until it’s rewritten or replaced.

### What Conditional Access can and can’t see

Conditional Access is the Zero Trust policy engine for Entra ID, and its policies run after first-factor authentication to the tenant completes. It sees modern-authentication clients and it can block legacy-authentication clients. Microsoft notes that legacy clients don’t support multifactor authentication and don’t pass device state, so a policy that requires MFA or a compliant device blocks them. Kerberos and NTLM traffic between a client and a domain controller never reaches it. In the program’s planning model, every remaining Kerberos or NTLM dependency is an access path with no cloud policy decision, and every one has to be found, moved to a token-based protocol, or accepted as a documented exception.

## Where the old protocols stand in 2026

The Active Directory protocols aren’t frozen; Microsoft has been hardening and retiring them. Plans that assume 2015-era defaults will misjudge both the risk and the breakage.

Status of the Active Directory protocols as of October 2026

| Protocol or setting | Status as of October 2026 |
| --- | --- |
| NTLM (all versions) | Deprecated since June 2024 and no longer under active feature development. Calls should move to Negotiate, which tries Kerberos first. |
| NTLMv1 | Removed starting with Windows 11, version 24H2 and Windows Server 2025. Beginning with the October 2026 security update, those versions and Windows 11 25H2 and 26H2 restrict generating NTLMv1-derived credentials for single sign-on by default on devices without Credential Guard, which can break Wi-Fi, Ethernet, and VPN connections that rely on MS-CHAPv2. |
| NTLMv2 and LANMAN | Deprecated in Windows Server 2025; NTLMv2 still works but is slated for removal in a future release. Microsoft’s January 2026 plan adds NTLM auditing now, IAKerb and a local KDC in the second half of 2026, and network NTLM disabled by default in the next major Windows release. |
| Kerberos RC4 | Deprecated in Windows Server 2025; AES should be used instead. DES is removed from Windows Server 2025. |
| LDAP signing | Required by default for new Active Directory deployments on Windows Server 2025 or later. Upgrades keep existing policy, and if none is set, Windows Server 2025 requires signing. |
| LDAP channel binding | Defaults to “When supported” for new Windows Server 2025 deployments, with auditing on; Windows Server 2022 and earlier default to “Never,” with auditing on since the March 2023 updates. |

The source material for this chapter called NTLM simply “legacy.” That understates the schedule: NTLMv1 is already gone from current Windows, and Microsoft has said network NTLM will be off by default in the next major release, though the code stays so administrators can turn it back on by policy. An agency that waits for the cutover to find its NTLM dependencies will find them in production. That’s why NTLM auditing belongs in the read-only discovery described in Chapter 07.

## Cryptography

Cryptography in the two worlds

| Purpose | Active Directory | Microsoft Entra ID |
| --- | --- | --- |
| Stored password | NT hash, an MD4 hash of the password | For synced users, a salted PBKDF2-HMAC-SHA256 hash of the NT hash; the original MD4 hash isn’t sent to the cloud and can’t be replayed on-premises |
| Ticket or token protection | Kerberos encryption types; RC4 deprecated, AES preferred | JWT signatures from asymmetric keys such as RS256, published through the tenant’s OpenID Connect metadata and rotated on a schedule |
| Transport | LDAP signing and sealing, LDAPS, SMB signing | TLS on every endpoint; the provisioning service connects to applications over TLS 1.2 |
| User credential | Password; smart card logon | Passkeys (FIDO2), certificate-based authentication with PIV/CAC, Windows Hello for Business |

The source table listed ES256 and ES384 among Entra’s token-signing algorithms and said the cloud hash lives “in an HSM-backed boundary.” Microsoft’s documentation shows RS256 as the signing algorithm for Entra access and ID tokens and doesn’t make the HSM claim for password hashes, so both statements are dropped here.

## Languages and tooling

Most languages carry over; the libraries and endpoints underneath them change.

Languages and libraries in the two worlds

| Language | Active Directory era | Entra ID era |
| --- | --- | --- |
| PowerShell | ActiveDirectory module from RSAT, talking to Active Directory Web Services on a domain controller | Microsoft Graph PowerShell SDK and Microsoft Entra PowerShell, both authenticating with MSAL |
| .NET (C#) | System.DirectoryServices, System.DirectoryServices.AccountManagement | MSAL.NET, Microsoft.Identity.Web, the Microsoft Graph SDK, Azure.Identity |
| Python | python-ldap, ldap3, pywin32 | MSAL Python, the Microsoft Graph SDK, azure-identity |
| JavaScript and TypeScript | Rare | MSAL.js for browser apps, MSAL Node, MSAL React and Angular |
| Java and Go | Java via JNDI over LDAP | MSAL Java and MSAL Go |
| VBScript | Logon scripts and directory automation | Deprecated in Windows; available as a Feature on Demand in Windows Server 2025 before removal; rewrite in PowerShell |
| C++ | Native clients over ADSI, LDAP, and SSPI | Little greenfield identity work; native apps usually use MSAL for their platform |
| YAML | Little use | Pipeline definitions, parameter files, and policy-as-code repositories |

### The retired modules

PowerShell stayed the primary administration language, but three modules that many scripts still import are gone. Microsoft Learn lists the Azure AD, Azure AD Preview, and MSOnline modules as deprecated and points to Microsoft Graph PowerShell instead. MSOnline stopped working between early April and late May 2025, and Microsoft scheduled the AzureAD module’s retirement for later in 2025, after the MSOnline migration. Microsoft’s own security checklist now includes a check to block the legacy Azure AD PowerShell application in the tenant. Any script that calls Connect-MsolService or Connect-AzureAD should be treated as already broken. Microsoft publishes cmdlet maps from both old modules to Microsoft Graph PowerShell and to Microsoft Entra PowerShell, which offers a backward-compatibility option for AzureAD scripts.

The same task in each world shows the protocol shift inside a familiar language. The Active Directory version reads from a domain controller. The Graph version gets an OAuth token with a named permission scope and calls a REST API.

## Illustrative code

The code in this chapter is illustrative. It hasn’t been tested against a production forest or tenant. Review it, and run it first in a test environment with read-only permissions.

# Active Directory: the RSAT ActiveDirectory module queries a domain controller
Import-Module ActiveDirectory
Get-ADUser -Filter "Department -eq 'Finance'" -Properties Department, Manager |
    Select-Object SamAccountName, Department, Manager

# Microsoft Entra ID: Microsoft Graph PowerShell gets an OAuth token, then calls Graph
Connect-MgGraph -Scopes "User.Read.All"
Get-MgUser -Filter "department eq 'Finance'" -Property "userPrincipalName,department" -All |
    Select-Object UserPrincipalName, Department

Two differences matter more than the syntax. The Graph session carries a consented permission (User.Read.All) that shows up in the tenant’s audit trail, while the Active Directory session runs with whatever rights the signed-in account holds. And the Graph call works from any network that can reach the service; it doesn’t need line of sight to a domain controller.

## Infrastructure, pipelines, and compliance as code

Three layers that Active Directory never had grow up around Entra ID.

- Infrastructure as code. The Microsoft Graph Bicep extension lets a Bicep template declare Entra resources, such as groups, applications, and service principals, next to Azure resources, and deploy them repeatably. It covers a limited set of resource types today: role-assignable groups can’t be deployed through it, and application passwords aren’t supported. Other declarative tools fill gaps; the program doesn’t prescribe one.

- Pipelines as code. In the program’s design, changes to identity configuration move through YAML pipelines with review and approval, the same way application code does.

- Compliance as code. NIST’s Open Security Controls Assessment Language (OSCAL) defines eight models in three layers: catalog, profile, and control mapping (control layer); system security plan and component definition (implementation layer); and assessment plan, assessment results, and plan of action and milestones (assessment layer). The source material listed seven; the control mapping model is the newer addition. Generating these from the configuration, instead of writing them in Word, is what makes the evidence in Appendix A regenerable.

## The eight core concepts of directory migration

The Federal Modernization Program frames every migration workstream with eight concepts. They’re the program’s own architecture principles, not external standards, and they apply beyond identity. Directory migration is where most of them are tested first.

The eight core concepts

| # | Core concept | What it means |
| --- | --- | --- |
| 1 | Single source of truth | Every claim has one authoritative origin. Every other representation is a pointer, not a copy. |
| 2 | Conversation as the atomic unit | Each interaction binds identity, certificates, addressing, path, quality of service, and telemetry together. |
| 3 | Identity as the root namespace | Addresses, certificates, subnets, policies, and telemetry events all derive from identity. |
| 4 | Deterministic addressing | Addressing is derived from identity and driven by policy. |
| 5 | Certificate-anchored overlay | Mutual TLS anchors tunnels, services, and trust relationships. |
| 6 | Telemetry as control | Telemetry is a real-time control input, not passive reporting. |
| 7 | Embedded governance | Governance runs through orchestrated workflows, not manual tickets. |
| 8 | User experience first | If governance was done right, the migration is invisible to end users. |

### How the concepts map to the migration adapters

The program breaks directory migration into adapters, each one an interface to a service that Active Directory either provides or underpins. Each adapter names the concepts it has to satisfy.

Migration adapters and the core concepts they implement

| Adapter | Concepts | Why |
| --- | --- | --- |
| IP address management | 1, 4 | Addressing records have one master and are derived from identity, not maintained by hand. |
| PKI | 5 | Certificates anchor service and device trust once Kerberos is no longer the trust mechanism. |
| RADIUS | 3, 5 | Network access decisions key off identity and certificates instead of domain group membership. |
| LDAP proxy | 3 | Applications that still bind over LDAP get identity from the authoritative source, not a stale copy. |
| Directory synchronization engine | 1 | Retiring sync is the moment the single source of truth moves to the cloud identity platform. |
| Device management | 7 | Device configuration moves from Group Policy to workflow-driven policy. |
| NTP | 5 | Time remains a dependency while Kerberos is in use: by default, Kerberos tolerates at most five minutes of clock difference. |
| Distributed File System | 8 | Users’ path names must not break when the namespace behind them changes. |

The directory synchronization row is the one most programs get wrong. While Microsoft Entra Connect is synchronizing, Active Directory stays the master for synced users and the sync cycle, every 30 minutes by default, is the floor for how fast a change reaches the cloud. Retiring sync is not a cleanup task at the end. It’s the change of authority that concept 1 describes, and it has to be planned as one.

## Why the shift matters

The languages mostly carry over. The protocols, the cryptography, the session unit, and the policy plane don’t. A program that treats the move as swapping one admin tool for another will carry Active Directory’s silent failures into the new estate: NTLM fallback that nobody audited, services that work only because a service principal name happens to be missing, and database logins that authenticate outside the directory entirely. Those dependencies don’t show up in a user count or a group export. They show up when a domain controller is switched off. Chapter 04 lays out where they hide, and Chapter 05 takes on the other concept that doesn’t carry over: delegation through organizational units.

## Continue the book

← Previous: Chapter 02 — The Structural Problem · Book index · Next: Chapter 04 — The Hidden Migration Surface →

# Chapter 04 — The Hidden Migration Surface

Moving the users is the visible tenth of the work; the rest is every service that quietly trusted the domain.

## In this chapter

The eleven types of object that depend on Active Directory, and why most of them fail without an error when AD goes away. The eight adapter interfaces the Federal Modernization Program uses to move those services off AD, ranked by risk, with what Microsoft’s products do and don’t replace. The six-phase adapter model, how adapters register, how a migration is validated before AD is decommissioned, and the inventory categories that feed the whole effort.

When an organization plans its move from Active Directory to Microsoft Entra ID, it plans for users and groups. It rarely plans for everything else AD was holding together. For twenty years AD was the implicit governance model for name resolution, certificates, network access, application sign-in, time, and file paths. None of those services were designed as “AD projects”; they simply assumed a domain controller would always be there.

When that assumption breaks, most of them don’t fail loudly. There’s no error and no alert. Certificates stop renewing and nobody notices until they expire. RADIUS authentications start failing at the network edge. DNS records go stale. Applications that bind to a domain controller over LDAP stop letting people in. Each of these looks like a local outage with a local cause, and the connection to the identity migration is made late, if at all.

Active Directory anchors eleven types of object; most migration plans count only users and groups.

## The eleven AD dependency object types

The program’s dependency inventory names eleven object types. The first five are what a migration plan usually covers. Types 6 through 11 are the hidden surface.

| # | Object type | What AD was doing | What breaks without governance |
| --- | --- | --- | --- |
| 1 | Users | Identity lifecycle, OU placement, attribute authority | Orphaned accounts, privilege drift, compliance gaps |
| 2 | Computers | Domain join, Group Policy targeting, machine certificates | Unmanaged endpoints, missed patches, security exposure |
| 3 | Service accounts | Service principal names (SPNs), Kerberos delegation, password management | Application authentication failures, silent service outages |
| 4 | Security groups | Access control, policy scoping, resource permissions | Permission sprawl, ungoverned access, audit findings |
| 5 | Group Policy Objects | Device configuration, security baselines, software deployment | Configuration drift, inconsistent baselines |
| 6 | DNS and DHCP | Name resolution, IP allocation, AD-integrated zones | Resolution failures, IP conflicts, split-brain DNS |
| 7 | PKI and certificate services | Certificate issuance, auto-enrollment, CRL distribution | Silent certificate expiration, authentication failures, broken mutual TLS |
| 8 | RADIUS and NPS | 802.1X wired and wireless access, VPN authentication | Network access failures, VPN outages |
| 9 | LDAP | Application authentication, directory queries, legacy integrations | Application sign-in failures, broken integrations |
| 10 | SPNs and service identities | Kerberos service principal names, application identity | Single sign-on breaks, delegation failures |
| 11 | Trust relationships | Cross-domain and forest trusts, selective authentication | Cross-domain access failures between organizations |

Types 10 and 11 have no direct counterpart in Entra ID. An Entra ID tenant has app registrations and service principals rather than Kerberos SPNs, and it has cross-tenant access settings and cross-tenant synchronization rather than forest trusts: cross-tenant synchronization creates and removes B2B collaboration users across the tenants of one organization. Neither is a drop-in replacement; each needs its own design, which is why the program lists both as adapter gaps (see the adapter priority matrix).

## The adapter interface

Each AD-dependent service gets a dedicated adapter: an interface that defines how that service is governed while it moves off AD. Vendor implementations plug in underneath the interface. Every adapter has the same six parts:

- Discovery: what to inventory and how to find it in AD.

- Risk assessment: what fails if the service is migrated badly.

- Target architecture: the modern equivalent and how governance works there.

- Migration path: the step-by-step governed migration.

- Validation: how to confirm governance survived the move.

- Rollback: what to do if the migration causes failures.

### The core concepts behind every adapter

The adapters rest on eight architectural concepts the Federal Modernization Program applies everywhere. They’re design positions, not product facts, and they explain why the adapters are ordered as they are.

| Core concept | Definition | Adapter relevance |
| --- | --- | --- |
| Single source of truth | Every claim has one authoritative origin | Each adapter names its source of truth for governance decisions |
| Conversation as atomic unit | Every interaction binds identity, certificates, addressing, path, QoS, and telemetry | A migration must keep every conversation intact end to end |
| Identity as root namespace | IPs, certificates, subnets, policy, and telemetry all derive from identity | All adapter governance traces back to identity authority |
| Deterministic addressing | Addressing is identity-derived and policy-driven | The IPAM and DNS adapters enforce deterministic assignment |
| Certificate-anchored overlay | Mutual TLS anchors tunnels, services, and trust | The PKI adapter is the foundation; others depend on it |
| Telemetry as control | Telemetry is a real-time control input, not passive reporting | Every adapter emits governance telemetry for drift detection |
| Embedded governance | Governance runs through orchestrated workflows, not manual tickets | Each migration is a governed workflow, not an ad hoc project |
| User experience first | If governance was done right, users notice nothing | The final validation: users don’t notice the move |

## The adapter priority matrix

The program ranks the eight adapters by the cost of getting them wrong.

| ID | Adapter | Priority | Risk if ignored |
| --- | --- | --- | --- |
| DM_020 | PKI and certificate services | Critical | Silent authentication failure weeks after the migration is declared complete |
| DM_030 | RADIUS, 802.1X, and VPN | Critical | Total network access failure, not a degraded experience |
| DM_040 | LDAP proxy | Critical | Silent application sign-in failure across the largest uninventoried surface |
| DM_010 | IPAM (DNS, DHCP, IP management) | High | DNS resolution failure, rogue DHCP |
| DM_050 | Sync engine (Microsoft Entra Connect) | High | Permanent AD dependency |
| DM_060 | Device management | High | Non-deterministic policy application |
| DM_070 | NTP and time services | Medium | Kerberos clock-skew failures that look like identity problems |
| DM_080 | DFS and file services | Medium | Silent UNC path failure |

The three critical adapters share a property: they fail silently. They must be addressed before any AD infrastructure is decommissioned. The sync engine is high priority but finishes last, because it’s the tether that keeps AD in production until every other adapter has moved.

Adapter sequencing: the critical adapters gate decommissioning, and the sync engine is retired last.

### Gaps in the adapter registry

The program’s adapter taxonomy has twelve leaves. Eight have adapter specifications; four are open gaps.

| Leaf | Adapter | Status |
| --- | --- | --- |
| D.1 | IPAM — DM_010 | Specified |
| D.2 | DNS — DM_015 | Gap: not yet in the registry (covered today inside DM_010) |
| D.3 | DHCP — DM_016 | Gap (covered today inside DM_010) |
| D.4 | PKI / AD CS — DM_020 | Specified |
| D.5 | RADIUS / NPS — DM_030 | Specified |
| D.6 | LDAP proxy — DM_040 | Specified |
| D.7 | Sync engine — DM_050 | Specified |
| D.8 | Device management — DM_060 | Specified |
| D.9 | NTP — DM_070 | Specified |
| D.10 | DFS — DM_080 | Specified |
| D.11 | SPN and app registration — DM_085 | Gap |
| D.12 | Trust relationship — proposed DM_090 | Gap; the proposed ID collides with the validation checklist (DM_090) and needs a new number |

Object types 10 and 11 map to the last two gaps. Until those adapters exist, treat SPNs and trusts as manual line items in the inventory (see the transformation inventory).

## Adapter by adapter

The adapter specifications below keep the program’s discovery lists and migration sequences. Where a source named a Microsoft capability, the claim has been checked against current Microsoft documentation and corrected where needed.

### IPAM: DNS, DHCP, and IP management (DM_010, high)

AD-integrated DNS is the most visible dependency. Domain-joined computers find domain controllers through the DC locator, which queries DNS for SRV records that domain controllers register, such as _ldap._tcp.<domain>, plus records for capabilities like the Key Distribution Center and the global catalog. Retiring AD means moving those zones to standalone DNS without losing the records that hybrid clients still need during the transition.

Required capabilities:

- Full zone export as a canonical snapshot and drift-detection baseline.

- Migration of the DC locator SRV records (_kerberos, _ldap, _gc) for as long as any domain remains.

- Side-by-side operation with AD-integrated DNS during the hybrid window.

- DHCP scope inventory and rogue DHCP detection.

The program’s registry lists Infoblox, BlueCat Address Manager, and a generic RFC-compliant IPAM as implementations. The earlier description of “Infoblox NIOS (FedRAMP authorized)” was imprecise: the FedRAMP authorization belongs to the Infoblox Government Cloud service, listed on the FedRAMP Marketplace as FedRAMP Certified at the Moderate impact level, not to on-premises NIOS appliances. The DNS and DHCP leaves (DM_015, DM_016) will split out of this adapter once specified.

### PKI and certificate services (DM_020, critical)

Active Directory Certificate Services (AD CS) is embedded deeply in most federal environments. Auto-enrollment flows through Group Policy, machine certificates support 802.1X and VPN, and smart card logon to Windows relies on trust configuration anchored in the domain. The failure mode is the reason this adapter is critical: certificates keep working until they expire. If the replacement CA isn’t issuing before the first expiry wave, authentication fails across the organization weeks or months after the migration was declared complete.

Required capabilities:

- Full certificate inventory: issued, pending, revoked, and expired.

- Certificate-to-identity binding: who owns each certificate.

- Expiry timeline export in 90-, 180-, and 365-day windows.

- CA hierarchy mapping: root, issuing, and subordinate chains.

- Smart card, PIV, and CAC certificate inventory.

- Migration of auto-enrollment from Group Policy to Intune certificate profiles.

Migration sequence:

- Inventory every issued certificate and its expiry date.

- Map certificates to identity objects.

- Stand up the replacement CA before any AD retirement begins.

- Move auto-enrollment to Intune certificate profiles.

- Validate the certificate chain through the new CA.

- Retire AD CS only after every renewal is confirmed through the new CA.

Three corrections to the target architecture:

- Intune delivers certificates by SCEP, PKCS, or imported PKCS profiles, with a trusted-root profile that deploys the CA chain; network authentication (802.1X) and VPN are the typical uses. Using SCEP with a Microsoft CA still requires an NDES server and the Certificate Connector for Microsoft Intune. The earlier reference to “Intune/SCEP/EST” is corrected: Intune’s documented provisioning methods are SCEP and PKCS, not EST.

- Microsoft Cloud PKI (an Intune capability) can host a two-tier root and issuing CA in the cloud, or anchor a cloud issuing CA to an existing private root (“bring your own CA”). It issues leaf certificates through SCEP to Intune-managed devices and hosts the CRL distribution point and AIA endpoint. That’s a direct path off AD CS for device certificates.

- Microsoft Entra certificate-based authentication (CBA) is a relying party, not a CA. The earlier registry listed “Entra CBA” alongside DigiCert and Entrust as an implementation; it belongs in a different column. CBA validates user certificates against CAs uploaded to the Entra trust store, and every CA in the chain must be uploaded. Its CRL distribution point must be an internet-facing HTTP URL; OCSP and LDAP URLs aren’t supported, and a CA with no CRL configured gets no revocation checking at all. AD CS deployments that publish CRLs only over LDAP need a new HTTP distribution point before CBA can rely on them.

Windows Hello for Business also shrinks the PKI surface. Its cloud Kerberos trust model is the only hybrid deployment option that needs no certificates, and Microsoft recommends it over key trust when certificate authentication isn’t otherwise required.

### RADIUS and Network Policy Server (DM_030, critical)

Windows Network Policy Server (NPS) authenticates 802.1X wired and wireless, VPN, and dial-up connections against AD groups. Every access point, VPN concentrator, and managed switch that uses RADIUS is an AD dependency. If NPS goes down before its replacement is validated, users can’t connect at all.

Required capabilities:

- Inventory of all NPS policies (connection request, network, and health).

- Map of every NPS policy to the AD groups it depends on.

- Inventory of RADIUS clients: access points, VPN concentrators, switches.

- Inventory of 802.1X certificate profiles and EAP methods.

- Translation of policy from AD groups to Entra ID groups.

- Side-by-side validation before cutover.

Migration sequence:

- Inventory every RADIUS client and NPS policy.

- Map every NPS AD group dependency to its Entra ID equivalent.

- Deploy the replacement RADIUS service.

- Validate in parallel, with NPS and the replacement serving at the same time.

- Cut RADIUS clients over to the new server.

- Decommission NPS only after a 30-day validation window.

Entra ID has no native RADIUS service, and the earlier “Entra RADIUS Proxy” implementation doesn’t exist as a Microsoft product; it has been removed. The NPS extension for Microsoft Entra multifactor authentication is often mistaken for an exit path. It isn’t one: NPS still performs primary authentication against AD and then hands off to Entra ID for the second factor. The extension also identifies users by their on-premises UPN by default. It’s a useful interim control, not a retirement.

The retirement paths are a non-Microsoft RADIUS or network access control service (the program’s registry lists Cisco ISE and Aruba ClearPass), certificate-based EAP-TLS using device certificates delivered by Intune, and, for VPNs, replacing RADIUS altogether. Microsoft recommends moving VPNs to SAML federated directly with Entra ID so they get Conditional Access, MFA, and device compliance.

### LDAP proxy (DM_040, critical)

LDAP is the largest hidden AD dependency. Applications deployed ten or fifteen years ago bind to domain controllers to authenticate users and read attributes. Nobody kept an inventory because nobody had to; AD was always there. Discovery for this adapter takes the longest, because you can’t migrate what you can’t see.

Required capabilities:

- Network traffic analysis identifying every host that binds to a domain controller.

- Inventory of service accounts used for LDAP binds.

- Application-to-LDAP dependency map.

- Query analysis: which attributes each application reads.

- Bind type inventory: simple, SASL, certificate-based.

- Attribute mapping from AD names to Entra ID equivalents.

Migration sequence:

- Deploy a passive LDAP traffic monitor on the domain controller network segment.

- Run a 30-day discovery window to capture every bind source.

- Build the application-to-LDAP dependency map.

- Deploy the LDAP target (Microsoft Entra Domain Services or a standalone directory).

- Validate each application against the target.

- Cut applications over in waves, never all at once.

Domain controllers can help with step 2 but can’t replace network capture. A DC logs a daily summary (Event 2887) of unsigned SASL binds and clear-text simple binds, and with the 16 LDAP Interface Events diagnostic level set to 2 it logs Event 2889 for each such bind, with the client IP address and identity. Those events cover only the insecure binds. Applications that already sign their binds don’t appear, which is why the passive monitor stays in the sequence.

## Illustrative code

The PowerShell in this chapter is illustrative. It hasn’t been tested against a production forest. Review it, and run it first in a lab, before using it on a domain controller.

# On a domain controller: log each unsigned or clear-text LDAP bind (Event 2889)
$diag = 'HKLM:\SYSTEM\CurrentControlSet\Services\NTDS\Diagnostics'
Set-ItemProperty -Path $diag -Name '16 LDAP Interface Events' -Value 2 -Type DWord

# After the collection window: count binds per client address
Get-WinEvent -FilterHashtable @{ LogName = 'Directory Service'; Id = 2889 } |
    ForEach-Object { ($_.Properties[0].Value) -replace ':\d+$', '' } |
    Group-Object |
    Sort-Object Count -Descending |
    Select-Object Count, Name

# Turn detailed logging back off when the investigation ends
Set-ItemProperty -Path $diag -Name '16 LDAP Interface Events' -Value 0 -Type DWord

Microsoft’s guidance is to set the diagnostic value back to 0 after the investigation.

Microsoft Entra ID itself has no LDAP endpoint. The Microsoft-managed option is Entra Domain Services, a standalone managed domain that supports LDAP bind and read, secure LDAP, Kerberos, and NTLM. LDAP writes work only for objects created in the managed domain, not for objects synchronized from Entra ID. Two prerequisites matter for planning. Cloud-only users must change their password before they can use the managed domain, because that’s when Entra ID generates the legacy password hashes it needs. And Microsoft Entra Cloud Sync isn’t supported with Domain Services; synchronized users need Microsoft Entra Connect Sync to carry their password hashes. For web applications that use Integrated Windows Authentication, Entra application proxy can provide single sign-on through Kerberos constrained delegation, but its connector servers must be domain-joined. Both are bridges that keep a domain alive. The real exit is re-platforming the application onto SAML or OpenID Connect.

### Sync engine: Microsoft Entra Connect (DM_050, high, finishes last)

The sync engine is both the bridge between AD and Entra ID and the tether that keeps AD alive. As long as it runs, AD is a production dependency. It isn’t retired until every other adapter has moved.

Retirement criteria (all must be true):

- Every user is provisioned from the authoritative HR source, not from AD sync.

- Every group is dynamic or managed in Entra ID.

- No application uses on-premises AD authentication.

- Every device is managed by Intune with no AD dependency.

- Every service account has moved to an Entra ID workload identity.

- AD CS is replaced; DNS, RADIUS, and LDAP applications are migrated and validated.

These six conditions are the core of the 12-point retirement readiness checklist in the program’s adapter specification. HR-sourced provisioning is the subject of the provisioning pipeline in the HR-driven IAM series.

Current Microsoft facts that shape this adapter:

- Two sync clients. Microsoft Entra Connect Sync runs a full sync engine on premises; Microsoft Entra Cloud Sync runs the engine in the cloud with lightweight on-premises agents. Microsoft recommends Cloud Sync where it meets an organization’s requirements, because new sync features are arriving there. The clients aren’t equivalent. Cloud Sync supports disconnected forests and multiple active agents but limits groups to 50,000 members and supports up to 150,000 objects per domain; Connect Sync keeps advanced sync rules and cross-forest references. The two can’t sync the same objects side by side; migration between them uses OU-based scoping.

- Source of authority can move object by object. Group source of authority conversion turns a synced group into a cloud-managed group; both sync clients then stop syncing it from AD, and the change can be reversed. User source of authority conversion works the same way through the onPremisesSyncBehavior property. That makes the retirement criteria above achievable incrementally rather than in one cutover.

- Provisioning back to AD is asymmetric. Cloud Sync can provision groups from Entra ID to AD, but neither client provisions users from the cloud to AD. An application that still needs an AD user account keeps AD, and a writer into it, alive.

### Device management (DM_060, high)

Configuration Manager collections query AD, Group Policy flows down the OU tree, and co-management splits responsibility between Configuration Manager and Intune. This adapter governs the move from AD-dependent device policy to Intune-native management.

Co-management moves seven workloads, individually or together: compliance policies, Windows Update policies, resource access policies, Endpoint Protection, device configuration, Office Click-to-Run apps, and client apps. Before switching any workload, run Group Policy analytics in Intune. It imports GPO exports, reports which settings have an MDM equivalent, flags deprecated settings, and can migrate the supported ones into a Settings Catalog policy. Settings without an equivalent become explicit decisions: replace, accept the loss, or keep a GPO-managed island.

### NTP and time services (DM_070, medium)

Kerberos tolerates a maximum clock difference of five minutes by default. In a domain, time follows the AD hierarchy: member computers synchronize with a domain controller in their own domain, domain controllers synchronize up the hierarchy, and the PDC emulator of the forest root domain is the best time source unless another reliable source is configured. The earlier statement that every domain-joined machine syncs from the PDC emulator is corrected: only the domain controllers chain to the PDC emulator; members use any domain controller in their domain.

Decommission domain controllers without redirecting time and authentication fails across whatever still uses Kerberos, with symptoms that look like identity problems. Two facts shape the fix:

- Computers that aren’t joined to a domain, which includes Microsoft Entra joined Windows devices, get time from time.windows.com by default.

- Intune can set the NTP source explicitly through the ADMX_W32Time policy area (Configure Windows NTP Client, NtpServer), whose default value is time.windows.com,0x09.

The program’s position is to set the time source by policy before any domain controller is decommissioned, rather than rely on defaults, and to choose the source deliberately: many agencies require an authoritative government time source. Microsoft notes that manually specified NTP sources aren’t authenticated, unlike time inside the domain hierarchy.

### DFS and file services (DM_080, medium)

A domain-based DFS namespace has a path that starts with the domain name (\\domain\root), and its configuration lives in AD DS. When the domain is retired, those paths fail silently in drive mappings, shortcuts, scripts, and embedded links.

Migration targets:

- SharePoint Online and OneDrive, for collaborative content.

- Azure Files with Microsoft Entra Kerberos, which lets Entra ID issue the Kerberos tickets for SMB access. Cloud-only identities no longer need a domain controller for authentication or authorization; hybrid identities still need line of sight to a domain controller to set Windows ACLs.

- A standalone DFS namespace, whose configuration lives in the namespace server’s registry rather than AD. With root consolidation it can keep an old file server’s UNC path (\\oldserver\share) working after migration, which Microsoft recommends when migrating shares to Azure Files.

Drive mappings delivered by Group Policy move with the device management adapter.

### Kerberos for whatever remains

Every adapter above shrinks the set of resources that still need an AD Kerberos ticket, but rarely to zero during the transition. Microsoft Entra Kerberos bridges the gap for Entra-joined and hybrid-joined Windows devices: Entra ID issues a cloud ticket-granting ticket for cloud resources such as Azure Files and a partial ticket that an on-premises domain controller exchanges for a full one. The on-premises half requires users synchronized from AD. It’s a bridge for the transition, not a target state.

## The six migration phases

Every adapter follows the same six-phase, governance-gated migration.

| Phase | What happens | Governance gate |
| --- | --- | --- |
| 1. Discover | Complete inventory of what AD encodes for this service | Inventory signed off by the service owner |
| 2. Normalize | Rationalize decades of organic growth into a clean model | Normalized model reviewed against the canonical model |
| 3. Map | Translate AD governance constructs to modern equivalents | Mapping validated: no governance gaps, no orphaned objects |
| 4. Migrate | Execute with continuous validation | Each step validated before the next; no big-bang cutover |
| 5. Validate | Confirm governance integrity after migration | Full drift scan, telemetry confirmation, user experience check |
| 6. Decommission | Retire the legacy infrastructure after a stability window | Legacy systems offline, rollback window expired with no incidents, provenance archived for audit |

An adapter that adds a net-new capability without retiring legacy infrastructure may record Phase 6 as N/A — net-new capability, with a short justification in its registry entry.

### Canon phase mapping

Each adapter’s operational guide may have its own internal steps, but every guide, existing or future, must open with a canon phase mapping table that maps its steps onto the six phases above. Two guides serve as reference implementations. The DNS modernization guide maps eleven internal steps onto the six phases; the PKI modernization guide maps six onto six. The mapping is what lets a program manager read the status of a DNS migration and a RADIUS migration on the same scale.

## Adapter registration

Every adapter registers in the program’s migration adapter registry (migration-adapter-registry.yaml), validated against a JSON schema (migration-adapter-registry.schema.json). Each entry records:

- Adapter ID and name.

- Priority tier: CRITICAL, HIGH, or MEDIUM.

- Current migration phase, one of Discover, Normalize, Map, Migrate, Validate, Decommission, or N/A — net-new capability.

- Dependencies: which adapters must complete first.

- Validation criteria: machine-checkable success conditions.

- Canon crosswalk: links to the relevant FMP_ canon documents. The older MOD_ document namespace has been retired into FMP_.

The registry lives with the adapter specifications in the program’s source tree under src/fmp/modernization/directory-migration/, alongside the full adapter interface specifications and vendor manifests (adapters/), the eight core concepts, and the AD dependency inventory.

## Post-migration validation

After all adapters have moved, the program’s validation checklist (DM_090) is the pass/fail gate for each service category before AD decommission is authorized. The gate restates each adapter’s own validation criteria in one place:

| Service | Passes when |
| --- | --- |
| DNS and DHCP | Zones resolve without AD-integrated storage; no client still depends on DC locator records; no rogue DHCP |
| PKI | Every renewal in the expiry window issued by the new CA; trust chain validated on every platform |
| RADIUS | Every RADIUS client points at the new service; 30-day parallel window closed with no failures |
| LDAP | Every application in the dependency map validated against its target; no bind traffic to domain controllers |
| Sync engine | All six retirement criteria true |
| Devices | Every workload on Intune; no GPO setting left without a decision |
| Time | Every device and server has an explicit, policy-set time source |
| File services | No domain-based namespace path in use |

## The transformation inventory

The adapters need data, and that data comes from the identity and directory transformation inventory: a structured assessment of the current estate that answers what exists, what depends on it, and what must be decided before anything is moved or retired.

| Category | Key questions |
| --- | --- |
| Forest and domains | Functional levels, trusts, sites, domain controllers |
| Users | Count, privileged, service, stale, external |
| Groups | Count, nested, privileged, dynamic or static |
| Computers | Domain-joined, OS distribution, last logon |
| Authentication | NTLM usage, Kerberos delegation, certificate-based |
| Applications | Apps that require AD, LDAP, or Kerberos |
| Group Policy | Count, high-risk settings, link structure |
| DNS and PKI | Zones, CAs, templates, issued certificates |
| Dependencies | Systems that break if a domain controller, GPO, or trust is removed |

The output is a decision-ready inventory that feeds identity transformation sequencing, GPO sunset planning, application remediation, and residual-risk acceptance. Chapter 07 explains how to collect it without changing the forest, and Chapter 08 turns it into an assessment.

## Continue the book

← Previous: Chapter 03 — Active Directory and Entra ID, Side by Side · Book index · Next: Chapter 05 — Delegation Without OUs →

# Chapter 05 — Delegation Without OUs

In Active Directory the OU tree was the delegation model; in Entra ID the scope has to be declared on purpose, from governed attributes.

## In this chapter

Why removing OUs removes the delegation model, and the two bad choices organizations fall into. What administrative units are, what they don’t do, and what dynamic and restricted management units cost and constrain. The program’s three-tier model and role assignment matrix, corrected against current Microsoft behavior, followed by the delegation principles and the drift checks that keep the matrix true.

In Active Directory, delegation was implicit. Place a user in an OU, grant an administrators’ group rights on that OU, and delegation was done. Every branch of the tree defined a scope of management authority, and the tree was usually drawn to match the organization.

Microsoft Entra ID has no OUs. Its directory is flat: every user sits at the same level. Without a replacement for OU-based scope, organizations make one of two bad choices:

- Over-delegate. Give administrators tenant-wide roles such as User Administrator, or worse Global Administrator, because nothing narrower exists. This breaks least privilege and produces audit findings.

- Under-delegate. Keep all administration with a small central team, so every password reset, group change, and profile update becomes a ticket and a queue.

Administrative units (AUs) are the replacement. They create scope boundaries inside the flat directory. The program’s Delegation Matrix (FMP_154) names the canonical AUs and the role assignments they carry. This chapter presents that matrix with the corrections that current Microsoft behavior requires.

The three-tier delegation model: tenant-scoped readers above department and division administrative units.

## What administrative units are

An administrative unit is a Microsoft Entra resource that contains users, groups, or devices, and nothing else. Assigning a role at the scope of an AU limits that role’s permissions to the AU’s members. A user can belong to several AUs, for example one for geography and one for division. The constraints matter more than the definition:

- AUs can’t be nested. There’s no tree. A department AU and its division AUs are siblings; “division inside department” is a naming convention and a design intent, not containment.

- A group in an AU brings the group, not its members. An administrator scoped to the AU can rename the group and change its membership, but can’t manage the users in it or reset their passwords unless those users are themselves members of the AU.

- AUs scope management, not visibility. They don’t stop administrators or users from browsing users and groups outside the AU with their default permissions in the Entra admin center or PowerShell. Only the Microsoft 365 admin center filters out users outside a scoped administrator’s AUs. Treat AUs as a write boundary, not a confidentiality boundary.

- Only some roles can be scoped to an AU. The list includes User Administrator, Groups Administrator, Helpdesk Administrator, Password Administrator, Authentication Administrator, Privileged Authentication Administrator, License Administrator, Cloud Device Administrator, and a few others, plus custom roles with permissions over users, groups, or devices. AU-scoped Helpdesk and Password Administrators can reset passwords only for users who don’t hold administrator roles.

- Licensing. Each administrator assigned a role over an AU needs Microsoft Entra ID P1; members need only Entra ID Free.

### Dynamic administrative units

An AU’s membership can be maintained by a rule, using the same attributes as dynamic membership groups. That’s what lets the program derive scope from HR-sourced attributes instead of hand-maintained lists. A dynamic AU has limits of its own:

- One object type per AU: users or devices, not both. Dynamic rules for groups aren’t supported.

- Every unique user who is a member of one or more dynamic AUs must be covered by an Entra ID P1 license count; devices need no license.

- Dynamic AUs are available in the global Azure cloud, not in specialized clouds such as Azure Government. A tenant in a Microsoft government cloud may have to maintain membership another way.

- Dynamic groups and dynamic AUs together can’t exceed 15,000 per tenant, and a rule can’t exceed 3,072 characters.

- Membership can’t be edited by hand; to add a single exception, extend the rule with an -or clause.

### Restricted management administrative units

A restricted management AU protects its members from tenant-level administrators. Only administrators with a role assigned at the scope of that AU (or of another restricted management AU the object belongs to) can change the Entra properties of its users, groups, and devices. Tenant-scoped Global Administrators and Privileged Role Administrators can’t modify the objects, but they can manage the AU itself: create or delete it, add and remove members, and assign roles over it, including to themselves. Those actions are written to the audit log.

Restricted management has limits that shape any design that uses it:

- The setting is chosen when the AU is created and can’t be changed afterward.

- A tenant can have at most 100 restricted management AUs.

- Users and groups in a restricted management AU can’t be managed by Microsoft Entra ID Governance features: Privileged Identity Management, entitlement management, lifecycle workflows, and access reviews.

- Role-assignable groups added to one can’t have their membership modified, except by Global Administrators and Privileged Role Administrators.

- Operations whose role can’t be AU-scoped become impossible inside it. For example, nobody can reset the password of a Global Administrator who sits in a restricted management AU until that user is removed from it.

- Only users, devices, and security groups can be members; Microsoft 365, mail-enabled, and distribution groups can’t.

- Applications can’t modify members through Microsoft Graph application permissions; they need an Entra role assigned at the AU’s scope.

## The three-tier model

| Tier | Scope | Who | What they can do |
| --- | --- | --- | --- |
| Tier 1 | Enterprise | Security, compliance, executives | Read-only visibility across all governed principals |
| Tier 2 | Department or division | Department administrators | Full user lifecycle management within their AU |
| Tier 3 | Sub-team (department, division, and role tier) | Help desk and per-team administrators | Password resets and basic user support within a narrow AU |

The program’s matrix mapped each tier to an AU: AU-Enterprise for Tier 1, department AUs such as AU-Department-IT for Tier 2, and division AUs such as AU-IT-CyberOps for Tier 3. Tier 1 needs a correction. Its roles (Global Reader, Security Reader, Reports Reader) aren’t on the list of roles that can be assigned at AU scope, so they’re assigned at tenant scope. Because AUs don’t restrict reading anyway, a tenant-scoped reader role delivers exactly the “read-only visibility across everything” that Tier 1 calls for.

AU-Enterprise keeps a narrower job: it defines the governed population. Its rule treats a populated Department attribute as the “this principal has been HR-provisioned” predicate, (user.department -ne null). That population is useful for reporting and for scoping services that accept AUs, such as Microsoft Purview, but it isn’t the scope of the Tier 1 role assignments.

## Administrative unit registry

### Enterprise AU (Tier 1 population)

| AU | Membership | Restricted management |
| --- | --- | --- |
| AU-Enterprise | Dynamic: (user.department -ne null) | No (see below) |

### Department AUs (Tier 2)

| AU | Department | Membership |
| --- | --- | --- |
| AU-Department-IT | IT | Dynamic: (user.department -eq "IT") |
| AU-Department-HR | HR | Dynamic: (user.department -eq "HR") |
| AU-Department-Finance | Finance | Dynamic: (user.department -eq "Finance") |
| AU-Department-Legal | Legal | Dynamic: (user.department -eq "Legal") |
| AU-Department-Engineering | Engineering | Dynamic: (user.department -eq "Engineering") |
| AU-Department-Operations | Operations | Dynamic: (user.department -eq "Operations") |
| AU-Department-Sales | Sales | Dynamic: (user.department -eq "Sales") |
| AU-Department-Executive | Executive | Dynamic: (user.department -eq "Executive") |

### Division AUs (Tier 3, created on demand)

| AU | Scope |
| --- | --- |
| AU-IT-CyberOps | IT / CyberOps |
| AU-IT-InfraOps | IT / Infrastructure |
| AU-IT-AppDev | IT / AppDev |
| AU-Legal-GRC | Legal / GRC |

Division AUs use a rule that combines the department with the division attribute the HR feed supplies. Which attribute carries the division is a schema decision; the program’s canonical attribute schema is described in the HR-driven IAM series.

## Role assignment matrix

| Role | Assigned to | Scope | Tier |
| --- | --- | --- | --- |
| Global Reader | IT-CyberOps-Users | Tenant | 1 |
| Security Reader | Legal-GRC-Users | Tenant | 1 |
| Reports Reader | Department-Executive-Users | Tenant | 1 |
| User Administrator | Finance-Admins | AU-Department-Finance | 2 |
| Groups Administrator | Finance-Admins | AU-Department-Finance | 2 |
| User Administrator | HR-Admins | AU-Department-HR | 2 |
| User Administrator | IT-Admins | AU-Department-IT | 2 |
| Helpdesk Administrator | IT-CyberOps-Admins | AU-IT-CyberOps | 3 |
| Password Administrator | IT-CyberOps-Admins | AU-IT-CyberOps | 3 |
| Authentication Administrator | IT-InfraOps-Admins | AU-IT-InfraOps | 3 |

Two corrections to the principals in this table:

- The groups that hold roles must be role-assignable, and role-assignable groups can’t be dynamic. The earlier design derived the *-Admins groups from the *-Users groups by a dynamic rule. Entra ID doesn’t allow that: a role-assignable group’s membership type must be Assigned, the isAssignableToRole property can only be set at creation, nested groups aren’t allowed, and a tenant can have at most 500 role-assignable groups. The program’s position is to keep the *-Admins groups assigned, populate them through an approval workflow, and make members eligible rather than permanently active through Privileged Identity Management, which supports eligible assignments scoped to an AU.

- Tier 1 assignees need the same treatment. The *-Users groups in the Tier 1 rows are department populations. If they’re dynamic, they can’t hold a role. Assign Tier 1 roles to a separate assigned, role-assignable group for each reader population.

How one scoped delegation is built from an HR attribute, an administrative unit, a role-assignable group, and a scoped role assignment.

## Illustrative code

The PowerShell in this chapter is illustrative and hasn’t been tested against a production tenant. Review it and run it first in a test tenant. The scope string /administrativeUnits/<id> grants management of the AU’s members, not of the AU itself.

# Illustrative: assign User Administrator to Finance-Admins over AU-Department-Finance
Connect-MgGraph -Scopes 'RoleManagement.ReadWrite.Directory', 'AdministrativeUnit.Read.All', 'Group.Read.All'

$au    = Get-MgDirectoryAdministrativeUnit -Filter "displayName eq 'AU-Department-Finance'"
$group = Get-MgGroup -Filter "displayName eq 'Finance-Admins'"
$role  = Get-MgRoleManagementDirectoryRoleDefinition -Filter "displayName eq 'User Administrator'"

New-MgRoleManagementDirectoryRoleAssignment `
    -DirectoryScopeId ('/administrativeUnits/' + $au.Id) `
    -PrincipalId $group.Id `
    -RoleDefinitionId $role.Id

## Restricted management: a per-AU decision

The program’s matrix marked every AU as restricted management and called that non-negotiable, on the reasoning that restriction prevents privilege escalation because even a Global Administrator can’t bypass AU-scoped delegation. The documented behavior is narrower. A Global Administrator can’t edit a protected object directly, but can add or remove the AU’s members and assign themselves a role over it; restriction makes that bypass deliberate and audited, not impossible.

Applied to every AU, restriction also collides with the rest of this book. HR-driven provisioning relies on lifecycle workflows, access packages, access reviews, and PIM, and none of those can manage users or groups inside a restricted management AU. An AU-Enterprise that is both restricted and dynamic over every HR-provisioned user would take the whole governed workforce out of Entra ID Governance and out of reach of every tenant-scoped administrator.

So this chapter treats restriction as a per-AU decision with a default of no:

| Use restricted management for | Don’t use it for |
| --- | --- |
| Executive accounts and their devices | Broad department populations under HR-driven lifecycle |
| Break-glass and other high-value accounts that must not be reset by the help desk | AU-Enterprise |
| Security groups that gate sensitive applications | Groups governed by access packages, access reviews, or PIM for Groups |
| Populations with a legal or regional rule on who may administer them | Anything that needs Microsoft 365 or distribution groups as members |

Because the setting can’t be changed after creation, decide it before the AU exists, and record the decision in the registry entry. The program default is unrestricted; restriction is chosen per AU where the table above calls for it.

## Delegation principles

Delegation defines who may perform which actions on which objects. In a modernized environment the scope comes from governed attributes, not from OUs. Five principles govern every row of the matrix:

| Principle | Implication |
| --- | --- |
| Least privilege | Each role is limited to the minimum actions required |
| Scoped by attribute | Scope is an attribute value or combination, not a manually maintained group |
| Time-bound where possible | Standing access is the exception; eligible assignments are the default |
| Recorded | Every delegation has an owner, a scope, and a review date |
| Separated | Requestor and approver are different people for high-privilege actions |

These map to the access control family of NIST SP 800-53 Revision 5, which federal systems are assessed against. Review cadence follows the risk of the scope:

| Scope | Typical roles | Review cadence |
| --- | --- | --- |
| Single department | Help desk, local administration | Quarterly |
| Division or region | Tier 2 operations | Quarterly |
| Privileged roles | Identity administrators | Monthly or on change |
| Break-glass | Emergency only | Continuous monitoring |

Delegation stays auditable when the scope is a governed attribute and the assignment is recorded. Manual group membership as the only scope mechanism loses that.

## Drift detection

The registry and matrix are the desired state; the tenant is the actual state. Drift detection compares them on a schedule and classifies every difference.

| Drift type | Severity | Auto-fix |
| --- | --- | --- |
| AU membership drift: rule in the tenant differs from the registry | High | Yes: reapply the registry rule |
| AU rule processing paused | High | Yes: set processing back to On |
| Role assignment drift: an assignment not in the matrix | Critical | No: investigate |
| Restriction mismatch: the AU’s restricted setting differs from its registry decision | Critical | No: the setting is immutable; create a correctly configured AU, move role assignments and members, then delete the old one |
| Orphaned AU: no role assignments | Low | No: flag |
| Missing AU: registry entry with no tenant AU | High | Yes: create it with the registry’s restriction setting |
| Dynamic group used as a role principal | Critical | Not possible in Entra ID; flag any registry entry that assumes it |

Two of these rows differ from the source design. “Unrestricted AU” was marked auto-fixable; it can’t be, because the restricted setting can only be set at creation. “Rule processing paused” is new: an AU’s dynamic rule can be paused, and a paused rule leaves membership frozen while every other check passes. Restricted management changes are recorded in the Entra audit log (adding a restricted AU, adding or removing members, and adding or removing role members scoped over it), which gives the drift engine an event stream to watch between scheduled comparisons.

The scheduled comparison starts from a read of the tenant’s actual state:

# Illustrative, read-only: export AU state and AU-scoped role assignments for comparison
Connect-MgGraph -Scopes 'AdministrativeUnit.Read.All', 'RoleManagement.Read.Directory'

$aus = Get-MgDirectoryAdministrativeUnit -All -Property Id, DisplayName, IsMemberManagementRestricted, MembershipType, MembershipRule, MembershipRuleProcessingState

$state = foreach ($au in $aus) {
    $scoped = Get-MgDirectoryAdministrativeUnitScopedRoleMember -AdministrativeUnitId $au.Id -All
    [pscustomobject]@{
        DisplayName     = $au.DisplayName
        Restricted      = [bool]$au.IsMemberManagementRestricted
        MembershipType  = $au.MembershipType
        MembershipRule  = $au.MembershipRule
        RuleProcessing  = $au.MembershipRuleProcessingState
        RoleAssignments = $scoped.Count
    }
}

$state | Export-Csv -Path .\au-actual-state.csv -NoTypeInformation

Chapter 10 covers how drift findings feed remediation and evidence.

## Continue the book

← Previous: Chapter 04 — The Hidden Migration Surface · Book index · Next: Chapter 06 — Who Owns the Migration →

# Chapter 06 — Who Owns the Migration

Active Directory let a handful of domain administrators own identity by default; Entra ID spreads that ownership across people and tools, so the migration has to assign it on purpose.

## In this chapter

The first half names the people: who decides, who does the work and who is consulted, from the executive sponsor and authorizing official down to the help desk and end users, with a responsibility matrix and the Entra roles each team should hold. The second half names the tools: what each Microsoft-native tool does and doesn’t do for this migration, a compressed capability matrix and gap analysis, and the line between what the program consumes and what it builds.

In an Active Directory estate, ownership of identity was rarely written down because it didn’t need to be. Domain Admins could change anything, the OU tree encoded who managed whom, and most decisions about accounts, groups and Group Policy were made by the same small team that ran the domain controllers. Chapter 05 explains why that delegation model doesn’t survive the move to a flat directory. This chapter deals with the human version of the same problem. Once identity becomes a cloud control plane that Conditional Access, device compliance, application access and audit evidence all depend on, the decisions about it belong to more people than the directory team, and some of them carry legal accountability.

Federal policy already says so. OMB M-19-17 directs each agency to designate an integrated, agency-wide ICAM office, team or other governance structure, and says it should include personnel from the offices of the CIO, the CFO, Human Resources, General Counsel, the CISO, the Senior Agency Official for Privacy, the Chief Acquisition Officer and physical security, along with the components that run ICAM capabilities. NIST’s Risk Management Framework defines the accountable roles, such as the authorizing official, the senior agency information security officer, the system owner and the system security officer, and says what each one is responsible for. Neither document tells an agency who decides how to replace an OU-based delegation model, or who signs off on moving a wave of users to cloud authentication. That part is the program’s recommended model, set out below.

Who decides, who supplies authority and design, and who does and supports the work in an Active Directory to Entra ID migration.

## The people

### Decision rights and work are different things

The program separates three kinds of involvement. A role decides when it is accountable for the outcome and can say no. A role does the work when it builds, configures or runs the thing. A role is consulted when the decision can’t be made well without its input, but the decision isn’t its to make. Every decision in the matrix below has exactly one decider. Many have several doers.

The split matters because the AD habit is to let the people who can make a change also decide whether to make it. In Entra ID that habit is how an identity engineer ends up choosing the agency’s risk posture by default, for example by leaving legacy authentication open because nobody told them to close it. The authorizing official is the only organizational official who can accept security and privacy risk on the organization’s behalf, so decisions that amount to accepting risk have to reach that person, not stop at the console.

### The roles

The following descriptions combine NIST’s role definitions, where NIST defines the role, with the program’s recommended assignments for this migration, where it doesn’t.

The executive sponsor and the CIO set scope, funding and sequence. Under the RMF, the CIO designates the senior agency information security officer, maintains security policy and oversees personnel with significant security responsibilities. In this migration the CIO’s organization also usually holds the system owner role for the identity platform, which NIST describes as the official responsible for a system’s procurement, development, integration, operation, maintenance and disposal. The program recommends that the sponsor own the migration schedule, decide when Active Directory components are retired, and break ties between teams.

The CISO, acting as the senior agency information security officer, carries out the CIO’s security responsibilities and is the primary liaison to authorizing officials, system owners and system security officers. In the program’s model the CISO decides the control requirements that the target has to meet: phishing-resistant authentication, the Conditional Access baseline, the privileged-access model and logging. The security operations team inside that organization receives the identity detections and privileged-activation alerts that the target produces.

The authorizing official accepts residual risk and authorizes the system. For this migration that means the Entra ID tenant and its interconnections, plus every point where the program proposes to carry risk instead of removing it: a deferred legacy-authentication cutoff, a service account that can’t be converted yet, a deviation from a mandatory baseline. CISA’s BOD 25-01 states this explicitly for cloud configuration baselines. Agencies must explain any deviation from a mandatory SCuBA policy, and authorizing officials may accept the risk under agency policy.

The information system security officer is responsible for keeping the system’s security posture in place day to day and advises on its controls, working closely with the system owner. In the program’s model the ISSO assembles the evidence an assessor will read, tracks findings to closure, and is consulted on every design decision that changes a control.

Identity engineering designs and builds the target. NIST’s systems security engineer and system administrator roles describe the two halves of that work. In this migration identity engineering owns the sync design, authentication methods, Conditional Access policies, the administrative-unit delegation model, Privileged Identity Management settings and the governance features. It is the team most likely to be over-trusted, because it holds the most powerful Entra roles. The program’s answer is to give it the roles it needs and route its risk-bearing decisions upward, not to slow it down.

Active Directory administrators run the source estate until it is retired. They clean up stale objects and UPN suffixes before sync, run the hosts that sync depends on, and eventually decommission domain controllers, AD FS and the AD-dependent pieces that Chapter 04 catalogs. Microsoft classifies the Cloud Sync provisioning agent server as a tier 0 server, and creating the agent’s group managed service account requires Domain Administrator or Enterprise Administrator credentials. Those tasks stay with the AD administrators. The same team often knows more than anyone else about why a group or a delegation exists, so the program consults them on every mapping decision.

Application owners decide for their own applications. They know which service accounts, Kerberos dependencies, LDAP binds and hard-coded groups their application needs, and they’re the only people who can accept a test result or a cutover window for it. The identity modernization guidance the program follows already treats them as reviewers of application assignments and requires at least two human owners for every app registration. The program extends that to the migration itself: no application moves without its owner’s sign-off.

The help desk supports users through the change and becomes a high-value target while it does. Help desk staff reset passwords, re-register authentication methods and issue Temporary Access Passes for onboarding and recovery. In Entra ID, an Authentication Administrator can create a Temporary Access Pass for members but not for administrators. Only a Privileged Authentication Administrator can do that for admins. The program scopes help desk roles to administrative units, as Chapter 05 describes, and makes the help desk’s identity-verification procedure a CISO decision, not a help desk one.

HR supplies the facts the directory can’t verify on its own: who is a worker, what kind of worker, where they sit and who they report to. In an AD estate those facts were typed in by administrators, if anyone recorded them at all. In the target, they should arrive from the HR system of record and drive account creation, changes and removal. The HR-driven identity series covers that source-of-authority model in full, including why contractors need a separate authoritative source. For this book’s purposes, HR decides what the authoritative attributes mean, and identity engineering decides how they flow.

End users are participants, not bystanders. NIST’s definition of the system user includes following acceptable-use policy and reporting anomalous or suspicious behavior. In this migration users register phishing-resistant methods, join pilot waves and report what breaks. The program treats registration rates and help desk ticket volume as go/no-go inputs for each wave.

### The responsibility matrix

The matrix is the program’s recommended model. Adapt it to the agency’s governance structure, but keep the rule of one decider per row.

D = decides (accountable) · R = does the work · C = consulted · blank = informed at most.

| Decision or work item | Sponsor / CIO | CISO | AO | ISSO | Identity eng. | AD admins | App owners | Help desk | HR | Users |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Migration scope, funding and sequence | D | C | C |  | C | C | C |  | C |  |
| Sync tool and authentication method (Chapter 09) |  | C |  | C | D, R | C | C |  |  |  |
| Authorize the tenant; accept residual risk | C | C | D | R | C |  |  |  |  |  |
| Control requirements (MFA strength, Conditional Access baseline, logging) |  | D | C | R | R |  |  |  |  |  |
| Privileged role mapping and PIM settings |  | D |  | C | R | C |  |  |  |  |
| Delegation model: OUs to administrative units (Chapter 05) |  | C |  | C | D, R | C |  | C |  |  |
| Directory hygiene before sync (stale objects, UPN suffixes, filtering) |  |  |  |  | D | R | C |  |  |  |
| Authoritative worker attributes and their meaning |  |  |  | C | R |  |  |  | D |  |
| Service account conversion, per application |  | C |  |  | R | R | D |  |  |  |
| Application sign-in migration and testing |  |  |  |  | R |  | D, R |  |  | C |
| Pilot and wave go/no-go (Chapter 10) | C | C |  | C | D | C | C | C |  | C |
| Help desk identity verification and Temporary Access Pass procedure |  | D |  | C | C |  |  | R |  |  |
| Access review cadence and reviewers |  | D |  | C | R |  | R |  | C |  |
| Legacy authentication cutoff | C | C | D | C | R | R | C | C |  |  |
| Retire AD FS, domain controllers and AD-dependent services | D | C | C | C | R | R | C |  |  |  |
| Continuous monitoring evidence and drift findings |  | D | C | R | R |  |  |  |  |  |
| User readiness: method registration and communications | D |  |  |  | C |  |  | R |  | R |

Two rows need comment. The legacy-authentication cutoff sits with the authorizing official because the alternative, keeping it open, is a risk acceptance. Retiring AD components sits with the sponsor because it’s a system-ownership decision that ends a fallback the rest of the program relies on. The ISSO and the authorizing official are consulted on it because it changes the authorization boundary.

### Entra roles for each team

Decision rights don’t change what a console lets someone do. Roles do. The program maps each team to the least-privileged Microsoft Entra built-in roles for its work, assigns privileged ones as eligible through PIM, and scopes help desk roles to administrative units. Chapter 10 covers the PIM rollout itself.

| Team | Work | Least-privileged Entra role(s) |
| --- | --- | --- |
| Identity engineering (sync) | Configure Cloud Sync or Connect Sync, password hash sync, pass-through authentication, federation settings | Hybrid Identity Administrator |
| Identity engineering (governance) | Lifecycle Workflows; access reviews and access packages | Lifecycle Workflows Administrator; Identity Governance Administrator |
| Help desk | Password resets and basic support in scope; Temporary Access Pass for members | Helpdesk Administrator or Authentication Administrator, scoped to an administrative unit |
| CISO, ISSO, assessors | Read configuration and risk without changing it | Global Reader; Security Reader |
| Small, named group | Assign roles and manage PIM | Privileged Role Administrator, eligible only, with approval |

Restricted management administrative units add a further check. Tenant-level administrators, Global Administrators included, can’t modify objects in them unless they assign themselves a role scoped to the unit, and that assignment is written to the audit log. That makes the self-assignment visible, which is the property the program wants, but it doesn’t make Global Administrator a low-risk role.

## The tools

Microsoft provides the instruments; the program provides the orchestra.

“Doesn’t Microsoft already do this?” is the first question a sponsor asks, and the honest answer is that Microsoft does most of the individual pieces well and none of the connecting. Each Microsoft tool solves one part of the migration and keeps its results in its own portal, report or log. None of them produces one correlated record of the source estate, the target and the drift between them. The program’s position is the same one it takes toward CISA’s ScubaGear. It doesn’t compete with the native tools. It consumes their output and supplies the governance layer above it. Microsoft provides the instruments. The program provides the orchestra.

### What each tool does and doesn’t do

Names, capabilities and license tiers below were checked on October 20, 2026. Licensing changes often. Confirm against the agency’s own agreements before planning purchases.

| Tool | What it does for this migration | What it doesn’t do | License tier |
| --- | --- | --- | --- |
| Microsoft Entra Cloud Sync | Synchronizes users, groups, contacts and, with device sync, computer objects from AD to Entra ID through lightweight agents configured in the cloud. Supports disconnected forests and multiple active agents, and is the platform for new features such as group provisioning to AD and source-of-authority changes. | Has lower documented limits than Connect Sync (150,000 objects per domain, 50,000-member groups) and doesn’t configure pass-through authentication. Not an assessment tool. | Provisioning groups back to AD requires Entra ID P1. |
| Microsoft Entra Connect Sync | The on-premises sync engine, with richer sync-rule customization. Microsoft says Cloud Sync is replacing it, and that it will be retired once Cloud Sync reaches full functional parity. | Not an assessment tool: no OU, GPO, DNS or PKI analysis. Connect Sync must be upgraded to version 2.6.84.0 or later and configured for application-based authentication by April 7, 2027, or synchronization stops. | Free with the Azure subscription. |
| Microsoft Entra Connect Health | Monitors sync, AD FS and AD DS health through agents on each server. | Monitors health, not readiness or governance. | Entra ID P1 or P2. The first agent needs one license, and each additional agent needs 25 more. |
| Microsoft Entra ID Governance | Lifecycle Workflows, entitlement management, access reviews and PIM, all reachable through Microsoft Graph. Available in GCC, GCC High and DoD. | Doesn’t decide who should have access, or supply the HR facts it acts on. | Lifecycle Workflows, and access reviews for member users, require Entra ID Governance or Entra Suite. Some entitlement-management and review capabilities work with P2. |
| Microsoft Entra ID Protection | Sign-in and user risk detection, risk-based Conditional Access, risk reports through Graph. | Doesn’t assess the AD source. Some detections depend on Defender licensing. | Full capability requires Entra ID P2 or Entra Suite. |
| Microsoft Defender for Identity | Sensors on domain controllers, AD CS, AD FS and Entra Connect servers. Detects identity attacks and publishes security posture assessments in Secure Score across hybrid security, identity infrastructure, certificates, Group Policy, accounts and cloud identities. Its data is queryable in advanced hunting and through the Defender XDR APIs, and can be streamed to Sentinel. | Not an inventory tool: no forest topology export, OU tree, full GPO inventory, DNS assessment or trust inventory. Certificate-authority assessments need a sensor on the AD CS server. Advanced hunting keeps data for 30 days. | EMS E5, Microsoft 365 E5 or E5 Security, or standalone. In GCC: Microsoft 365 GCC G5, G5 Security GCC or standalone. |
| Microsoft Graph | The single API endpoint for users, groups, applications, devices, roles and governance in Entra ID. | Raw building blocks with no orchestration or reporting. | Calling a feature through an API still needs that feature’s license; Intune’s licensing terms say so explicitly. |
| Microsoft Intune with Group Policy analytics | Imports GPO XML exports, reports MDM support per setting, shows whether each GPO is linked to an OU, exports the view to CSV, and migrates supported settings to a settings catalog policy. Flags conflicting settings across imported GPOs during migration. | Analyzes Windows settings only. Each GPO export must be under 4 MB, and non-English, non-ADMX settings skew the MDM support percentage. No WMI-filter analysis or tracking of migration status over time. | Intune is licensed through Plan 1 and higher plans, usually inside a Microsoft 365 bundle. |
| Security Compliance Toolkit | Policy Analyzer compares sets of GPOs against Microsoft baselines and local policy, and highlights redundant settings and internal inconsistencies across a set. LGPO manages local policy. Baselines include Windows Server 2025. | Desktop tools with Excel output, no automation pipeline, and no OU, DNS, PKI or trust analysis. | Downloaded from the Microsoft Download Center with the baselines. |
| Azure Arc with Azure Machine Configuration | Audits and enforces OS and application settings on Arc-enabled servers with Azure Policy. Machine Configuration was formerly called Azure Policy Guest Configuration. | Requires Arc enrollment, so it can’t assess before onboarding. No AD-specific analysis. | Included at no extra charge for Windows Server with Software Assurance or pay-as-you-go licensing. Otherwise billed per server. |
| Microsoft Purview Audit | Searchable audit log covering Entra ID and Microsoft 365 activity, with export to CSV and access through the Office 365 Management Activity API. Standard keeps records for 180 days. Premium keeps Entra ID, Exchange and SharePoint records for one year, or up to 10 years with an add-on. | Audit, not configuration assessment. | Standard is enabled by default. Premium requires E5-level licensing or an add-on. |
| Microsoft Sentinel | SIEM for long-term retention and correlation of Entra, Defender for Identity and AD security events. | Detects threats. Doesn’t compare configuration against a desired state. Sentinel won’t be supported in the Azure portal after March 31, 2027, only in the Defender portal. | Billed as part of the agency’s Azure bill. |
| Microsoft Secure Score and the Zero Trust Assessment | Secure Score ranks recommended actions across identity, devices and apps. The Zero Trust Assessment is an open-source, read-only PowerShell module that tests hundreds of tenant configuration items across Entra, Intune and other services and produces a local report. | Both describe the cloud tenant, not the AD source. The assessment’s first run needs Global Administrator consent. Later runs need Global Reader and the other reader-level roles listed in its prerequisites. | Defender for Identity assessments in Secure Score need a Defender for Identity license. The Zero Trust Assessment is open source. |
| CISA ScubaGear | Assesses a Microsoft 365 tenant, including Entra ID, against CISA’s SCuBA baselines and writes HTML, JSON and CSV results. BOD 25-01 requires agencies to deploy CISA’s SCuBA assessment tools and report results. | Tenant configuration only. | Open source, published by CISA. |
| Azure Migrate | Discovers and assesses servers, databases and web apps for migration to Azure. | No AD forest, GPO, OU, DNS, PKI or trust analysis. Microsoft still points to the MAP Toolkit for Windows OS migration planning and software usage tracking. | Part of Azure. Microsoft charges no tool fee for migration during the first 180 days of a VM’s replication. |
| Active Directory Migration Tool (ADMT) | Moves users, groups and computers between AD domains and forests, with SID history and password migration. | Doesn’t move anything to Entra ID. Microsoft has deprecated the ADMT 3.2 code base, stopped development, and provides no security or bug fixes. It hasn’t been updated for Windows Server 2012 R2 or later, and Microsoft says to use it at your own risk. | Free download. |
| Microsoft Entra Health monitoring | Tenant-level signals and anomaly alerts for MFA, Conditional Access and device-compliance sign-ins, plus monthly SLA attainment. | Cloud-side only, and scenario monitoring and alerts are still in preview. | Viewing the signals requires Entra ID P1 or P2. |
| FastTrack | Remote deployment guidance from Microsoft, including Entra Connect, Cloud Sync, authentication methods and hybrid identity. | Guidance only. No discovery, inventory or artifacts. | Tenants with 150 or more licenses from eligible plans. |

### The capability matrix

The matrix maps each assessment domain the program covers to the native tools that touch it. It replaces the source’s tool-by-tool grid with one row per domain. “Partial” means a native tool covers part of the domain but doesn’t produce a complete, versioned inventory that a governance process can track.

| Domain | Native coverage | Native tools that touch it | What’s missing |
| --- | --- | --- | --- |
| Forest topology (domains, DCs, functional levels, FSMO, sites) | Partial | AD PowerShell module (raw cmdlets); Defender for Identity (monitors DCs) | A structured, versioned topology artifact |
| OU hierarchy and delegation ACLs | None | AD PowerShell (raw) | Recursive tree with GPO links, object counts and delegation; see Chapter 05 |
| GPO inventory and settings | Partial | Group Policy analytics (Windows MDM subset, OU-linked flag, conflict check at migration); Policy Analyzer (baseline comparison, redundancy and inconsistency across a set); Defender for Identity (Group Policy posture) | Full inventory including server GPOs, link scope, WMI filters and migration status over time |
| DNS zones and records | None | AD and DNS PowerShell modules (raw) | Zone, record, scavenging and SRV assessment |
| PKI and AD CS | Partial | Defender for Identity certificate assessments (template misconfigurations such as ESC1 through ESC4 and ESC15; CA assessments with an AD CS sensor) | Operational PKI health (CRL, AIA, OCSP) and migration readiness |
| Computer objects | Partial | Azure Migrate (server discovery); Defender for Identity (stale entities) | AD-specific attributes: delegation, SPNs, group membership, LAPS |
| Users and groups | Partial | Defender for Identity (accounts posture); Entra Connect or Cloud Sync (sync state) | Complete governance inventory: nesting, service-account classification, ownership |
| Trusts | None | AD PowerShell (raw) | Direction, type, SID filtering, selective authentication |
| ACLs and dangerous delegation | Partial | Defender for Identity (selected dangerous permissions) | A complete delegation audit |
| Cloud tenant configuration | Strong | ScubaGear; Zero Trust Assessment; Secure Score | Correlation back to the AD source and to remediation owners |
| Cross-domain correlation | None | — | One assessment record joining all of the above |
| Drift against desired state | Partial | Machine Configuration (Arc servers); Secure Score and ScubaGear (tenant); Defender for Identity (security drift) | Governance drift against a canonical desired state, with an owner and a deadline |

The source analysis gave headline coverage figures for the native tools (about 30 percent of the discovery surface, 22 percent once governance was included). It labeled those figures illustrative, derived from its own matrix and not from any assessment run. This chapter doesn’t repeat them. The program’s position is that an agency gets its own numbers by running the read-only assessment in Chapter 07 and Chapter 08 against a representative forest, then counting which findings each tool surfaced.

### The gap analysis

| Category | Native strength | Who owns the gap |
| --- | --- | --- |
| Server discovery | Strong for hardware and VM inventory | Consume Azure Migrate. The program adds AD attributes. |
| Group Policy | Partial: client MDM subset and baseline comparison | The program builds the full inventory, including server GPOs and link scope |
| Security posture | Strong for detection and posture recommendations | Consume Defender for Identity. The program adds correlation. |
| Cloud tenant configuration | Strong | Consume ScubaGear and the Zero Trust Assessment |
| DNS | None | Program-built |
| PKI and AD CS | Partial, security findings only | Program-built health and readiness |
| Trusts | None | Program-built |
| OU and delegation | None | Program-built (Chapter 05) |
| Cross-domain correlation | None | Program-built, the core of the pipeline |
| Governance pipeline and drift | Security drift only | Program-built |

### What the program consumes and what it builds

| Domain | Decision | Why |
| --- | --- | --- |
| Server inventory | Consume Azure Migrate exports | Better at hardware and VM discovery than anything the program would write |
| GPO MDM readiness | Consume Group Policy analytics exports | Microsoft maintains the setting-to-CSP mapping and updates it automatically |
| Identity security posture | Consume Defender for Identity findings | Agencies with E5 or G5 licensing already have it, and it covers AD CS and Group Policy posture |
| Security baselines | Consume Policy Analyzer output | Free, maintained, authoritative |
| Tenant configuration | Consume ScubaGear output | Required reporting under BOD 25-01, and the same baselines the assessors use |
| Lifecycle, access reviews, PIM | Consume Entra ID Governance through Graph | The target’s own controls; the program reads their state and results |
| Forest topology, OU tree, trusts, DNS | Build | No native tool inventories them |
| Full GPO inventory | Build | Group Policy analytics covers the Windows MDM subset only |
| PKI and AD CS health | Build | Defender for Identity covers the security subset only |
| Cross-domain correlation and governance drift | Build | The program’s reason to exist |

The program-built discovery is read-only and PowerShell-first, using the same Active Directory cmdlets an AD administrator already knows. Appendix B and Appendix C document the modules; Chapter 07 covers the read-only stage.

### How the program consumes native output

The program’s import adapters (the FMPImportAdapters PowerShell module, specified in FMP_182) take a report that an operator or another tool has already exported and normalize it into the program’s assessment schema. The design is deliberately file-based. Each importer reads a report from -ReportPath and writes normalized JSON to -OutputPath, and the module never calls a live API. That keeps ingestion read-only, credential-free and auditable inside the agency’s boundary.

| Function | Consumes | Produces |
| --- | --- | --- |
| Import-FMPAzureMigrateReport | Azure Migrate assessment export | Computer inventory |
| Import-FMPGPOAnalyticsReport | Intune Group Policy analytics export | GPO migration tracker |
| Import-FMPDefenderFindings | Defender for Identity Secure Score export | Security assessment overlay |
| Import-FMPSCuBAReport | ScubaGear output | Conformance evidence |
| Import-FMPADReconReport | ADRecon output | Computer and identity inventory |
| Merge-FMPAssessmentSources | Several normalized sources | One correlated assessment bundle |

Each importer wraps its records in a provenance envelope (schema: fmp.import.v1) that records the source tool, its export version, the import time in UTC, a content hash over the normalized data, the source file, and the adapter’s identity and version. Merge-FMPAssessmentSources checks every envelope’s completeness and hash before it correlates them. An envelope that is incomplete, or whose hash no longer matches its data, is a provenance drift finding by definition. Policy Analyzer, Entra Connect Health and Azure Policy compliance exports are candidates for future adapters.

### Third-party tools

A few non-Microsoft tools overlap parts of the assessment. The program treats them as inputs or cross-checks, not competitors.

- ADRecon is an open-source PowerShell tool, licensed AGPL-3.0, that collects forest, domain, trust, site, OU, GPO, DNS, user, group, computer and SPN data. It writes CSV, XML, JSON, HTML and Excel output. The program uses it as a validation reference: the program’s own collection should capture at least what ADRecon captures.

- PingCastle is an Active Directory security assessment tool, now part of Netwrix.

- BloodHound Community Edition, from SpecterOps, maps attack paths through AD and Azure identity relationships using graph analysis. It’s licensed Apache 2.0.

- Purple Knight, from Semperis, is a free assessment of AD, Entra ID and Okta against more than 200 indicators of exposure and compromise.

## Ownership in practice

Put the two halves together and a pattern appears. Every native tool in this chapter has an owner in the matrix. Defender for Identity findings go to the CISO’s organization. Group Policy analytics belongs to identity engineering working with endpoint management. ScubaGear results go to the ISSO’s evidence. Entra ID Governance runs under identity engineering, with application owners and managers as reviewers. What no tool has, unless the program assigns it, is an owner for the gaps between them: the OU tree that nobody inventories, the trust nobody documented, and the drift that no single portal can see. That’s the work the program builds and keeps, and it’s why the governance pipeline needs a named owner as much as any Entra role does. Chapter 07 starts that work with read-only discovery.

## Continue the book

← Previous: Chapter 05 — Delegation Without OUs · Book index · Next: Chapter 07 — Read-Only Discovery →

# Chapter 07 — Read-Only Discovery

The first weeks of an engagement are spent waiting for access; spend them learning what the directory already tells everyone.

## In this chapter

Why the assessment starts with read-only access, and what that access actually covers in a default forest. Where the default read boundary sits: protected groups, confidential attributes, secrets, and restricted containers. How to turn what read-only discovery couldn’t see into a narrow, time-bound delegation request. And how to run the assessment so that it is visible to the security team and its output is protected.

An assessment team rarely gets privileged access on the first day. Authorization paperwork, security review and trust between the agency’s directory team and an outside team all take time. The program uses that window. A standard domain account, with no rights beyond what every employee already has, can read most of what the migration plan needs: the topology, the OU tree, group structure, Group Policy links, sites and subnets, and certificate templates. Read-only discovery captures that baseline first. Only then does the team ask for the specific, limited access needed to see the rest (Chapter 08).

Starting this way has three benefits. It changes nothing in the directory. It applies least privilege, NIST SP 800-53 control AC-6, to the assessment team itself. And the request for elevated access is built from evidence of what is missing, not from a general request for Domain Admin.

What a standard authenticated account can read in Active Directory, what depends on how the forest was configured, and what it can’t read without delegation.

## What a standard account can read

Read access in Active Directory doesn’t come from one setting. It is the sum of several default grants, and a careful assessment knows which grant it is relying on.

- Authenticated Users receives a limited set of property sets on user objects by default: general, public, personal and web information, plus the right to read permissions.

- Pre–Windows 2000 Compatible Access receives list, read-all-properties and read-permissions rights on users, groups and InetOrgPerson objects. Its default membership depends on a choice made when the domain was created. In the Windows 2000-and-later permissions mode it contains Authenticated Users; in the pre-Windows 2000 compatible mode it contains Everyone and Anonymous.

Taken together, these mean that in most domains a standard account can read most attributes of users and groups. That is broader than many teams expect. The exact result depends on the domain’s history: whether that group’s membership was ever trimmed, and whether OUs were hardened. So the assessment’s first step is a pre-flight that tests what this account can actually read in this forest, rather than assuming the defaults. Every later export records which access it relied on.

| Area | Typical read-only result | What it contributes to the plan |
| --- | --- | --- |
| Forest and domain topology, domain controllers, sites, subnets, site links | Readable | Scope, functional levels, and the shape of replication |
| OU hierarchy and Group Policy links | Readable | The structure that attribute-driven targeting replaces (Chapters 03 and 05) |
| Group Policy objects and settings reports | Usually readable, unless security filtering restricts a GPO | The GPO-to-Intune inventory |
| Users, groups, computers and service principal names | Readable | The identity inventory and service account discovery (Chapter 09) |
| Certificate templates and enrollment services, in the configuration partition | Readable | The AD CS dependency surface (Chapter 04) |
| AD-integrated DNS zones | Often readable; test it | The DNS dependency surface (Chapter 04) |
| Replication health and DNS server settings such as scavenging | Needs a right or server access | A delegation item or an administrator-provided export |

## Where the default read boundary sits

The assessment report should never claim coverage it doesn’t have. Four mechanisms set the default boundary. Each needs to be described accurately, because several are commonly misstated.

### Protected accounts and groups

The AdminSDHolder object in each domain’s System container holds template permissions for the protected accounts and groups: Domain Admins, Enterprise Admins, Schema Admins, Administrators, the operator groups, krbtgt and others. A process called SDProp runs every 60 minutes by default on the domain controller that holds the PDC emulator role. It resets the permissions on those protected accounts and groups to match the template, and inheritance is disabled on them.

SDProp acts on current members of protected groups. An account removed from a protected group keeps adminCount set to 1 unless someone clears it. SDProp no longer updates its permissions, but it still doesn’t inherit permissions from its OU. For discovery, this means adminCount=1 lists accounts that are or were privileged. That makes it a useful clean-up list, but it is not the current privileged population. Membership of the protected groups is.

### Confidential attributes

Since Windows Server 2003 SP1, setting bit 7 (value 128) of an attribute’s searchFlags marks the attribute as confidential. Reading it then needs the CONTROL_ACCESS right in addition to read-property, and by default only administrators hold that right on all objects. Base-schema attributes can’t be marked confidential. Local administrator passwords that LAPS stores in Active Directory are an example: they sit in protected attributes that only delegated readers can see.

Read-only discovery can therefore show where a capability is deployed without seeing the secret. With Windows LAPS, for example, the presence and age of the expiration attribute (msLAPS-PasswordExpirationTime) shows coverage without anyone reading the password. The legacy Microsoft LAPS product, which uses the ms-Mcs-AdmPwd* attributes, is deprecated as of Windows 11 23H2. Newer Windows versions block its installer, and Windows LAPS is its replacement. A forest still on legacy LAPS has a finding before the assessment even reaches identity.

### Secrets

Password hashes are never returned to a directory read. They leave a domain controller only through directory replication, and pulling them that way needs the “Replicating Directory Changes” and “Replicating Directory Changes All” rights. “Replicating Directory Changes All” is the control access right that allows replication of secret domain data. Microsoft Entra Connect’s password hash sync account holds both rights for exactly this reason.

For discovery this boundary cuts both ways. The assessment never needs these rights, and the program never requests them for an assessment account. But which accounts already hold them is one of the most important things a later, privileged assessment checks. Any holder that is not a domain controller or the sync service account is a finding (Chapter 08).

### Restricted containers and policy objects

By default, only the System account and members of the Administrators group can view the hidden Deleted Objects container. Microsoft documents granting read (list children and read property) to a named non-administrator if needed; the procedure starts with a Domain Admin taking ownership of the container. Restoring a deleted object is a separate and more sensitive right (“Reanimate Tombstone”), which an assessment never needs. In forests created with Windows Server 2003 SP1 or later, the default tombstone lifetime is 180 days.

Fine-grained password policies are managed by Domain Admins by default. Treat their settings and the groups they apply to as a delegation or administrator-export item. Record them as “not seen” rather than inferring them from the default domain policy.

## Recording what read-only discovery couldn’t see

Each gap is recorded with four facts: what is missing, the narrowest right or export that would close it, why the migration plan needs it, and whether there’s a read-only substitute. A program-standard gap list starts with the rows below and is then edited to match the pre-flight’s actual results.

| Gap | Narrowest way to close it | Why the plan needs it | Read-only substitute |
| --- | --- | --- | --- |
| Replication health and convergence | An administrator-run replication summary, or SIEM data | Cutover sequencing; domain controllers that fail to converge | None reliable |
| Domain controller event logs | A log export or SIEM read access | Authentication patterns, including NTLM use (Chapter 03) | None |
| DNS server settings (aging, scavenging, forwarders) | DNS administrator export | Stale records that block the DNS adapter (Chapter 04) | Zone object reads cover records, not server settings |
| Issued-certificate database | CA administrator export | Which certificates must be reissued from a new PKI | Template permissions and enrollment services |
| Deleted Objects | Read on the container for one named account | Audit trail of recent deletions | Recycle Bin status only |
| Fine-grained password policies | Domain Admin export | Password policy mapping for Entra ID | None |
| Confidential attributes (LAPS, BitLocker recovery) | Not requested; coverage only | Deployment coverage, not secrets | Expiration and child-object presence |

The source guide quoted a read-only coverage figure of about 87 percent. Its own calculation averages to about 94 percent, because it leaves out the zero-coverage rows. Neither figure is a measurement. The program reports the coverage the pre-flight actually measured in this forest, and nothing else.

## The delegation request

The gap list becomes a short written request to the directory team or security review board. The request is what makes the program’s least-privilege position credible, so it follows fixed rules.

- Read only. No write, create, delete or permission-change rights. Rights that expose secrets are never requested: replication of secret data, confidential-attribute reads, and tombstone reanimation.

- Specific. Each line names the right, the exact object path and the business reason, taken from the gap list. “Domain Admin for the assessment” is not an acceptable line.

- Time-bound. Each delegation expires at the end of the assessment window, and the account’s accountExpires is set to match.

- One named, dedicated account. A standard user with no existing elevated memberships. Its activity can then be attributed and told apart from normal use.

- Preferably an export. Where the directory team can run a report and hand over the output (replication summary, DNS server settings, CA database export), that is better than granting a right at all.

The directory team implements the delegations with its own change process. The program doesn’t hand over commands for others to run with their privileges.

## Running the assessment safely

Read-only queries change nothing, but they aren’t invisible, and the output is sensitive.

- Tell the security operations team first. Broad LDAP enumeration looks like reconnaissance, and monitoring tools are built to flag it. Microsoft Defender for Identity, for example, raises discovery alerts for Active Directory enumeration and for unusual LDAP queries against sensitive attributes. Give the security operations team the window, the account and the expected query pattern so they can recognize the activity without switching detection off.

- Be gentle with domain controllers. Page large queries, run bulk enumeration off-peak, and direct queries to a domain controller designated for administrative load.

- Protect the output as sensitive. An assessment output set is a map of the estate. It lists privileged group membership, service accounts and their service principal names, certificate template permissions, and the delegation model. Store it only on encrypted volumes, on a dedicated assessment workstation, and never on a general-purpose endpoint. Handle it under the agency’s data classification policy.

- Make it tamper-evident. Record a SHA-256 hash of every output file in an assessment manifest. Commit the set to the program’s versioned repository under a dated path, so later snapshots can be compared to it for drift.

- Close it down. When the assessment ends, disable the account, confirm that every delegation has expired, and brief the engagement authority.

Read-only discovery from pre-flight to the targeted delegation request.

## Checklist

Before starting

- Scope documented and approved by the engagement authority.

- Dedicated assessment account provisioned: standard user, no elevated memberships, expiry set to the end of the window.

- Dedicated assessment workstation with the Active Directory and Group Policy management tools installed.

- Output location on an encrypted volume.

- Security operations notified of the window, the account and the expected query pattern.

After finishing

- Manifest generated with a hash for every file, and the files verified against it.

- Output committed to the program repository.

- Gap list and delegation request prepared from the measured coverage.

- Assessment account disabled.

- Summary briefed to the engagement authority.

The assessment tooling the program used for this stage is kept with the source guide in the repository archive. It needs a technical review before reuse: the review behind this chapter found several defects. Chapter 08 covers the privileged assessment that fills the gaps.

## Continue the book

← Previous: Chapter 06 — Who Owns the Migration · Book index · Next: Chapter 08 — Assessing the Forest →

# Chapter 08 — Assessing the Forest

A migration plan is only as good as the inventory under it, and the inventory is only as good as the evidence that proves when, how and by whom it was taken.

## In this chapter

The privileged half of discovery: what the full forest assessment collects, the rights it needs, and how to keep those rights narrow. It walks the eight collection areas (topology, OUs, Group Policy, DNS, AD CS, computers, users and groups, trusts), then the pipeline that turns each run into a hashed, versioned record in a Git repository, with findings raised as issues. It closes with security handling, troubleshooting, the output schema and a quick reference card. The complete module is in Appendix B.

Chapter 07 ends with a gap analysis: the list of things a read-only account couldn’t see. This chapter fills those gaps. The full assessment reads the configuration partition, ACLs on OUs, every GPO’s settings, DNS server configuration, the PKI containers and certificate authority (CA) settings, and the delegation flags on every account. Some of that needs rights beyond default read access, so the assessment is run deliberately, by a named account, on a schedule, and every run leaves the same evidence behind.

The program’s position is that the assessment is an evidence-producing process, not a set of scripts. Each run does three things:

- It collects a fixed set of artifacts into a fixed directory layout, so two runs can be compared file by file.

- It writes a manifest with a SHA-256 hash of every file, so anyone can prove later that an artifact wasn’t changed.

- It commits the run to the program’s Git repository (a self-hosted Gitea instance in the reference design), so the history of the forest is the history of the repository.

The downstream planning documents in this book and its companions read those artifacts, not someone’s memory of the forest.

## What the assessment covers

| Area | What is captured | Main output |
| --- | --- | --- |
| Forest topology | Domains, functional levels, sites, site links, subnets, global catalogs, the five operations master role holders | ForestTopology.json |
| Domain controllers | Host name, site, address, OS version, global catalog and read-only flags, roles held | DomainControllers.json |
| OU hierarchy | The full tree with object counts, GPO links, inheritance blocking and non-inherited ACEs | OUHierarchy.json, OUDelegations.json |
| Group Policy | Every GPO, its XML and HTML report, links, permissions, a native backup, and the unlinked, empty and overlapping sets | GPOInventory.json, GPOSettings\ |
| DNS | Zones, partitions, forwarders, stub zones, DNSSEC, scavenging, stale records, DC locator SRV records | DNSInventory.json |
| AD CS | Enterprise CAs, templates, CDP and AIA locations, and template and CA settings that match known escalation patterns | PKIInventory.json, PKISecurityReport.json |
| Computers | Every computer object, OS classification, staleness, Kerberos delegation | ComputerInventory.json, DelegationReport.csv |
| Users and groups | Privileged membership, AdminSDHolder-protected accounts, service accounts, empty and circular groups | UserInventory.json, GroupInventory.json |
| Trusts | Direction, type, transitivity, SID filtering, selective authentication, verification status | TrustMap.json |

Out of scope here: Microsoft Entra Connect configuration (Chapter 09), the mapping of GPO settings to Intune policy (the workbook’s GPO sunset program), and Azure services. The assessment runs against on-premises Active Directory and writes to an on-premises repository.

The topology discovery model: what the forest, each domain and the sites configuration contribute to the topology record.

## Prerequisites

## Illustrative code

The PowerShell in this chapter is illustrative. It hasn’t been tested against a production forest. Review it, and run it first in a test forest with the narrow rights described below. Complete functions are in Appendix B.

### Platform and modules

The assessment host is a domain-joined Windows Server 2025 or Windows 11 machine with the Remote Server Administration Tools (RSAT). Both report OS build 26100 or later (Windows 11 version 25H2 reports 26200), which is what the prerequisite check tests for. On Windows client, RSAT tools are Features on Demand; on Windows Server they are features installed with Install-WindowsFeature.

| Module or tool | Used for | Windows client (Feature on Demand) | Windows Server |
| --- | --- | --- | --- |
| ActiveDirectory | Forest, domain, object and trust queries | Rsat.ActiveDirectory.DS-LDS.Tools~~~~0.0.1.0 | RSAT-AD-PowerShell |
| GroupPolicy | GPO inventory, reports, links, permissions, backup | Rsat.GroupPolicy.Management.Tools~~~~0.0.1.0 | GPMC |
| DnsServer | Zone, record, DNSSEC and scavenging queries | Rsat.Dns.Tools~~~~0.0.1.0 | RSAT-DNS-Server |
| AD CS tools | CA and template snap-ins, certutil against remote CAs | Rsat.CertificateServices.Tools~~~~0.0.1.0 | AD CS management tools |
| PSPKI (optional) | Convenience cmdlets for CAs and templates | Install-Module PSPKI -Scope CurrentUser | Same |

The client capability names are as Microsoft publishes them. On Windows Server, run Get-WindowsFeature -Name RSAT* and confirm the exact feature names before scripting the install; Microsoft’s guidance shows that discovery step and the RSAT-AD-PowerShell name.

Two corrections to the source design. First, the ADCSAdministration module, which the source listed as required, isn’t used by any assessment function; it manages a local CA role and isn’t needed on the assessment host. Second, PSPKI is now optional. Its publisher says it no longer actively supports or updates the module, although version 4.4.1 was still published to the PowerShell Gallery in June 2026. The collectors in this chapter read AD CS configuration directly from the directory and from certutil, and use PSPKI only where it’s installed and approved.

### Rights

Most of the forest is readable by any authenticated user. The parts that aren’t are the reason this chapter exists.

| Collector | Minimum rights | Notes |
| --- | --- | --- |
| Get-FMPForestTopology | Authenticated user | Forest, domain, site and DC metadata are readable by default |
| Get-FMPOUHierarchy | Read on OUs; read permissions on their security descriptors | Some ACLs need explicit read-permissions rights |
| Get-FMPGPOInventory | Read on GPOs and SYSVOL; GPO backup rights | Backup needs explicit delegation |
| Get-FMPDNSAssessment | Read permission on each DNS server | Delegate read on the server; don’t use DnsAdmins (see below) |
| Get-FMPPKIAssessment | Read on the Public Key Services containers; read on each CA | certutil -getreg against a CA can need CA-level rights |
| Get-FMPComputerInventory | Authenticated user | Delegation attributes are readable by default |
| Get-FMPUserInventory, Get-FMPGroupInventory | Authenticated user | Recursive expansion is slow in large forests |
| Get-FMPTrustMap | Authenticated user to enumerate; Domain Admins to verify | netdom verification needs administrative credentials |

The source guide recommended adding the assessment account to DnsAdmins for DNS read access. Don’t. Microsoft treats DnsAdmins as a privileged group, because its members have administrative control over the DNS Server service, and Defender for Identity flags non-privileged members as a risk. Grant read permission on the DNS server object to a dedicated group instead. The same reasoning applies to the source’s “Domain Admin for initial discovery.” The program’s position is that no assessment run uses a standing Domain Admins account; trust verification is the only step that needs those rights, and it runs separately under a just-in-time elevation.

Trust verification needs those credentials because netdom requires domain administrator credentials for accurate verification.

### Output layout

Every run writes to the same tree, rooted at the domain’s DNS name, so runs compare file by file:

D:\FMP\Assessment\<domain>\
├── AssessmentManifest.json
├── Forest\     ForestTopology.json, ForestInfo.json, Sites.json, SiteLinks.json, Subnets.json, FSMORoles.json
├── Domains\    AllDomains.json, <domain>.json, DomainControllers.json
├── OUs\        OUHierarchy.json, OUFlatList.csv, OUFlatExport.json, OUGPOLinks.json, OUDelegations.json, OUTreeVisual.txt
├── GPOs\       GPOInventory.json, GPOLinks.json, GPOEmpty.json, GPOConflicts.json, GPOPermissions.json,
│               GPOSettingsDecomposed.json
│   ├── GPOSettings\   <GUID>.xml, <GUID>.html
│   └── GPOBackups\
├── DNS\        DNSInventory.json, DNSHealthReport.json, DNSRecordInventory.json
├── PKI\        PKIInventory.json, PKISecurityReport.json, <CA name>.cer
├── Objects\    ComputerInventory.json, ComputersByOS.csv, StaleComputers.csv, DelegationReport.csv,
│               UserInventory.json, PrivilegedUsers.csv, AdminCountReport.csv, ServiceAccounts.csv,
│               GroupInventory.json, CircularGroups.json
├── Trusts\     TrustMap.json
└── ServiceAccounts\   MSAInventory.json, gMSAInventory.json

Test-FMPPrerequisites in Appendix B checks the OS build, the modules, forest connectivity and the output root, and returns a pass or fail row for each.

## Forest and domain topology

Topology discovery records the shape of the forest before anything inside it. It answers the questions that size every later decision: how many domains, at what functional level, with how many domain controllers in how many sites, and which controllers hold the operations master roles.

### Operations master roles

Active Directory has five operations master (FSMO) roles. Two are forest-wide and exist once per forest: the schema master and the domain naming master. Three are domain-wide and exist once in every domain: the PDC emulator, the RID master and the infrastructure master. The PDC emulator in the forest root domain is also the authoritative time source for the forest. A three-domain forest therefore has eleven role holders to record, not five.

Get-ADForest returns the two forest-wide holders and Get-ADDomain returns the three domain-wide holders. Get-ADDomainController also returns an OperationMasterRoles property for each controller, which is the simpler way to attribute roles to controllers.

$forest = Get-ADForest
foreach ($domainDns in $forest.Domains) {
    Get-ADDomainController -Filter * -Server $domainDns |
        Select-Object HostName, Domain, Site, IPv4Address,
            OperatingSystem, IsGlobalCatalog, IsReadOnly,
            @{ N = 'Roles'; E = { $_.OperationMasterRoles -join ', ' } }
}

### Functional levels

Record the forest mode and every domain mode. The values tell you which domain controller operating systems the forest can accept and which features are available. The ActiveDirectory module’s ADForestMode values now run up to Windows2025Forest. The Windows Server 2025 functional level (DomainLevel and ForestLevel 10 in answer files) is the first new level since Windows Server 2016; Windows Server 2019 and 2022 didn’t add one. It’s required for the optional 32k database page size feature, and only Windows Server 2025 domain controllers can run at it.

The assessment should flag two conditions:

- A functional level below Windows Server 2016. A Windows Server 2025 domain controller can join only a domain at the Windows Server 2016 functional level or higher, so a lower level blocks the domain controller refresh before any cloud work starts.

- Mixed domain levels across the forest. If every domain controller in the forest runs Windows Server 2025, raising the forest level to Windows Server 2025 raises every domain with it.

### Sites, site links and subnets

Get-ADReplicationSite, Get-ADReplicationSiteLink and Get-ADReplicationSubnet capture the replication topology and the subnet-to-site map. The subnet map matters beyond replication: domain controller location for clients depends on it, and an unmapped subnet sends clients to arbitrary domain controllers. Record site link cost and replication interval; they explain authentication latency at remote sites better than any network diagram.

Get-FMPForestTopology combines all of this into one ForestTopology.json with a timestamp.

## OU hierarchy and delegation

Chapter 05 explains why the OU tree is the delegation model in Active Directory, and why Entra ID has none. The assessment’s job is to capture what the tree actually encodes, so that the attribute design in Chapter 09 reproduces intent rather than structure.

Extract four things for every OU:

- Placement and size. Distinguished name, depth, description, ManagedBy, protection from accidental deletion, and direct counts of users, computers and groups. A recursive builder produces a nested OUHierarchy.json; a flat CSV goes to spreadsheet review.

- GPO links. Linked GPOs with link order, enforcement and enabled state, and whether the OU blocks inheritance.

- Delegated permissions. The non-inherited access control entries on the OU, excluding well-known built-in principals. These are the delegations someone made by hand, and they become the administrative unit and role assignment candidates in Chapter 05’s matrix.

- A text rendering of the tree with object and GPO counts at each node, for human review.

For GPO links, prefer Get-GPInheritance to parsing the raw attribute. It returns the GPOs linked directly to a domain or OU, the GPOs that actually apply in precedence order, and whether inheritance is blocked. If you do parse gPLink, each link is a GPO path plus a linkOptions bitmask: 0x1 means the link is disabled and 0x2 means it’s enforced. Block inheritance is a property of the container, stored in its gPOptions attribute; an enforced link still applies through a block. Match GUIDs case-insensitively, because the cn= and CN= spellings both occur.

Get-ADOrganizationalUnit -Filter * | ForEach-Object {
    $som = Get-GPInheritance -Target $_.DistinguishedName
    [pscustomobject]@{
        OU                 = $_.DistinguishedName
        InheritanceBlocked = $som.GpoInheritanceBlocked
        Links              = $som.GpoLinks |
            Select-Object DisplayName, GpoId, Enabled, Enforced, Order
    }
}

OU delegation analysis reads ACLs through the AD: drive, which the ActiveDirectory module provides. Keep only entries where IsInherited is false, and drop NT AUTHORITY, BUILTIN and well-known SIDs. What remains is usually short, and it’s the most valuable list in the OU export.

## Group Policy inventory and analysis

The GPO inventory is the largest and most consequential artifact for modernization. Every live setting either moves to Intune, moves somewhere else, or is retired, and nobody can decide which without the inventory.

The GPO analysis flow: inventory, reports and links feed three classifications, and only live settings go on to Intune analysis.

### What to collect

| Step | Cmdlet | Output |
| --- | --- | --- |
| Enumerate | Get-GPO -All | Name, GUID, GpoStatus, created and modified times, owner, WMI filter |
| Report | Get-GPOReport -Guid <id> -ReportType Xml and Html | One XML and one HTML file per GPO |
| Links | Get-GPInheritance per domain and OU, plus site links | GPOLinks.json with order, enforced and enabled |
| Permissions | Get-GPPermission -Guid <id> -All | Who can edit, apply and read each GPO |
| Backup | Backup-GPO -All -Path <folder> | A native backup for rollback |

All five cmdlets are in the GroupPolicy module. Get-GPOReport produces XML or HTML, and its report includes links, security filtering, WMI filtering, delegation and the computer and user configuration of the GPO. Get-GPPermission -All returns the permission level of every principal that has permissions on the GPO.

The source link analysis searched only OUs and the domain root. GPOs can also be linked to sites, and a site-linked GPO looks unlinked to an OU-only search. Include the site objects in the configuration partition, or the “unlinked” list will contain GPOs that are in use.

### Classify before you migrate

Decompose each XML report by configuration area: security settings, administrative templates, preferences, scripts, software installation and folder redirection, separately for the computer and user halves. Then sort GPOs into three groups:

- Unlinked or empty. No links anywhere, or no settings in either half. These are retirement candidates. An empty GPO is one whose report has no ExtensionData under either Computer or User.

- Overlapping. The same setting configured in more than one GPO. Find these before migration, because Intune’s migration step refuses conflicting values and asks you to pick one.

- Live. Linked, enabled, non-empty settings that need a decision.

Intune’s Group Policy analytics imports GPOs as XML reports, shows which settings have an MDM equivalent, and can build a Settings Catalog policy from the supported settings. Each imported file must be under 4 MB with proper Unicode encoding. The <GUID>.xml reports from this collector are the input; check their sizes in the manifest before importing.

The full functions (Get-FMPGPOInventory, Export-FMPGPOSettings, Find-GPOConflicts) are in Appendix B. The handoff to Intune policy design belongs to the workbook’s GPO sunset program.

## DNS infrastructure

Active Directory runs on DNS, and many of the hidden dependencies in Chapter 04 are DNS records nobody remembers creating. Query every domain controller that runs DNS, not only the global catalogs as the source did; the two sets usually overlap, but they aren’t the same thing.

| Check | Cmdlet | What to look for |
| --- | --- | --- |
| Zones | Get-DnsServerZone | Type (primary, secondary, stub, forwarder), AD integration and partition (ForestDnsZones, DomainDnsZones, domain), signed state, dynamic update mode |
| Records | Get-DnsServerResourceRecord | Count by type per zone; records with old timestamps |
| Forwarders | Get-DnsServerForwarder, forwarder zones | Where unresolved names go, and conditional forwarders to partners |
| DNSSEC | Get-DnsServerDnsSecZoneSetting | Denial-of-existence mode, key master, DS record algorithms |
| Scavenging | Get-DnsServerScavenging | Whether scavenging is on, and its intervals |
| Locator records | Resolve-DnsName -Type SRV | _ldap._tcp, _kerberos._tcp, _gc._tcp, _kpasswd._tcp for each domain |

Get-DnsServerDnsSecZoneSetting returns, among other fields, DenialOfExistence, IsKeyMasterServer, KeyMasterServer and DSRecordGenerationAlgorithm. Get-DnsServerScavenging returns the server’s aging and scavenging settings.

Read stale-record results carefully. A record with a zero or empty timestamp is static and is never scavenged; only dynamically registered records age. The source’s 90-day threshold is a review trigger, not a deletion rule.

One more correction: the source used PowerShell 7’s ?? operator to pick a record’s data field, but its module declares PowerShell 5.1. Appendix B replaces it with an explicit switch on record type. The DNS design that consumes this inventory is in the workbook’s Book 08 — DNS, DHCP & IPAM.

## Certificate Services (AD CS)

AD CS matters twice in a migration. It issues the certificates that devices, domain controllers and smart cards depend on, and its misconfigurations are among the most direct privilege-escalation paths in an Active Directory forest.

### Discovery

Enterprise CAs publish themselves in the directory, so discovery doesn’t need a tool on the CA. Under CN=Public Key Services,CN=Services in the configuration partition:

- Enrollment Services holds a pKIEnrollmentService object for each enterprise CA, recording which certificate types it can issue; its permissions control who can enroll.

- Certificate Templates holds the templates enterprise CAs issue from.

- AIA, CDP, Certification Authorities and NTAuthCertificates hold CA certificates, CRLs, the forest root trust store and the CAs trusted for smart card and domain controller authentication.

certutil -ADCA lists the CAs in the directory, -CAInfo and -ping query a CA, and -getreg policy\EditFlags reads the policy module flags. The source used certutil -config - -ping; -config - asks for a CA interactively, which a scheduled run can’t answer. Pass -config <host>\<CA name> instead.

The source also called three PSPKI cmdlets that don’t exist under those names. The CRL and AIA cmdlets are Get-CRLDistributionPoint and Get-AuthorityInformationAccess, and there’s no Get-CACertificate. Appendix B reads the CA certificate with certutil -ca.cert instead.

### Escalation patterns

The ESC naming for AD CS escalation patterns comes from SpecterOps’ 2021 research, which defined ESC1 through ESC8; SpecterOps’ own tooling now covers patterns through ESC16. Microsoft Defender for Identity now assesses several of them in Secure Score. The assessment checks the ones it can see from the directory and the CA registry:

| Pattern | Condition | Source of truth |
| --- | --- | --- |
| ESC1 | Template lets the enrollee supply the subject, allows an authentication EKU, needs no manager approval or authorized signature, and is enrollable by broad groups | msPKI-Certificate-Name-Flag, EKU attributes, msPKI-Enrollment-Flag, msPKI-RA-Signature, template ACL |
| ESC2 | Template has the Any Purpose EKU or no EKU | EKU attributes |
| ESC4 | Template ACL lets broad groups write to it | Template ACL |
| ESC6 | CA has EDITF_ATTRIBUTESUBJECTALTNAME2 set, so any requester can add a SAN | certutil -getreg policy\EditFlags |
| ESC7 | Broad groups hold Manage CA or Manage Certificates on the CA | CA ACL |

Defender for Identity’s definitions are the reference. ESC1 is a template with Supply in the request on, an authentication EKU such as Client Authentication, Smart Card Logon, PKINIT client authentication or Any Purpose, and enrollment open to unprivileged groups, unless manager approval or authorized signatures mitigate it. ESC6 is the CA flag that lets every requester specify the SAN for every template; Microsoft’s remediation is certutil -setreg policy\EditFlags -EDITF_ATTRIBUTESUBJECTALTNAME2 and a service restart. ESC4 is a template ACL that gives a broad group rights such as Full Control or Write DACL.

The source’s ESC1 check tested for the Digital Signature key usage. That’s the wrong field: almost every template has it. The check has to test the extended key usage for an authentication purpose. In the directory, the enrollee-supplies-subject flag is 0x1 in the name flags and the pend-all-requests (manager approval) flag is 0x2 in the enrollment flags. The authentication EKUs are Client Authentication 1.3.6.1.5.5.7.3.2, Smart Card Logon 1.3.6.1.4.1.311.20.2.2, PKINIT client authentication 1.3.6.1.5.2.3.4, and Any Purpose 2.5.29.37.0.

$config = (Get-ADRootDSE).configurationNamingContext
$authEku = '1.3.6.1.5.5.7.3.2','1.3.6.1.4.1.311.20.2.2','1.3.6.1.5.2.3.4','2.5.29.37.0'
Get-ADObject -SearchBase "CN=Certificate Templates,CN=Public Key Services,CN=Services,$config" `
    -LDAPFilter '(objectClass=pKICertificateTemplate)' `
    -Properties displayName, msPKI-Certificate-Name-Flag, msPKI-Enrollment-Flag,
                msPKI-RA-Signature, pKIExtendedKeyUsage |
    Where-Object {
        ($_.'msPKI-Certificate-Name-Flag' -band 0x1) -and
        -not ($_.'msPKI-Enrollment-Flag' -band 0x2) -and
        ([int]$_.'msPKI-RA-Signature' -eq 0) -and
        ((-not $_.pKIExtendedKeyUsage) -or
         ($_.pKIExtendedKeyUsage | Where-Object { $_ -in $authEku }))
    } |
    Select-Object displayName

A template that passes this filter is an ESC1 candidate only if it’s also published by a CA and enrollable by a broad group; Appendix B checks both before raising a finding. Report only; don’t remediate from the assessment. Remediation belongs to the PKI owner, through Book 07 — PKI & Certificates.

For the migration itself, the PKI inventory tells you whether user certificates can move to Microsoft Entra certificate-based authentication, which authenticates X.509 certificates against your PKI directly in Entra ID without federated AD FS.

## Computer objects

Every computer object is a migration decision: Entra join, hybrid join, Azure Arc, retirement, or keep in Active Directory. The computer inventory carries name, DNS name, OS and version, enabled state, last logon, password last set, SPNs, encryption types and the delegation attributes.

### Staleness

LastLogonDate is a converted lastLogonTimestamp, which a domain controller updates only when the stored value is older than the current time minus msDS-LogonTimeSyncInterval; the default granularity means it can lag the true last logon by up to two weeks. It’s accurate enough for a 90-day staleness test and not for a 7-day one. Use it together with PasswordLastSet, which a working domain member refreshes on its own, and treat a computer as stale only when both are old. Defender for Identity uses the same 90-day threshold for stale accounts.

### Kerberos delegation

Classify delegation by what’s actually set, in this order:

| Attributes | Classification |
| --- | --- |
| TrustedForDelegation is true | Unconstrained |
| msDS-AllowedToDelegateTo set and TrustedToAuthForDelegation true | Constrained, with protocol transition |
| msDS-AllowedToDelegateTo set | Constrained, Kerberos only |
| PrincipalsAllowedToDelegateToAccount set (resource side) | Resource-based constrained |

The source had two errors here. It labeled any account with TrustedToAuthForDelegation “protocol transition” even without a target list, and it missed resource-based constrained delegation entirely. Resource-based delegation is configured on the resource, in msDS-AllowedToActOnBehalfOfOtherIdentity, which the ActiveDirectory module exposes as PrincipalsAllowedToDelegateToAccount.

Unconstrained delegation lets a service impersonate any user who authenticates to it, to any service. Microsoft calls it less secure than CredSSP, and Defender for Identity reports it as unsecure Kerberos delegation on non-domain-controller entities. Domain controllers are expected to have it, so exclude them from the finding, as Defender for Identity does; every other unconstrained entry becomes a critical issue.

## Users, groups and service accounts

### Privileged users

Expand the membership of the privileged groups recursively: Domain Admins, Enterprise Admins, Schema Admins, Administrators, Account Operators, Server Operators, Backup Operators and Print Operators. Each of these is in Microsoft’s list of privileged on-premises groups. Record enabled state, last logon and password age for each member.

Then cross-check against AdminSDHolder. Every 60 minutes, the SDProp process on the PDC emulator resets the permissions on protected accounts and groups to match the AdminSDHolder object. When an account leaves a protected group, its adminCount stays at 1 unless someone clears it, and the account keeps inheritance disabled, so delegated OU permissions no longer reach it. The assessment reports those orphaned adminCount=1 accounts. The check has to use recursive membership; a direct MemberOf match, which the source used, misses nested membership and over-reports orphans.

### Service accounts

Service accounts come in four kinds, and the inventory records all of them:

| Kind | How to find it | Migration note |
| --- | --- | --- |
| User account with SPNs | Get-ADUser where ServicePrincipalName is set | Kerberoastable; highest priority to replace |
| Standalone MSA | Get-ADServiceAccount | Single computer; password managed by the computer |
| Group MSA (gMSA) | Get-ADServiceAccount | Multiple servers; password managed by the domain |
| Delegated MSA (dMSA) | Get-ADServiceAccount | Windows Server 2025 domains only |

A dMSA is the Windows Server 2025 account type that replaces a traditional service account with a machine-bound managed identity and disables the original account’s password, which defends against Kerberoasting. gMSAs remain the default for services that run on more than one server. Record the raw ObjectClass that Get-ADServiceAccount returns rather than guessing the type from the name.

The source mapped service accounts to “gMSA or managed identities.” Managed identities are an Azure resource feature and outside this program’s boundary. For workloads that stay on premises the target is a gMSA or dMSA; for workloads that move to cloud services, the target is a Microsoft Entra workload identity, which Chapter 09 covers.

### Groups

The group inventory records category (security or distribution), scope (domain local, global, universal), ManagedBy, adminCount and direct member count, and flags empty groups and circular nesting. Two limits matter in large forests:

- A domain controller returns at most 5,000 values of a multivalued attribute such as member in one LDAP response, so very large group counts need ranged retrieval or a recursive member query to be accurate.

- A security principal can be a member of at most 1,015 groups, because of the access token size limit; accounts near that limit will have authentication problems before and after migration.

The group and user inventories feed the identity design in Chapter 09 and the access reviews in Chapter 10.

## Trust relationships

Each trust is a trusted domain object in the System container of its domain, carrying the partner’s DNS name, SID, trust type and transitivity. Get-ADTrust -Filter * returns them all. Decode trustAttributes from the published bit values rather than from memory:

| Bit | Name | Meaning |
| --- | --- | --- |
| 0x1 | Non-transitive | The trust can’t be used transitively |
| 0x2 | Uplevel only | Only Windows 2000 and later clients can use it |
| 0x4 | Quarantined domain | SID filtering applies |
| 0x8 | Forest transitive | A cross-forest trust between forest root domains |
| 0x10 | Cross-organization | The partner isn’t part of the organization |
| 0x20 | Within forest | The partner is in the same forest |
| 0x40 | Treat as external | A forest trust filtered as if it were external |

The values come from the Active Directory technical specification, which also defines later bits for AES keys, RC4, PIM trusts and TGT delegation control. Record the raw value as well as the decoded list, so that bits added later aren’t lost.

### Direction and posture

Trust direction is relative, and access flows the opposite way to trust: members of the trusted domain can reach resources in the trusting domain. Seen from one domain, an inbound (incoming) trust lets this domain’s users reach resources in the partner, and an outbound (outgoing) trust lets the partner’s users reach resources here. The source’s direction analysis had this reversed: it said an inbound trust lets users of the partner authenticate here. For each trust, the assessment states plainly which side’s users can reach which side’s resources, then rates the posture: selective authentication on is hardened, SID filtering on is standard, neither is a finding.

### Verification

The source’s verification called Test-ADTrust, which isn’t a cmdlet in the ActiveDirectory module. Use netdom trust <trusting domain> /domain:<trusted domain> /verify, which verifies the secure channel secrets for the trust, or netdom query trust /verify to check every outbound trust. Both need administrative credentials for accurate results, so verification runs as its own elevated step, not inside the scheduled collection.

Forest trusts often record partner relationships that will need a cloud equivalent. In Entra ID, the partner relationship is governed by cross-tenant access settings, which control inbound and outbound B2B collaboration and B2B direct connect with other Microsoft Entra organizations. A forest trust doesn’t convert into a cross-tenant setting; it identifies a partner whose access has to be redesigned.

## The assessment pipeline

The assessment pipeline: one orchestrator, eight collectors, a hashed manifest, and a versioned repository that raises issues and starts planning.

### Orchestration

Invoke-FMPADAssessment runs the collectors in a fixed order: topology, OUs, GPOs, DNS, AD CS, computers, users and groups, trusts. It then writes AssessmentManifest.json:

| Field | Content |
| --- | --- |
| AssessmentId | A new GUID for the run |
| Domain, ComputerName, ExecutedBy | Where, on what host, and as whom it ran |
| StartTime, EndTime, DurationMinutes | The execution window, in ISO 8601 |
| StaleThresholdDays | The threshold the run used |
| FileCount, Files | Every output file with relative path, size, last write time and SHA-256 hash |

The manifest is what makes a run evidence. Anyone holding the repository can recompute the hashes and show that no artifact changed after collection.

### From artifact to plan

| Artifact | Consumed by | Use |
| --- | --- | --- |
| GPOInventory.json, GPOSettingsDecomposed.json, <GUID>.xml | GPO-to-Intune migration plan | Group Policy analytics import and Settings Catalog design |
| ComputerInventory.json, ComputersByOS.csv | Device modernization plan | Entra join, hybrid join, Arc or retire, per device |
| DNSInventory.json | DNS modernization plan | Zones and forwarders mapped to the target design |
| PKIInventory.json, PKISecurityReport.json | PKI modernization plan | CBA readiness and ESC remediation |
| OUHierarchy.json, OUDelegations.json | Attribute and delegation design | OU targeting converted to attributes, dynamic groups and administrative units |
| TrustMap.json | Partner access plan | Partners whose access needs a B2B or cross-tenant design |
| UserInventory.json, GroupInventory.json, PrivilegedUsers.csv | Identity design | Group structure, PIM role assignments, access review scopes |
| ServiceAccounts.csv | Service account plan | gMSA or dMSA on premises; workload identities in the cloud |

### Drift

Run the assessment on a schedule (the reference design is weekly) and compare each run with the last. Compare-FMPAssessments compares the key JSON files by hash and reports which changed. A changed hash says that something changed; to say what, compare the parsed objects by a stable key (GUID or SID), which Appendix B shows for the computer, user, group and GPO inventories. Exclude timestamps from the comparison, or every file will look changed on every run.

Schedule the run under a gMSA so no password is stored. Group MSAs support Task Scheduler tasks, and Microsoft’s own on-demand assessments can run their scheduled task as an sMSA or gMSA; Microsoft recommends caching the account on the collection host with Install-ADServiceAccount first, to prove the host can retrieve its password.

## Git integration for assessment data

The repository is the system of record for assessment history. The reference design uses Gitea’s REST API at /api/v1, authenticated with an API token in an Authorization: token <value> header. Gitea’s API specification marks the older token and access_token query parameters as deprecated, so don’t use them; they also put the secret in URLs and logs.

| Purpose | Endpoint | Notes |
| --- | --- | --- |
| Create a branch per run | POST /repos/{owner}/{repo}/branches | new_branch_name plus old_ref_name; old_branch_name is deprecated |
| Commit a whole run at once | POST /repos/{owner}/{repo}/contents | files is a list of operations (create, update, upload, delete, rename), each with base64 content |
| Create or update one file | POST or PUT /repos/{owner}/{repo}/contents/{filepath} | PUT needs the existing blob sha to update a file |
| Raise a finding | POST /repos/{owner}/{repo}/issues | labels is a list of label IDs, not names |
| Start downstream automation | POST /repos/{owner}/{repo}/hooks | type, config with url and content_type, events, branch_filter |

All of these are from Gitea’s published API specification. Two corrections to the source code follow from it. First, the source created issues with an empty label list and a comment that IDs “would be resolved here”; resolve label names to IDs with GET /repos/{owner}/{repo}/labels first, or the labels are silently dropped. Second, the source committed a run one file per API call, which produces hundreds of commits per run. The multi-file contents endpoint commits the whole run, manifest included, as one commit, which is what makes “one run, one commit” true.

The local-clone alternative (git add, git commit, git push) works as well and is simpler on a host that already has Git. Either way, the commit message names the domain and the run timestamp, and the branch is assessment/<domain>/<timestamp>.

Raise issues automatically for two classes of finding only: critical PKI patterns and unconstrained delegation on non-domain-controller accounts. Everything else goes to the planning documents, not the issue tracker. Webhook secrets are generated once and stored with the receiving automation, not regenerated on each run.

## Security and least privilege

Assessment data is sensitive. It contains the forest’s topology, its privileged account list, its delegation configuration and its PKI weaknesses: a map for an attacker. Treat the output tree and the repository accordingly.

### The assessment account

The program’s design is a group managed service account, svc-fmp-assess$, with delegated read rights and nothing more:

- Read on the domain naming contexts and the configuration partition (default for authenticated users).

- Read-permissions rights on OUs whose ACLs aren’t readable by default.

- Read on GPOs and SYSVOL, and GPO backup rights through Group Policy Management delegation.

- Read on each DNS server, delegated on the server object; not DnsAdmins.

- Read on the Public Key Services containers and each CA.

The source created a user account with a password typed at a prompt, and then scheduled the task under a gMSA of the same name. Use the gMSA throughout. Create it with New-ADServiceAccount -PrincipalsAllowedToRetrieveManagedPassword <host>$, after confirming a KDS root key exists with Get-KdsRootKey. For interactive runs, use Get-Credential; never store a password in a script or a text file.

The source also read the Gitea token from a plain text file. Store it in the Windows credential store or a secrets vault the host can reach, scoped to the one repository, and rotate it.

### Network paths

| Protocol | Port | From the assessment host to | Purpose |
| --- | --- | --- | --- |
| ADWS | TCP 9389 | Domain controllers | All ActiveDirectory module cmdlets |
| LDAP / LDAPS | TCP 389 / 636 | Domain controllers | Direct LDAP queries and certutil -ADCA |
| Global catalog | TCP 3268 / 3269 | Global catalogs | Forest-wide searches |
| Kerberos | TCP/UDP 88 | Domain controllers | Authentication |
| DNS | TCP/UDP 53 | DNS servers | Name resolution and SRV checks |
| SMB | TCP 445 | Domain controllers | SYSVOL reads for GPO reports |
| RPC | TCP 135 plus 49152–65535 | Domain controllers, CAs, DNS servers | GPO, certutil and netdom operations |
| WinRM | TCP 5985 / 5986 | DNS servers, CAs | PowerShell remoting, HTTP and HTTPS |

The source table left out ADWS, which is the port the ActiveDirectory module actually uses: its cmdlets connect to ADWS on 9389, and ADWS queries the directory on their behalf. It also left out SMB. The other ports are as Microsoft lists them for Active Directory and for PowerShell remoting.

### Handling

The program’s design rules for the data:

- Store the output tree on an encrypted volume, and the Gitea data directory likewise.

- Restrict the repository to the assessment team and the plan owners; it’s not a general engineering repository.

- Keep runs for at least 12 months, archive older runs, and delete runs older than 36 months unless a legal hold applies.

- Log every run to the Windows Application log under the source FMPAssessment and to D:\FMP\Logs\Assessment.log.

- Sign the module and run it under an AllSigned or RemoteSigned policy, rather than the source’s -ExecutionPolicy Bypass.

## Troubleshooting

| Symptom | Likely cause | Resolution |
| --- | --- | --- |
| Get-ADForest: unable to find a default server with Active Directory Web Services running | Host can’t reach a DC on TCP 9389, or ADWS is stopped | Test-NetConnection <DC> -Port 9389; start ADWS on the DC; target a DC with -Server |
| The term 'Get-ADForest' is not recognized | ActiveDirectory module not installed | Run Test-FMPPrerequisites; install the RSAT capability or feature |
| Get-GPOReport: access is denied | Account lacks read on the GPO or SYSVOL | Check \\<domain>\SYSVOL access; grant read through GPMC delegation |
| Get-DnsServerZone: the RPC server is unavailable, or WinRM errors | Remote management blocked to the DNS server | Test-WSMan <server>; enable remoting on the server; open the WinRM rule |
| No CA found | No enterprise CA in the forest, or no read on Public Key Services | certutil -ADCA; read CN=Enrollment Services with Get-ADObject |
| Large queries time out or return partial results | Directory limits on page size or value ranges | Scope with -SearchBase, set -ResultPageSize; don’t raise LDAP policy limits |
| Cross-domain failures | Trust not verified, or selective authentication blocks the account | netdom trust ... /verify; check the trust’s attributes; pass -Credential |

Two of the source’s resolutions were unsafe and are removed. Setting TrustedHosts to a domain wildcard tells the WinRM client to send credentials to hosts it hasn’t authenticated; in a domain, Kerberos authentication doesn’t need TrustedHosts at all. Raising LDAP MaxPageSize with ntdsutil changes a forest-wide protection whose default is 1,000 records; Microsoft documents raising it only temporarily, for a specific recovery, and restoring it afterwards.

## Output schema reference

Every JSON file is either a root object with an AssessmentTimestamp and named arrays, or an array of objects. Field-level schemas and examples are in Appendix B.

| File | Root | Primary contents |
| --- | --- | --- |
| ForestTopology.json | Object | Forest, Domains[], DomainControllers[], Sites[], SiteLinks[], Subnets[], FSMORoles[] |
| OUHierarchy.json | Array of nodes | Name, DN, description, linked GPOs, object counts, Children[] |
| GPOInventory.json | Array | Display name, ID, GpoStatus, times, owner, WMI filter |
| DNSInventory.json | Object | DnsServer, Zones[], Scavenging, Forwarders |
| PKIInventory.json | Object | CertificationAuthorities[], CertificateTemplates[] |
| PKISecurityReport.json | Array | Finding, severity, template or CA, description, remediation |
| ComputerInventory.json | Array | Name, DNS name, OS, enabled, last logon, SPNs, delegation |
| UserInventory.json | Array | sAMAccountName, UPN, enabled, last logon, adminCount, MemberOf |
| GroupInventory.json | Array | sAMAccountName, category, scope, direct member count, empty flag |
| TrustMap.json | Object | Domain, TrustCount, Trusts[] |
| AssessmentManifest.json | Object | Run identity and window, Files[] with SHA-256 hashes |

## Quick reference

| Function | Purpose | Main output |
| --- | --- | --- |
| Test-FMPPrerequisites | Check OS, modules, connectivity, output root | Pass or fail table |
| Get-FMPForestTopology | Forest, domains, DCs, sites, roles | ForestTopology.json |
| Get-FMPOUHierarchy | OU tree, links, delegations | OUHierarchy.json, OUFlatList.csv |
| Get-FMPGPOInventory | GPO inventory, reports, links, permissions, backup | GPOInventory.json, XML and HTML |
| Get-FMPDNSAssessment | Zones, forwarders, DNSSEC, scavenging | DNSInventory.json |
| Get-FMPPKIAssessment | CAs, templates, escalation patterns | PKIInventory.json, PKISecurityReport.json |
| Get-FMPComputerInventory | Computers, OS, staleness, delegation | ComputerInventory.json, CSVs |
| Get-FMPUserInventory | Users, privileged accounts, service accounts | UserInventory.json, CSVs |
| Get-FMPGroupInventory | Groups, empty and circular nesting | GroupInventory.json |
| Get-FMPTrustMap | Trusts and posture | TrustMap.json |
| Invoke-FMPADAssessment | Run all collectors and write the manifest | All files plus AssessmentManifest.json |
| Compare-FMPAssessments | Compare two runs | Drift report |
| Push-FMPAssessmentToGitea | Commit a run as one commit on a run branch | API response |
| New-FMPSecurityIssue, Invoke-FMPFindingIssues | Raise issues for critical findings | Issue URLs |

### Run checklist

- Run Test-FMPPrerequisites and resolve every failure.

- Confirm the gMSA is installed on the host and holds only the delegated rights above.

- Import-Module FMPADAssessment.

- Invoke-FMPADAssessment -Domain <domain> -OutputPath D:\FMP\Assessment -StaleThresholdDays 90.

- Open AssessmentManifest.json; check the file count and spot-check hashes.

- Review PKISecurityReport.json and DelegationReport.csv.

- Review StaleComputers.csv and the stale and orphaned user counts.

- Run trust verification as a separate elevated step.

- Commit the run to its branch with Push-FMPAssessmentToGitea.

- Raise issues for critical findings with Invoke-FMPFindingIssues.

- On recurring runs, compare with the previous baseline using Compare-FMPAssessments.

- Archive runs past the retention period.

## Continue the book

← Previous: Chapter 07 — Read-Only Discovery · Book index · Next: Chapter 09 — Building the Entra ID Target →

# Chapter 09 — Building the Entra ID Target

In Active Directory, where an object sits decides what applies to it; in Entra ID, what an object says about itself decides, so the target has to be built from attributes, not copied from containers.

## In this chapter

How each Active Directory object class and administrative construct maps to a Microsoft Entra ID construct, and which license tier each governance feature needs. The two decisions that shape the hybrid period: which sync engine to run and how users sign in. How to migrate groups and service accounts, how to rebuild privileged access on Privileged Identity Management (PIM), and the persona-based Conditional Access framework that replaces Group Policy logon restrictions. Chapter 10 covers governance, authentication modernization, monitoring, and the migration playbook.

## Purpose and scope

This chapter and the next are the program’s technical reference for moving the full identity lifecycle from on-premises Active Directory Domain Services (AD DS) to Microsoft Entra ID. They’re written for the architects who plan and run that move. The scope covers every object class and governance construct that makes up an Active Directory identity model:

- User objects: attributes, UPN routing, security identifiers (SIDs), group memberships, OU placement, and lifecycle state.

- Security and distribution groups: scope, nesting patterns, mail enablement, and dynamic membership.

- Service accounts: traditional user-object service accounts, managed service accounts (MSAs), and group managed service accounts (gMSAs).

- Privileged access: AdminSDHolder-protected groups, delegation models, and tiered administration.

- Conditional Access, replacing Group Policy logon restrictions with policy-driven cloud controls.

- Identity governance: access reviews, entitlement management, lifecycle workflows, and compliance attestation.

The environment is the one this workbook assumes throughout: a Microsoft 365 Government Community Cloud (GCC) tenant. GCC uses the worldwide Microsoft Graph and Azure portal endpoints (https://graph.microsoft.com), not the separate graph.microsoft.us endpoints that GCC High and DoD use. Some features reach GCC later than the commercial service or differ there, so check each feature against the Microsoft 365 Government service descriptions before you plan around it. Azure infrastructure and platform services are out of scope unless the text calls one out and says why.

The chapters assume:

- A GCC tenant with at least Microsoft Entra ID P2, and Microsoft Entra ID Governance for the features that need it (see the licensing table below).

- One or more source forests at Windows Server 2016 forest functional level or later, already inventoried with the read-only tools in Chapter 07 and Chapter 08.

- A Git repository for configuration as code and drift detection. The program’s reference build uses Gitea, but any Git host works.

- PowerShell examples written against the Microsoft Graph PowerShell SDK v2 and the ActiveDirectory module. The retired MSOnline and AzureAD modules aren’t used anywhere; see Appendix C for the retirement dates.

- Read access in both directories: a delegated read account in Active Directory and Global Reader (at minimum) in the tenant. Write steps name the narrower role they need.

## Decomposing the Active Directory identity landscape

Before any object moves, break the Active Directory identity model into its component object types. Each one has its own migration path, attribute mapping, and Entra ID equivalent. The figure summarizes the decomposition; the sections after it work through each row.

Each Active Directory object class maps to a Microsoft Entra ID construct; placement-driven policy becomes attribute-driven policy.

### User objects

User objects are the foundational identity type. Each one carries the attributes that define credentials, organizational placement, group membership, and authorization scope. Five dimensions drive the migration:

- userPrincipalName (UPN). The UPN suffix must be a domain verified in the tenant. If it isn’t, sync doesn’t fail; Entra ID builds a substitute UPN from the mail nickname and the tenant’s initial onmicrosoft.com domain, which is rarely what anyone wants. Non-routable suffixes such as .local need remediation before sync (see UPN suffixes and alternate login ID).

- objectSid. Entra ID doesn’t use SIDs for its own authorization. The on-premises SID is carried in onPremisesSecurityIdentifier, which must be unique in the tenant; a duplicate raises an AttributeValueMustBeUnique error during provisioning.

- memberOf. Memberships arrive with group sync. Nested memberships behave differently in Entra ID (see Nested groups).

- OU placement. OUs decide which Group Policy Objects apply and who can administer the object. Entra ID has no OU; administrative units take the delegation role, and groups take the policy-targeting role.

- Attribute richness. Entra ID maps a subset of AD attributes natively and carries extensionAttribute1 through 15 in onPremisesExtensionAttributes. Custom data beyond that needs directory extensions.

The core user attribute mapping is in the following table. The full reference, including the program’s assignments for the fifteen extension attributes, is in Appendix C.

| AD attribute | Microsoft Graph user property | Notes |
| --- | --- | --- |
| sAMAccountName | onPremisesSamAccountName | Read-only in Entra ID for synced users |
| userPrincipalName | userPrincipalName | Suffix must be a verified domain; the sign-in name |
| objectSid | onPremisesSecurityIdentifier | Must be unique in the tenant |
| mail | mail | Primary SMTP address |
| displayName, givenName, sn | displayName, givenName, surname | Direct mapping |
| department, title | department, jobTitle | Direct mapping; both usable in dynamic group rules |
| manager (DN) | manager (relationship) | Resolved as a relationship, not an attribute |
| memberOf | memberOf (relationship) | Resolved by the sync engine |
| extensionAttribute1–15 | onPremisesExtensionAttributes | Program-assigned meanings in Appendix C |
| userAccountControl | accountEnabled | The disabled bit becomes a Boolean |
| pwdLastSet | lastPasswordChangeDateTime | Password age |
| whenCreated | createdDateTime | The date the object reached Entra ID, not the AD creation date |

### Security groups

Active Directory security groups are the authorization backbone. AD classifies them by scope (domain local, global, universal) and by type (security, distribution). The AGDLP pattern (accounts into global groups, global groups into domain local groups, domain local groups onto permissions) and its multi-domain variant AGUDLP define the canonical AD group architecture. Entra ID has no group scope, so each scope maps to the same target with a different migration path.

| AD group scope | Nesting capability | Entra ID equivalent | Migration path |
| --- | --- | --- | --- |
| Domain local | Can contain global and universal groups from any domain | Security group (assigned) | Sync or recreate as cloud-only; flatten if nested |
| Global | Can contain users and global groups from the same domain only | Security group (assigned or dynamic) | Sync; evaluate for dynamic membership |
| Universal | Can contain users and groups from any domain in the forest | Security group (assigned) | Sync; the preferred scope for multi-domain forests |

### Distribution groups

Distribution groups route mail. They’re either mail-enabled security groups, which do both jobs, or pure distribution groups. In the cloud they become mail-enabled security groups or distribution groups managed through Exchange Online.

- Mail-enabled security groups sync from AD and keep both their security and mail functions in Exchange Online.

- On-premises dynamic distribution groups don’t sync. Recreate them in Exchange Online as dynamic distribution groups, which use OPATH filter syntax.

- For each distribution group, decide whether it should become a Microsoft 365 group instead, to gain a shared mailbox, calendar, and file storage.

### Service accounts

Service accounts are a critical identity class that is often under-governed. They come in three forms in Active Directory, each with a different path to Entra ID. The detailed migration matrix is in Modernizing service accounts.

| AD service account type | Characteristics | Entra ID target | Risk profile |
| --- | --- | --- | --- |
| Traditional (user object, often an svc- prefix) | Password-based, often “password never expires,” often allowed to log on interactively | Application registration with a certificate or federated credential; managed identity where the workload runs in Azure | High: static credentials, often over-privileged |
| Managed service account (MSA) | Automatically managed password, bound to one server | gMSA on-premises; managed identity if the workload moves to Azure | Medium: server-scoped, little governance visibility |
| Group managed service account (gMSA) | Automatically managed password, usable by several servers | Retain for on-premises Kerberos workloads; workload identity federation when the workload moves | Medium: better than traditional, still AD-dependent |

### Computer objects

Computer objects represent domain-joined devices. Their path runs from domain joined, to Microsoft Entra hybrid joined, to Microsoft Entra joined. This chapter covers devices only where they meet identity governance, such as device-based Conditional Access and device compliance as an access signal. The device estate and the services it depends on are in Chapter 04.

### Organizational units

OUs serve three governance functions in Active Directory: Group Policy scoping, administrative delegation, and logical organization. Entra ID has no OU construct; each function moves somewhere different.

| AD OU function | Entra ID equivalent | Implementation notes |
| --- | --- | --- |
| Group Policy scoping | Conditional Access policies and Intune configuration profiles | Target by group membership, not container |
| Administrative delegation | Administrative units (AUs) | Creating AUs is free; each AU-scoped administrator needs Entra ID P1. Dynamic AU membership needs P1 for each member. |
| Logical organization | Dynamic groups and attributes | Attribute-driven grouping replaces the container hierarchy |

Chapter 05 works through the delegation design in detail.

## Design principle: placement versus attributes

Entra ID inverts the Active Directory governance model. In AD, placement determines policy: an object’s OU decides which Group Policy Objects apply. In Entra ID, attributes determine policy: an object’s properties decide its group memberships, and memberships decide which policies apply. This inversion is the most important architectural idea in the migration, and it’s why attribute quality (Chapter 08) gates everything that follows.

### AdminSDHolder and protected groups

Active Directory protects members of its most privileged groups with the AdminSDHolder object. Every 60 minutes by default, the Security Descriptor Propagator (SDProp) process on the PDC emulator compares the permissions on each protected account and group with the permissions on the domain’s AdminSDHolder object, and resets any that differ. On current Windows Server versions the protected accounts and groups are:

- Account Operators

- Administrator (the built-in account)

- Administrators

- Backup Operators

- Domain Admins

- Domain Controllers

- Enterprise Admins

- Enterprise Key Admins

- Key Admins

- krbtgt

- Print Operators

- Read-only Domain Controllers

- Replicator

- Schema Admins

- Server Operators

Cert Publishers was protected only in Windows 2000 SP4 through Windows Server 2003 and isn’t on the current list. Any account with direct or transitive membership in a protected group gets adminCount set to 1, and the flag stays set after the account leaves the group, so adminCount overstates current privilege. Treat it as a lead to investigate, not a finding.

Entra ID has no AdminSDHolder. The nearest controls are Privileged Identity Management, which makes role assignments eligible and time-bound instead of standing, and protected actions, which require a Conditional Access authentication context before specific high-impact permissions can be used. Neither copies AdminSDHolder’s behavior; together they serve its purpose, which is keeping privileged access from drifting quietly. The mapping from AD privileged groups to Entra roles is in Privileged access.

## The Entra ID identity architecture

### The object model

Entra ID is a flat, attribute-driven directory, where Active Directory is hierarchical and container-based. These object types make up the target architecture.

| Object type | Description | AD equivalent | Source of authority |
| --- | --- | --- | --- |
| User | Human identity with credentials and profile attributes | User object | Synced from AD, or cloud-only |
| Security group | Authorization group; assigned or dynamic membership | Security group (all scopes) | Synced or cloud-only |
| Microsoft 365 group | Collaboration group with mailbox, calendar, files, Planner, and Teams | None | Cloud-only |
| Mail-enabled security group | Security group with an Exchange Online address | Mail-enabled security group | Synced or cloud-only |
| Distribution group | Mail routing without a security function | Distribution group | Synced or cloud-only |
| Administrative unit | Scope for delegated administration | Organizational unit (delegation function) | Cloud-only |
| Application registration | Application definition: credentials, permissions, redirect URIs | None | Cloud-only |
| Service principal | The application’s instance and identity in a tenant | Service account (functional) | Created from an application registration or a gallery app |
| Managed identity | Identity for an Azure resource; Azure manages its credentials | gMSA (functional) | Created with an Azure resource, or as a standalone Azure resource |

Managed identities come in two types. A system-assigned identity is created with an Azure resource, shares that resource’s lifecycle, and can’t be shared. A user-assigned identity is a standalone Azure resource that can be assigned to several resources and must be deleted explicitly; Microsoft recommends user-assigned identities for most scenarios. Either way, a managed identity is a special type of service principal, and it exists only for workloads that run on Azure resources.

### Tenant boundary and forest boundary

The tenant is the security and administrative boundary. It’s analogous to an AD forest, not a domain.

- One tenant is one trust boundary. There are no domain trusts inside it.

- Cross-tenant access is governed by B2B collaboration, B2B direct connect, and cross-tenant access settings, which take the place of forest trusts (Chapter 10).

- A tenant has no domain hierarchy. Verified domains are routing suffixes for sign-in names and mail, not security boundaries.

- Several forests can sync into one tenant. Microsoft Entra Connect Sync handles connected forests from one server; Microsoft Entra Cloud Sync also handles disconnected forests, with agents in each.

### Licensing for governance features

Governance features are gated by license tier, and the tiers changed when Microsoft moved most governance capability into Microsoft Entra ID Governance. As of October 2026, access reviews and entitlement management require Entra ID Governance for the member users involved, with only some capabilities still operating under P2. Plan on Governance licensing for every user who requests access packages, reviews access, or is reviewed.

| Feature | Free | P1 | P2 | Entra ID Governance |
| --- | --- | --- | --- | --- |
| User and group management | Yes | Yes | Yes | Yes |
| Conditional Access |  | Yes | Yes | Yes |
| Dynamic membership groups (P1 per unique member) |  | Yes | Yes | Yes |
| Administrative units (P1 per AU administrator) | Create only | Yes | Yes | Yes |
| Group provisioning to AD with Cloud Sync |  | Yes | Yes | Yes |
| Cross-tenant synchronization of users (same cloud) |  | Yes | Yes | Yes |
| Risk-based Conditional Access (ID Protection) |  |  | Yes | Not included; the Entra Suite adds ID Protection |
| Privileged Identity Management, including PIM for Groups |  |  | Yes | Yes |
| Access reviews |  |  | Some capabilities | Yes |
| Entitlement management (access packages) |  |  | Some capabilities | Yes |
| Lifecycle Workflows |  |  |  | Yes |
| Cross-tenant synchronization of groups |  |  |  | Yes |
| Conditional Access for workload identities | Separate Workload ID Premium license |  |  |  |

The table draws on Microsoft’s licensing reference. A few packaging points matter for planning:

- Entra ID P1 is included in Microsoft 365 E3 and E5; P2 is included in E5. Government G3 and G5 plans carry the equivalent service plans.

- Entra ID Governance requires a P1 or P2 prerequisite in the tenant. Government SKUs (Microsoft Entra ID Governance for Government, and a Governance add-on for P2 for Government) are available in GCC.

- The Microsoft Entra Suite bundles Private Access, Internet Access, ID Governance, ID Protection, and Verified ID, for P1 and P2 customers.

- Risk-based Conditional Access policies require P2.

## Licensing assumption

These chapters assume P2 for every user and Entra ID Governance for the populations that use access packages, access reviews, and Lifecycle Workflows. Confirm GCC availability for each feature in the Microsoft 365 Government service description; GCC rollout can lag the commercial service.

### Dynamic group rule syntax

Dynamic groups compute membership from user or device attributes. Rules use operators such as -eq, -ne, -startsWith, -notStartsWith, -contains, -notContains, -match, -notMatch, -in, and -notIn, and they can be combined with -and and -or. A department group looks like this:

(user.department -eq "Finance") -and (user.accountEnabled -eq true)

Three cautions apply:

- Membership isn’t instant. When an attribute changes, Entra ID re-evaluates the dynamic group rules in the directory, and membership changes don’t appear immediately. Plan for that delay where a dynamic group gates access to a critical resource.

- Attribute write permissions are a security boundary. A dynamic group is only as trustworthy as the controls on the attributes it reads. Some on-premises attributes can be self-writable; audit write permissions, at the source and in Entra ID, for every attribute used in a security-sensitive rule.

- Don’t build on memberOf. The preview memberOf operator lets a dynamic group include members of other groups, but Microsoft is ending the preview: after November 3, 2026, dynamic groups, dynamic administrative units, and access package auto-assignment policies that use it stop updating and freeze in their last state. Replace any memberOf rule before then.

## Choosing and configuring the sync engine

### Cloud Sync or Connect Sync

Microsoft offers two engines for hybrid identity sync. Microsoft Entra Connect Sync is the long-standing, full-featured engine that runs on a Windows Server. Microsoft Entra Cloud Sync is a lightweight provisioning agent with its configuration held in the cloud. Microsoft now describes Cloud Sync as its strategic direction: new sync and provisioning features are built primarily on it, and it’s the recommended path for most organizations.

The program’s comparison draws on Microsoft’s decision guide (as of its October 2026 revision):

| Capability | Connect Sync | Cloud Sync |
| --- | --- | --- |
| Deployment | On-premises Windows Server | Lightweight agents; can run on existing domain controllers or standalone servers |
| Connected multi-forest | Yes | Yes |
| Disconnected forests (mergers and acquisitions) | No | Yes |
| High availability | One active server; a staging server as standby | Multiple active agents with automatic failover |
| Scale per AD domain | No stated limit | Up to 150,000 objects |
| Group size | Up to 250,000 members | Up to 50,000 members |
| Password hash sync and password writeback | Yes | Yes |
| Exchange hybrid writeback | Yes | Yes |
| Device sync for hybrid join | Yes | Yes (enabled separately) |
| OU-based filtering | Yes | Yes |
| Attribute-based filtering | Yes | Limited |
| Advanced sync rules | Yes (sync rules editor) | No (expression builder only) |
| Cross-forest references; merging attributes across domains | Yes | No |
| Group provisioning from Entra ID to AD | No | Yes |
| Device writeback | Yes (discontinued in favor of Cloud Kerberos trust) | No |
| Pass-through authentication or AD FS configured by the tool | Yes | No (configured separately; keeps working after migration) |
| On-demand provisioning for testing | No | Yes |
| US Government clouds | Yes | Yes |

Two corrections to older guidance matter here. First, Group Writeback v2 in Connect Sync was a preview that Microsoft discontinued on June 30, 2024; Connect Sync is no longer supported for provisioning cloud security groups to AD. Cloud Sync’s group provisioning to AD replaces it, and it can run alongside Connect Sync for that one job. Group Writeback v1 remains only for writing Microsoft 365 groups back to AD. Second, Cloud Sync now handles Exchange hybrid writeback, so Exchange hybrid alone no longer forces Connect Sync.

## Recommendation: Cloud Sync unless a Connect-only requirement applies

Use Cloud Sync for new deployments and plan to migrate existing Connect Sync installations to it. Stay on Connect Sync, for now, only where a forest needs something Cloud Sync doesn’t do: more than 150,000 objects in a domain, groups over 50,000 members, advanced sync rules, cross-forest references, or attribute merging across domains. Both engines can run in the same forest with mutually exclusive scopes, which lets you move populations in stages.

The sync and sign-in decision: Cloud Sync unless a Connect-only requirement applies, password hash sync in every case, pass-through authentication only as a transition, and AD FS as a decommission target.

### Filtering

Filtering decides which AD objects reach Entra ID. Connect Sync applies four methods in this order:

- Domain-based. Include or exclude whole domains, such as test or perimeter domains.

- OU-based. The most common method. Exclude OUs that hold service accounts, unneeded computer objects, or staging objects. Both engines support it.

- Attribute-based. Filter individual objects on attribute values with scoping conditions in sync rules; for example, exclude objects where extensionAttribute15 equals DoNotSync. Cloud Sync supports only basic attribute filtering.

- Group-based. Sync only members of a named group. Use it for pilots only; it doesn’t scale and it makes sync depend on group membership.

### Attribute flow and transformations

Attribute flow defines how AD attributes become Entra ID attributes. In Connect Sync, custom sync rules take precedence over the default rules by precedence number; Cloud Sync uses an expression builder for attribute mappings. Three transformations the program commonly needs, shown in Connect Sync’s declarative provisioning expression language:

| Scenario | Source expression | Target attribute | Purpose |
| --- | --- | --- | --- |
| UPN construction | IIF(IsPresent([userPrincipalName]),IIF(InStr([userPrincipalName],"@contoso.local")>0,Replace([userPrincipalName],"@contoso.local","@contoso.gov"),[userPrincipalName]),Error("UPN required")) | userPrincipalName | Replace a non-routable suffix with a verified domain |
| Display name normalization | IIF(IsPresent([sn]),Join(", ",[sn],[givenName]),[displayName]) | displayName | Enforce “Last, First” |
| Account type classification | IIF(CBool(InStr(LCase([distinguishedName]),"ou=service accounts")),"Service","Standard") | extensionAttribute10 | Classify from OU placement during the transition |

The third rule is a bridge, not an end state. It derives a classification from placement, which is exactly the AD habit the migration retires. Once the classification is written to the source object, drop the rule.

### Staging mode and recovery

Connect Sync’s staging mode lets a second server import and synchronize without exporting to Entra ID. It serves three purposes:

- Recovery. If the active server fails, disable staging mode on the standby to promote it. Microsoft recommends a staging-mode standby so that password hash sync isn’t down for long.

- Upgrade validation. Test new sync rules or versions on the staging server before cutting over.

- Configuration verification. Compare pending export counts between the active and staging servers to detect configuration drift.

Cloud Sync has no staging mode. It gets availability from multiple active agents instead.

## One active Connect Sync server per tenant

Never run two Connect Sync servers in active (non-staging) mode against the same tenant. Connect Sync supports one active instance; Cloud Sync is the engine that supports multiple active agents. Two active Connect servers export conflicting changes that are hard to unwind.

### Choosing the sign-in method

The sign-in method decides where passwords are validated. Microsoft’s comparison and the program’s position:

| Criterion | Password hash sync (PHS) | Pass-through authentication (PTA) | Federation (AD FS) |
| --- | --- | --- | --- |
| Where validation happens | In the cloud, against a synchronized hash of the password hash | In the cloud, after a check by an on-premises agent against AD | On-premises |
| Extra on-premises infrastructure | None beyond the sync tool | Agent servers; Microsoft recommends at least three in production, treated as Tier 0 | Two or more AD FS servers and two or more Web Application Proxy servers, load balancing, and certificates |
| Survives an on-premises outage | Yes | No | No |
| Enforces on-premises account state at sign-in | Not immediately; changes arrive with the next sync | Yes (disabled, locked out, expired, logon hours) | Yes |
| Leaked-credential detection | Yes; needs PHS | Only if PHS is also on | Only if PHS is also on |
| Single sign-on from domain-joined devices | Entra joined or hybrid joined devices, or Seamless SSO | Same as PHS | Yes |
| Program position | Preferred | Transitional | Legacy; decommission target |

Microsoft recommends PHS for cloud authentication, and recommends enabling it whichever method you choose: it’s the fallback if PTA agents or federation fail, it’s required for ID Protection’s leaked-credential detection, and organizations that had it on recovered from ransomware outages in hours rather than weeks. Failover from PTA to PHS isn’t automatic; an administrator switches the sign-in method in the sync tool.

## Recommendation: PHS everywhere

PHS is the program’s sign-in method. Where PTA or federation is still in place, turn PHS on anyway so that the fallback and risk detections exist before they’re needed.

### Soft match and hard match

When the sync engine adds an object that might already exist in the cloud, Entra ID looks for a match in this order:

- Hard match. The incoming object’s sourceAnchor (by default the Base64 form of ms-DS-ConsistencyGuid, or objectGUID in some configurations) is compared with the onPremisesImmutableId of existing cloud objects. A match makes AD the source of authority for that object.

- Soft match. If there’s no hard match, Entra ID compares userPrincipalName and the primary SMTP address in proxyAddresses. A soft match only works if the cloud object has no onPremisesImmutableId yet; afterward, the sourceAnchor is written so later matches are hard.

Either match overwrites the cloud object’s attributes with the on-premises values, including the password hash under PHS, so clean up AD data first. Microsoft has hardened both paths:

- Tenant settings BlockSoftMatchEnabled and BlockCloudObjectTakeoverThroughHardMatchEnabled disable each match type. Microsoft advises leaving both blocked except during a planned matching window.

- Since July 1, 2026, Entra ID blocks a hard match when the cloud account already has onPremisesObjectIdentifier set, or holds or is eligible for a privileged Entra role. The block is enforced in the cloud, so it applies to both sync engines. Don’t plan to take over cloud-only administrator accounts by sync; Microsoft recommends against syncing on-premises accounts onto existing administrative cloud accounts at all.

### UPN suffixes and alternate login ID

Many forests use non-routable UPN suffixes (contoso.local) or internal ones (corp.contoso.com) that can’t be verified in the tenant. The remediation options, in order of preference:

- Add a routable UPN suffix to the forest and update user UPNs. This keeps the sign-in name consistent everywhere and is what Microsoft recommends; it also recommends matching the UPN to the primary SMTP address.

- Transform the UPN during sync with a sync rule (see Attribute flow). AD keeps its UPN; Entra ID gets a constructed one. This creates a permanent mismatch that some applications notice.

- Use an alternate login ID. Connect Sync can use another attribute, such as mail, as the Entra ID sign-in name. Microsoft notes that alternate ID isn’t compatible with all Microsoft 365 workloads. Separately, “email as an alternate login ID” lets cloud-authenticated users sign in with a proxy address in addition to the UPN; it remains a preview feature as of October 2026.

DNS namespace alignment for new UPN suffixes is covered in the workbook’s network and DNS material.

## Migrating groups

### Mapping the AGDLP tiers

The AGDLP model doesn’t map one-to-one onto Entra ID, which has no scope-based nesting rules. Each tier has its own target.

| AGDLP tier | AD implementation | Entra ID equivalent | Migration approach |
| --- | --- | --- | --- |
| A (account) | User objects | Users | Sync |
| G (global group) | Global security group of users from one domain | Dynamic security group, or assigned security group | Evaluate for dynamic conversion; sync where membership must stay static |
| U (universal group) | Universal group spanning domains | Security group (no scope in Entra ID) | Sync; consider consolidating with G-tier groups |
| DL (domain local group) | Group placed on a resource ACL | Security group assigned to an app role or resource | Sync; may collapse into the resource assignment |
| P (permission) | NTFS, share, or resource ACL entry | App role assignment, SharePoint permission level, or Entra role | Re-express in the cloud permission model |

### The per-group decision

Every AD security group needs one of three decisions: keep it synchronized (hybrid), convert it to cloud-only, or retire it. The group’s purpose and dependencies decide which.

| Group characteristic | Decision | Rationale |
| --- | --- | --- |
| Used only for on-premises resource ACLs | Keep in AD; don’t sync | A cloud copy adds nothing |
| Used for both on-premises and cloud resources | Synchronize | AD stays the source of authority during the transition |
| Used only for cloud resources | Convert to cloud-only | Removes the AD dependency |
| Membership follows attributes exactly | Convert to dynamic group | Removes manual membership management |
| No members or no resource assignments | Retire | Shrinks the identity surface |

Where a cloud-only group still has to grant access to an AD-integrated (Kerberos) application, provision it back to AD with Cloud Sync’s group provisioning, which writes cloud security groups to AD as universal groups.

### Converting static groups to dynamic groups

Static AD groups whose membership really follows department, location, or role are candidates for dynamic groups. The conversion:

- Analyze current membership. Export the members and find the attributes they share.

- Draft the rule from those attributes (see Dynamic group rule syntax).

- Validate coverage. Compare what the rule would return with today’s membership. The admin center’s rule validation helps here.

- Handle exceptions. Members who don’t fit need attribute remediation at the source or an explicit, reviewed exception group.

- Create the dynamic group and watch membership populate.

- Move resource assignments from the synced static group to the dynamic group.

- Retire the static group. Take it out of sync scope and archive its membership export.

### Nested groups

Entra ID security groups can contain other security groups, but nesting works for fewer things than in AD. As of October 2026:

- Conditional Access and group-scoped policies follow nested members.

- Group-based assignment to applications doesn’t cascade to nested groups, and group-based licensing doesn’t apply to members of nested groups.

- Groups can’t be nested into groups synced from AD, into Microsoft 365 groups, into mail-enabled security groups, or into role-assignable groups.

- Dynamic groups contain only users or only devices, never groups.

So flatten deep AGDLP chains before they become cloud authorization:

- Identify the chains: recursively enumerate membership and find chains deeper than one level.

- Flatten to direct membership or a dynamic rule that produces the same effective membership.

- Record the mapping from the original nesting to the flattened result, for the audit trail.

### Microsoft 365 groups

Microsoft 365 groups add collaboration features that AD groups never had: a shared mailbox, calendar, files, Planner, and Teams.

- Convert to a Microsoft 365 group when the group needs collaboration features, represents a project or working team, or should be owner-managed.

- Don’t convert when the group exists only for authorization or needs to contain other groups; Microsoft 365 groups can contain only users.

- Govern them with naming conventions (prefixes such as GRP-, PRJ-, DEPT-), an expiration policy, and sensitivity labels.

The expiration policy deletes groups that owners don’t renew; groups with user activity renew automatically, owners are notified before expiry, and a deleted group can be restored for 30 days. The lifetime is a preset or a custom value of at least 30 days, and only one policy applies across the tenant. The program uses 365 days.

### Self-service group management

Entra ID lets group owners manage membership without IT. The program puts three controls around it:

- Recurring access reviews of sensitive group membership by owners (licensing in Licensing for governance features).

- An expiration policy for Microsoft 365 groups, as above.

- A group naming policy to enforce the conventions.

### Exporting AD groups and creating cloud groups

The script exports AD groups with a migration classification, then creates cloud-only security groups for the ones marked as security groups. It reads AD and writes only to Entra ID, and only for groups you select.

## Illustrative code

The PowerShell in this chapter is illustrative. It hasn’t been tested against a production forest or tenant. Review it, run the export in a lab first, and run the create step only after the group decisions above are recorded.

#Requires -Modules ActiveDirectory, Microsoft.Graph.Groups
# Federal Modernization Program: export AD groups and create cloud-only security groups.

# --- Phase 1: export AD groups ---
$exportPath = "C:\FMP\Exports\ADGroups_$(Get-Date -Format 'yyyyMMdd').json"

$adGroups = Get-ADGroup -Filter * -Properties Description, GroupScope, GroupCategory,
        ManagedBy, Members, MemberOf, Mail, extensionAttribute1, extensionAttribute2,
        DistinguishedName, WhenCreated, WhenChanged |
    Select-Object @{N = 'Name';        E = { $_.Name } },
                  @{N = 'Description'; E = { $_.Description } },
                  @{N = 'Scope';       E = { $_.GroupScope.ToString() } },
                  @{N = 'Category';    E = { $_.GroupCategory.ToString() } },
                  @{N = 'ManagedBy';   E = { $_.ManagedBy } },
                  @{N = 'MemberCount'; E = { ($_.Members | Measure-Object).Count } },
                  @{N = 'NestedGroupCount'; E = {
                        ($_.Members | Where-Object {
                            (Get-ADObject $_ -Properties objectClass).objectClass -eq 'group'
                        } | Measure-Object).Count } },
                  @{N = 'Mail';        E = { $_.Mail } },
                  @{N = 'OU';          E = { ($_.DistinguishedName -split ',', 2)[1] } },
                  @{N = 'Created';     E = { $_.WhenCreated } },
                  @{N = 'Modified';    E = { $_.WhenChanged } },
                  @{N = 'MigrationTarget'; E = {
                        if ($_.GroupCategory -eq 'Distribution') { 'DistributionGroup' }
                        elseif (($_.Members | Measure-Object).Count -eq 0) { 'Decommission' }
                        else { 'SecurityGroup' } } }

$adGroups | ConvertTo-Json -Depth 5 | Out-File -FilePath $exportPath -Encoding UTF8
Write-Host "Exported $($adGroups.Count) groups to $exportPath" -ForegroundColor Green

# --- Phase 2: create cloud-only security groups (review the export first) ---
Connect-MgGraph -Scopes 'Group.ReadWrite.All'

foreach ($group in ($adGroups | Where-Object MigrationTarget -eq 'SecurityGroup')) {
    $params = @{
        DisplayName     = $group.Name
        Description     = $group.Description
        MailEnabled     = $false
        MailNickname    = ($group.Name -replace '[^a-zA-Z0-9]', '').ToLower()
        SecurityEnabled = $true
        GroupTypes      = @()
    }
    try {
        $newGroup = New-MgGroup -BodyParameter $params
        Write-Host "Created group: $($newGroup.DisplayName) [$($newGroup.Id)]" -ForegroundColor Green
    }
    catch {
        Write-Warning "Failed to create group $($group.Name): $_"
    }
}

Disconnect-MgGraph

NestedGroupCount calls Get-ADObject once per member, which is slow on large groups; in a big forest, run the export against one OU at a time.

## Modernizing service accounts

### The migration path matrix

Each AD service account maps to an Entra ID construct that depends on where the workload runs. The general rule is to eliminate stored secrets: managed identities for Azure-hosted workloads, workload identity federation for workloads that already have an identity from another trusted issuer, and certificates only where neither applies.

| AD account type | Workload location | Entra ID target | Authentication | Credential management |
| --- | --- | --- | --- | --- |
| Traditional | Calls Microsoft 365 or other Entra-protected APIs | Application registration and service principal | Certificate, or federated credential where the host has an OIDC issuer | Certificate rotation (program standard: annual), or no stored secret |
| Traditional | Azure resource | Managed identity (user-assigned preferred) | Managed by Azure | None |
| Traditional | On-premises, Kerberos only | gMSA | Kerberos | Managed by AD |
| MSA | On-premises | gMSA (upgrade first) | Kerberos | Managed by AD |
| gMSA | Moving to the cloud | Workload identity federation or managed identity | Federated token or managed | No stored secrets |
| gMSA | Hybrid | Keep the gMSA, plus an application registration for cloud calls | Kerberos on-premises; certificate or federated credential to the cloud | Split |
| IIS application pool identity | On-premises IIS | gMSA now; managed identity once moved to Azure | Kerberos, then managed | Progressive |
| Scheduled task identity | On-premises | gMSA now; an Azure Automation runbook with a managed identity once moved | Kerberos, then managed | Progressive |

### Workload identity federation

Workload identity federation removes stored secrets by having Entra ID trust tokens from an external identity provider. The workload presents a token from its own issuer (GitHub Actions, a Kubernetes cluster, Google Cloud, a SPIFFE deployment, another OIDC provider), and Entra ID exchanges it for an access token. A federated identity credential on the application registration, or on a user-assigned managed identity, has three working parts:

- Issuer. The external provider’s OIDC issuer URL. It must match the token’s iss claim, and Entra ID uses it to fetch the signing keys, so the discovery document has to be reachable.

- Subject. Must match the token’s sub claim exactly; for GitHub Actions, for example, repo:org/repo:ref:refs/heads/main. Wildcards aren’t supported.

- Audience. The recommended value is api://AzureADTokenExchange.

An application or user-assigned managed identity can hold at most 20 federated identity credentials, and an incorrect subject is accepted at creation and only fails at token exchange, so test each one.

### Conditional Access for workload identities

Conditional Access can target service principals, which lets you block a workload from outside known IP ranges, block it when ID Protection flags it as risky, or combine it with authentication contexts. Know the limits before you design around it:

- Creating or modifying these policies requires Workload Identities Premium licensing.

- Policies apply only to single-tenant service principals registered in your tenant. Multitenant and third-party SaaS apps, and managed identities, aren’t covered; include managed identities in access reviews instead.

- A policy assigned to a group that contains a service principal isn’t enforced for it; assign the workload identity to the policy directly.

### Governing service principals

Every application registration and service principal gets the same controls:

- Ownership. At least two human owners, never service accounts.

- Credentials. Prefer federated credentials and managed identities. Where certificates remain, rotate them on a schedule (program standard: annually) through Key Vault or the CI/CD pipeline. Don’t use client secrets for production workloads.

- Reviews. Recurring reviews of delegated and application permissions by app owners (program standard: quarterly).

- Least privilege. Use application-specific roles and scopes; avoid broad permissions such as Directory.ReadWrite.All.

### Discovering service accounts

The discovery function finds likely service accounts in AD, classifies each by type and risk, and suggests a target. It only reads. The function is part of the FMPIdentityAssessment module in Appendix C, where it’s maintained.

#Requires -Modules ActiveDirectory
function Get-FMPServiceAccountInventory {
    [CmdletBinding()]
    param(
        [string]$SearchBase = (Get-ADDomain).DistinguishedName,
        [string]$ExportPath = "C:\FMP\Exports\ServiceAccounts_$(Get-Date -Format 'yyyyMMdd').json"
    )

    $results = [System.Collections.Generic.List[object]]::new()
    $staleCutoff = (Get-Date).AddDays(-90)

    # --- Traditional service accounts: user objects with service indicators ---
    $svcUsers = Get-ADUser -SearchBase $SearchBase -Filter {
            (ServicePrincipalName -like '*') -or (SamAccountName -like 'svc-*') -or
            (SamAccountName -like 'svc_*') -or (SamAccountName -like 'sa-*') -or
            (Description -like '*service*account*')
        } -Properties UserPrincipalName, DisplayName, Description, ServicePrincipalName,
                      Enabled, PasswordNeverExpires, PasswordLastSet, LastLogonDate,
                      WhenCreated, MemberOf, DistinguishedName

    foreach ($svc in $svcUsers) {
        $spnCount = ($svc.ServicePrincipalName | Measure-Object).Count
        $daysSincePasswordChange = if ($svc.PasswordLastSet) {
            (New-TimeSpan -Start $svc.PasswordLastSet -End (Get-Date)).Days
        } else { -1 }

        $recommendation = switch ($true) {
            (-not $svc.Enabled)                           { 'Disabled: verify and retire'; break }
            ($svc.LastLogonDate -lt $staleCutoff)         { 'Stale: verify use and retire if unused'; break }
            ($svc.PasswordNeverExpires)                   { 'HIGH RISK: move to a workload identity (federated credential, managed identity, or certificate)'; break }
            ($spnCount -gt 0)                             { 'Kerberos service: convert to gMSA, then evaluate workload identity federation'; break }
            default                                       { 'Evaluate the workload; target a managed identity or application registration' }
        }

        $riskLevel = if ($svc.Enabled -and $svc.PasswordNeverExpires) { 'HIGH' }
                     elseif ($daysSincePasswordChange -gt 365)          { 'HIGH' }
                     elseif ($svc.Enabled)                              { 'MEDIUM' }
                     else                                               { 'LOW' }

        $results.Add([PSCustomObject]@{
            Type                    = 'TraditionalServiceAccount'
            SamAccountName          = $svc.SamAccountName
            DisplayName             = $svc.DisplayName
            Description             = $svc.Description
            Enabled                 = $svc.Enabled
            PasswordNeverExpires    = $svc.PasswordNeverExpires
            DaysSincePasswordChange = $daysSincePasswordChange
            SPNCount                = $spnCount
            SPNs                    = ($svc.ServicePrincipalName -join '; ')
            LastLogon               = $svc.LastLogonDate
            GroupMembershipCount    = ($svc.MemberOf | Measure-Object).Count
            OU                      = ($svc.DistinguishedName -split ',', 2)[1]
            RiskLevel               = $riskLevel
            Recommendation          = $recommendation
        })
    }

    # --- Managed service accounts (MSA and gMSA) ---
    $msaAccounts = Get-ADServiceAccount -Filter * -SearchBase $SearchBase -Properties Enabled,
        DistinguishedName, ObjectClass, 'msDS-ManagedPasswordInterval', WhenCreated

    foreach ($msa in $msaAccounts) {
        $isGmsa = ($msa.ObjectClass -eq 'msDS-GroupManagedServiceAccount')
        $results.Add([PSCustomObject]@{
            Type                    = if ($isGmsa) { 'gMSA' } else { 'MSA' }
            SamAccountName          = $msa.SamAccountName
            DisplayName             = $msa.SamAccountName
            Description             = ''
            Enabled                 = $msa.Enabled
            PasswordNeverExpires    = $false
            DaysSincePasswordChange = 0
            SPNCount                = 0
            SPNs                    = ''
            LastLogon               = $null
            GroupMembershipCount    = 0
            OU                      = ($msa.DistinguishedName -split ',', 2)[1]
            RiskLevel               = 'LOW'
            Recommendation          = if ($isGmsa) {
                'Keep for on-premises workloads; plan workload identity federation when the workload moves'
            } else {
                'Upgrade to gMSA first, then evaluate for cloud migration'
            }
        })
    }

    $results | ConvertTo-Json -Depth 5 | Out-File -FilePath $ExportPath -Encoding UTF8

    Write-Host "`n=== Service account discovery summary ===" -ForegroundColor Cyan
    Write-Host "Traditional: $(($results | Where-Object Type -eq 'TraditionalServiceAccount').Count)"
    Write-Host "MSA:         $(($results | Where-Object Type -eq 'MSA').Count)"
    Write-Host "gMSA:        $(($results | Where-Object Type -eq 'gMSA').Count)"
    Write-Host "HIGH risk:   $(($results | Where-Object RiskLevel -eq 'HIGH').Count)" -ForegroundColor Red
    Write-Host "MEDIUM risk: $(($results | Where-Object RiskLevel -eq 'MEDIUM').Count)" -ForegroundColor Yellow
    Write-Host "Export:      $ExportPath" -ForegroundColor Cyan

    return $results
}

Compared with the earlier version of this script, the checks for disabled and stale accounts now run before the risk checks, so a disabled account with an SPN is reported as a retirement candidate instead of a gMSA candidate. Treat “stale” as a lead, and confirm it against domain controller and Entra ID sign-in logs before retiring anything.

## Privileged access

### Mapping AD privileged groups to Entra roles

Every AD privileged group maps to an Entra ID role governed by PIM. The core rule: no standing access to privileged roles. All privileged assignments are eligible, activated just in time; the only permanent active assignments are the two emergency access accounts. The mapping is the program’s design; there’s no one-to-one equivalence between AD groups and Entra roles.

| AD privileged group | Entra ID target | PIM assignment | Governance notes |
| --- | --- | --- | --- |
| Domain Admins | Global Administrator, held by very few | Eligible, with approval | Microsoft recommends fewer than five Global Administrators; most Domain Admin duties map to narrower roles |
| Enterprise Admins | Privileged Role Administrator | Eligible, with approval | Manages role assignments and PIM settings; separate approval chain |
| Schema Admins | No equivalent | Not applicable | Microsoft manages the directory schema. Directory extensions are added through application registrations (Application Administrator) |
| Account Operators | User Administrator scoped to administrative units | Eligible | Limits blast radius. Conditional Access can’t target AU-scoped role assignments, so put these administrators in a group for policy targeting |
| Server Operators | Intune role-based access, or Azure RBAC for Azure-hosted servers | Eligible | Server administration moves to device management |
| Backup Operators | Service-specific roles (for example, Exchange Administrator for mailbox recovery) | Eligible | No tenant-wide backup role |
| DnsAdmins | No direct equivalent | Not applicable | DNS moves to the Microsoft 365 admin center or the DNS provider |
| Group Policy Creator Owners | Intune Policy and Profile Manager (an Intune role) | Eligible | Group Policy functions move to Intune profiles and Conditional Access |

### PIM configuration standards

PIM role settings are defined per role. The program’s standards are below; Book 04, Appendix B is the authoritative per-role reference and tightens several values (shorter activations and approval for Tier 1 roles):

- Eligibility duration. Eligible assignments expire after at most 12 months and renew through an access review.

- Activation duration. Role-specific, from the table below. PIM allows 1 to 24 hours; the program’s default is 8.

- Activation requirements. Justification for every role. Ticket information for Global Administrator, Privileged Role Administrator, and Exchange Administrator; PIM records the ticket number but doesn’t check it against a ticketing system.

- Strong authentication at activation. PIM’s “require multifactor authentication” setting can be satisfied by an earlier sign-in in the same session. To force fresh, phishing-resistant authentication at activation, the program uses PIM’s Conditional Access authentication context option with an authentication strength.

- Approval. Required for Global Administrator, Privileged Role Administrator, and Security Administrator, with at least two named approvers who aren’t in the requester’s own administrative chain. If approval is required and no approvers are configured, PIM defaults to the active Privileged Role and Global Administrators, which can lock the tenant if none are active; configure named approvers and keep the emergency accounts ready.

- Notification. Activation notices go to the assignee, the Global Administrators, and the security operations mailbox.

| Role | Assignment | Max activation | Approval | Justification | Ticket |
| --- | --- | --- | --- | --- | --- |
| Global Administrator | Eligible | 4 hours | Yes | Yes | Yes |
| Privileged Role Administrator | Eligible | 4 hours | Yes | Yes | Yes |
| Security Administrator | Eligible | 8 hours | Yes | Yes | No |
| Exchange Administrator | Eligible | 8 hours | No | Yes | Yes |
| SharePoint Administrator | Eligible | 8 hours | No | Yes | No |
| User Administrator | Eligible | 8 hours | No | Yes | No |
| Groups Administrator | Eligible | 8 hours | No | Yes | No |
| Conditional Access Administrator | Eligible | 8 hours | No | Yes | No |
| Intune Administrator | Eligible | 8 hours | No | Yes | No |
| Authentication Administrator | Eligible | 8 hours | No | Yes | No |
| Application Administrator | Eligible | 8 hours | No | Yes | No |
| Compliance Administrator | Eligible | 8 hours | No | Yes | No |
| Security Reader | Eligible | 12 hours | No | No | No |
| Global Reader | Eligible | 12 hours | No | No | No |

Every activation in the table requires the phishing-resistant authentication context described above.

### PIM for Groups

PIM for Groups (formerly called privileged access groups) extends just-in-time activation to group membership and ownership. Instead of sitting permanently in a sensitive group, a user activates membership through PIM with the same controls as a role: justification, authentication context, approval.

- Use it for groups that grant access to sensitive applications, data, or administrative functions.

- Eligible groups. Any security group or Microsoft 365 group can be enabled, except dynamic groups and groups synced from AD. Since January 2023 a group doesn’t have to be role-assignable to use PIM for Groups.

- Role-assignable groups. A group must be created role-assignable only if it will hold an Entra role. Role-assignable groups get extra protection (only Global Administrators, Privileged Role Administrators, or the owner can manage them), so Microsoft suggests the setting even for non-role groups that guard sensitive resources. A tenant can have at most 500 role-assignable groups.

- Licensing. Every user eligible for membership or ownership needs P2 or Entra ID Governance.

### Emergency access accounts

Emergency access (“break-glass”) accounts restore access when normal administrator sign-in, MFA, or PIM fails. Microsoft’s current guidance changed an important detail of older designs: both accounts use phishing-resistant authentication, because Microsoft’s mandatory MFA for admin portals applies to them too (Microsoft enforces it in the public Azure cloud, not in Azure Government; see Book 04, Chapter 04). A password in a safe is no longer enough on its own. The program’s standard follows that guidance:

- Quantity. Two accounts, cloud-only, in the tenant’s onmicrosoft.com domain, not synced or federated.

- Naming. Don’t use names that mark them as emergency accounts (avoid emergency, breakglass, bg-).

- Authentication. A passkey (FIDO2) security key for each account, which is Microsoft’s recommended method, or certificate-based authentication where a PKI already exists. Use methods different from those of the normal admin accounts, and store each credential in a separate secure, fireproof location.

- Assignment. Global Administrator as a permanent active assignment in PIM, not eligible. These are the only permanent Global Administrator assignments.

- Conditional Access. Put both accounts in a dedicated exclusion group and exclude it from every policy that blocks or restricts sign-in. Report-only policies don’t need the exclusion.

- Monitoring. Alert on every sign-in and every audit event for these accounts. Any use is an incident until a post-use review says otherwise.

- Validation. Test sign-in and an administrative task at least every 90 days, as Microsoft recommends, and record the test in change management.

### Protected actions

Protected actions attach a Conditional Access authentication context to specific Entra permissions, so a user must satisfy that policy, typically phishing-resistant MFA, at the moment they use the permission, regardless of which role granted it. As of October 2026 they cover:

- Conditional Access policy management (create, update, delete)

- Cross-tenant access settings, including tenant restrictions

- Hard deletion of some directory objects from the recycle bin (users, Microsoft 365 groups, cloud security groups, applications)

- Named locations

- Protected action management itself

Protected actions require Entra ID P1 and can be added by a Conditional Access Administrator or Security Administrator. Microsoft’s privileged roles documentation still describes the feature as preview, so check its status before treating it as a compliance control. The source design’s mention of “deleting a tenant” isn’t on Microsoft’s list and has been dropped.

Protected actions and PIM complement each other. PIM can require an authentication context when a role is activated; protected actions enforce one when a high-impact permission is used, however the user got it. Use both: PIM for activation, protected actions for the operations that would let an attacker disable your controls. Exclude an emergency account from the Conditional Access policy behind each protected action, or a misconfiguration can lock everyone out of the policy that would fix it.

## The Conditional Access framework

### Design approach

Conditional Access replaces the logon restrictions, network access controls, and authentication policies that Active Directory enforced through Group Policy. The program’s framework is organized around personas, each a population with distinct access needs and risk.

| Persona | Description | Identified by | Risk |
| --- | --- | --- | --- |
| Internals | Employees and contractors with standard access | extensionAttribute6 in {Employee, Contractor} | Standard |
| Admins | Users eligible for or holding privileged roles | extensionAttribute10 = Privileged, or a group of PIM-eligible users | High |
| Externals | B2B guests from partner organizations | User type Guest, partner tenant | Elevated |
| Guests | Ad hoc external users outside partner organizations | User type Guest, other tenants or identity providers | High |
| Service accounts | Workload identities (single-tenant service principals) | Workload identity assignment | Variable |
| Break-glass | Emergency access accounts | Dedicated exclusion group | Excluded from restrictive policies |

Target the Admins persona with a group rather than by directory role alone: Conditional Access role targeting supports built-in directory roles only, not AU-scoped or custom roles.

### Named locations

- Trusted networks. IP ranges for offices, VPN egress points, and trusted proxies.

- Trusted countries. The United States, with others added only with documented justification.

- Location policy. Block sign-ins from outside the United States for all personas except approved travel exceptions. This is a program policy choice, not a property of GCC itself. GCC provides U.S. data residency, but users can sign in from anywhere unless policy blocks it.

### Authentication strengths

Authentication strengths name the method combinations a policy accepts. Entra ID has three built-in strengths:

| Strength | Accepted methods (summary) | Program target |
| --- | --- | --- |
| Phishing-resistant MFA | Windows Hello for Business or platform credential; FIDO2 security key (passkey); certificate-based authentication (multifactor) | Admins; high-risk sign-ins; all users as the end state |
| Passwordless MFA | The phishing-resistant methods, plus Microsoft Authenticator phone sign-in | Interim step for users moving off passwords |
| Multifactor authentication | All of the above, plus password with a second factor, Temporary Access Pass, and federated MFA | Internals and Externals during transition only |

Microsoft Authenticator push and phone sign-in aren’t phishing-resistant on their own; Microsoft’s M-22-09 guidance pairs Authenticator with managed-device policies to block external phishing. Passkeys held in Microsoft Authenticator are device-bound passkeys and count as FIDO2 methods. Custom strengths can narrow a policy further, for example to specific FIDO2 key models by AAGUID. You can’t use “require multifactor authentication” and “require authentication strength” in the same policy.

### The policy set

The program’s baseline policies. Every policy excludes the break-glass group from policies that block or restrict sign-in; “All users” means all users minus that group.

## The full library is in Book 04

Book 04, Chapter 07 is the program’s authoritative Conditional Access library. It keeps these identifiers, adds CA018–CA038 for the CISA BOD 25-01 Entra ID baseline, and revises three policies here: privileged-access-workstation enforcement moves from CA004’s device filter to its own block policy, CA025, because a grant policy scoped by a device filter simply doesn’t apply on other devices; CA013 takes a block form in BOD 25-01 tenants; and CA017 requires an app protection policy only, because Microsoft made the “approved client app” grant read-only on June 30, 2026.

| Policy | Persona | Conditions | Grant controls | Session controls |
| --- | --- | --- | --- | --- |
| CA001-AllUsers-BlockLegacyAuth | All users | Client apps: Exchange ActiveSync, other clients | Block | — |
| CA003-Admins-RequirePhishResistantMFA | Admins | All resources, any location | Authentication strength: phishing-resistant MFA | Sign-in frequency: 4 hours |
| CA004-Admins-RequireCompliantDevice | Admins | All resources | Require compliant device (a privileged access workstation; see Chapter 10) | Persistent browser: never |
| CA005-Admins-BlockUntrustedLocations | Admins | All resources, outside trusted networks | Block | — |
| CA006-Internals-RequireMFA | Internals | All resources | Authentication strength: MFA (phishing-resistant as the end state) | Sign-in frequency: 12 hours |
| CA007-Internals-RequireCompliantOrHybridDevice | Internals | All resources | Compliant device or hybrid joined device | — |
| CA008-Internals-BlockNonUSLocations | Internals | All resources, outside trusted countries | Block | — |
| CA009-Externals-RequireMFA | Externals | All resources | Authentication strength: MFA | Sign-in frequency: 8 hours |
| CA010-Externals-RequireTermsOfUse | Externals | All resources | Terms of use accepted | — |
| CA011-Guests-LimitedAppAccess | Guests | Selected apps only (SharePoint, Teams) | MFA and terms of use | App-enforced restrictions; sign-in frequency: 1 hour |
| CA012-Guests-BlockHighRisk | Guests | Sign-in risk: high | Block | — |
| CA013-AllUsers-HighUserRisk-RequireRemediation | All users | User risk: high | Require risk remediation | Sign-in frequency: every time (applied automatically) |
| CA014-AllUsers-MediumSigninRisk-RequireMFA | All users | Sign-in risk: medium or high | Authentication strength: MFA | Sign-in frequency: every time |
| CA015-ServiceAccounts-LocationRestriction | Service accounts | Workload identities, outside trusted networks | Block | — |
| CA016-AllUsers-RequireCompliantDevice-OfficeApps | All users | Office 365 apps on Windows and macOS | Require compliant device | — |
| CA017-Internals-AppProtection-Mobile | Internals | Office 365 apps on iOS and Android | Require app protection policy | — |

Three changes from the earlier version of this set reflect current Microsoft guidance:

- CA002 is gone. The earlier set had a “break-glass, grant with no controls” policy. A Conditional Access policy can’t create an exemption; the exemption is the exclusion on every other policy. The number is retired so the others keep their identifiers.

- CA013 uses risk remediation. Microsoft now recommends “require risk remediation” for high user risk. It handles both password and passwordless users, applies an authentication strength and sign-in frequency of every time automatically, and takes precedence over the older “require password change” control. It requires P2, and it isn’t supported for guests, so guests are handled by CA012.

- CA012 targets sign-in risk. The earlier version targeted user risk for guests. Risk remediation isn’t supported for external and guest users, because Entra ID can’t revoke their sessions, so the program blocks risky guest sign-ins instead.

Leaked-credential detection itself is available without P2, but its full reporting and the risk-based policies above require P2, and the detection needs PHS.

### Testing and rollout

Conditional Access deployment follows three stages:

- Report-only (2 to 4 weeks). Deploy every policy in report-only mode. Use the Conditional Access insights workbook to find the users and sign-ins each policy would affect, and fix false positives, such as users without MFA registration or non-compliant devices.

- Targeted pilot (2 weeks). Turn policies on for a pilot group, such as the IT department. Watch help desk volume and sign-in failure rates, and adjust conditions.

- Phased rollout (4 to 8 weeks). Expand in waves: IT and security teams, then corporate staff, then field and remote workers, then everyone. Each wave runs one to two weeks behind a monitoring gate.

## Never enforce untested policies on all users

Never switch a policy that targets all users from off straight to on. A misconfigured policy can lock out the whole organization, administrators included. Before enforcing any policy, confirm the break-glass exclusion group is excluded, and confirm both emergency accounts can still sign in.

## Continue the book

← Previous: Chapter 08 — Assessing the Forest · Book index · Next: Chapter 10 — Migrating and Governing →

# Chapter 10 — Migrating and Governing

The migration ends when governance runs on its own: when joiners, movers, and leavers flow from the HR record without a ticket, every privileged session starts with a phishing-resistant credential, and drift shows up in a diff instead of an incident.

## In this chapter

The governance machinery of the target: access reviews, access packages, and Lifecycle Workflows. Cross-tenant collaboration and how it replaces forest trusts. Authentication modernization toward phishing-resistant MFA, checked against OMB M-22-09 and NIST SP 800-53 Rev. 5. Monitoring and the compliance evidence it produces, the eleven-phase migration playbook, Git-based drift detection, and a troubleshooting reference. It builds on the target designed in Chapter 09.

## Identity governance and lifecycle

Governance in Active Directory was mostly a ticket queue: someone asked for group membership, someone else added it, and nobody took it away. The target replaces that with three Entra ID Governance capabilities that work as a loop. HR-driven provisioning creates and updates the account; Lifecycle Workflows run the joiner, mover, and leaver tasks; access packages grant access with an expiry; and access reviews remove what’s no longer justified.

The governance loop: the HR record drives provisioning, Lifecycle Workflows run joiner, mover, and leaver tasks, access packages grant access, and access reviews remove what reviewers deny.

The licensing for all three is covered in Chapter 09: Lifecycle Workflows need Entra ID Governance, and access reviews and entitlement management need it for the member users involved.

### Access reviews

Access reviews are periodic attestation that people still need the access they hold. The program’s schedule (the full access-governance design is in Book 04, Chapter 09):

| Review target | Frequency | Reviewers | Apply results automatically | If reviewers don’t respond |
| --- | --- | --- | --- | --- |
| PIM-eligible role assignments | Quarterly | The security team (Microsoft’s self-review option leaves role-assignable groups out of the review, so it can’t be the only reviewer) | Yes; remove if denied | Remove access |
| Sensitive security group memberships | Quarterly | Group owners | Yes; remove if denied | Remove access |
| Application assignments (Tier 1 apps) | Semi-annually | Application owners | Yes; remove if denied | No change; escalate |
| Guest access | Quarterly | Sponsors | Yes; disable if denied | Disable the guest account |
| Microsoft 365 group memberships | Semi-annually | Group owners | No (recommendations only) | No change |

The quarterly review of privileged roles is also the program’s evidence for NIST SP 800-53 AC-6(7) (see The compliance amendment). Reviews of PIM for Groups membership, and reviews scoped to inactive users, require Entra ID Governance.

### Entitlement management and access packages

Access packages bundle resources (group memberships, application assignments, SharePoint site access) into units that people request, approvers approve, and policies expire. They replace “submit a ticket for group membership” with a governed, self-service workflow. The program uses four categories:

- Onboarding packages. Baseline access for new hires: email, Teams, the intranet site, company-wide groups. Assigned by a Lifecycle Workflow on the hire date, or by an automatic assignment policy.

- Department packages. Department resources (SharePoint sites, Teams channels, line-of-business applications), assigned from the department attribute through an automatic assignment policy.

- Project packages. Time-bound access for a project, approved by the project lead and set to expire at the project end date.

- Cross-tenant packages. Resources shared with partner organizations through B2B collaboration, with terms of use acceptance and sponsor approval.

Expiration of assignments and separation-of-duties checks work with P2; automatic assignment policies, custom extensions, and Verified ID checks need Entra ID Governance. Avoid the preview memberOf operator in automatic assignment rules; Microsoft is ending that preview on November 3, 2026, after which those policies stop updating. Where an access package must grant access to an AD-integrated (Kerberos) application, include a cloud security group that Cloud Sync provisions to AD.

### Lifecycle Workflows

Lifecycle Workflows automate joiner, mover, and leaver tasks. They act on accounts that already exist; HR-driven inbound provisioning creates and updates the account. A workflow runs when a user meets its execution conditions, a trigger plus a scope. The triggers available as of October 2026 are a time-based attribute, an attribute change, a group membership change, sign-in inactivity, and on-demand. Time-based joiner and leaver workflows key on the native employeeHireDate and employeeLeaveDateTime attributes (or createdDateTime for joiners); the offset can be 0 to 180 days before or after the date, and a preview “V2” trigger extends that to 365 days with relative comparisons. Custom attribute triggers are in preview.

For users synced from Active Directory, those date attributes must be synced to Entra ID before the workflow can use them, and attribute-change and group triggers fire only after the sync cycle delivers the change. The canonical HR-driven design, including where the dates come from, is in HR-Driven Identity, Chapter 6. Scope rules can filter on standard attributes such as department and jobTitle and on extensionAttribute1 through 15. A tenant can have up to 50 workflows and 100 custom task extensions.

The workflows below use Microsoft’s built-in tasks where they exist. Steps that have no built-in task, marked “custom,” run through a custom task extension, which calls an Azure Logic App, or through a separate service.

#### Pre-hire workflow

Trigger: employeeHireDate, 7 days before. Based on Microsoft’s “Onboard pre-hire employee” template.

- Confirm the account exists, disabled. Inbound provisioning created it and set the HR attributes; Lifecycle Workflows don’t create accounts.

- Request the baseline onboarding access package (“Request user access package assignment”).

- Generate a Temporary Access Pass and email it to the user’s manager (“Generate TAP and send email”). The new hire uses it to register a phishing-resistant credential on day one.

- Send the hiring manager the onboarding checklist (custom, or the TAP email’s custom text).

#### Joiner workflow

Trigger: employeeHireDate, on the day. Based on the “Onboard new hire employee” template.

- Enable the user account (“Enable user account”; for synced users the task has an option to enable the on-premises account).

- Assign licenses through group-based licensing, or with the “Assign licenses to user” task, which is in preview.

- Let dynamic group membership take effect (department, region, and role groups).

- Send the welcome email with self-service portal links (“Send welcome email”).

- Request the department access package.

Prompting the user to register Authenticator or a passkey isn’t a workflow task. It’s a registration campaign in the Authentication methods policy (see Authentication methods policy).

#### Mover workflow

Trigger: an attribute change on department, division, or role. The program carries these in department, extensionAttribute3, and extensionAttribute4; confirm the attribute you choose is supported as a trigger attribute before relying on it. Based on the “Employee job profile change” template.

- Remove the previous department’s access package assignment (“Remove access package assignment for user”).

- Request the new department’s access package.

- Let dynamic group membership adjust to the new attributes.

- Start an access review of the user’s remaining non-baseline assignments (custom; or rely on the next scheduled review).

- Let a dynamic administrative unit rule move the user to the new division’s AU, if the division changed.

- Notify the previous and new managers (“Send email to notify manager of user move” covers the new manager; the previous manager is custom).

- Commit the attribute change record to the Git audit trail (custom).

#### Leaver workflow

Trigger: employeeLeaveDateTime, on the day, followed by a post-offboarding workflow. Based on the “Offboard an employee” and “Post-Offboarding of an employee” templates.

- Disable the user account (“Disable user account”).

- Revoke all refresh and browser session tokens (“Revoke all refresh tokens for user”; the Graph equivalent is Revoke-MgUserSignInSession).

- Remove all access package assignments and cancel pending requests.

- Remove all licenses (“Remove all licenses for user”), after the mailbox step below.

- Convert the mailbox to a shared mailbox, retained per policy (typically 90 days), and grant the manager access (custom; an Exchange Online operation, not a Lifecycle Workflows task).

- Move the user to the “Departed users” administrative unit, most simply with a dynamic AU rule on accountEnabled.

- At T+30 days, remove all group and Teams memberships (“Remove user from all groups,” “Remove user from all Teams”).

- At T+90 days, delete the account (“Delete user”).

- Notify the manager, HR, and security operations (“Send email on user’s last day,” plus custom recipients).

Two cautions. The “Delete user” task doesn’t support users with Entra role assignments or with membership or ownership of role-assignable groups, so remove privileged access first. And a synced user deleted only in the cloud comes back on the next sync; for synced users, delete the account in Active Directory, using the on-premises options Microsoft documents for synced users.

### Terms of use

Terms of use record compliance attestation and are enforced through Conditional Access; the feature needs Entra ID P1. The program uses three:

- Employee terms of use. Re-accepted annually: acceptable use, data handling, security responsibilities.

- Guest and external terms of use. Accepted on first access and quarterly after: data sharing terms and compliance boundaries.

- Privileged access terms of use. Accepted before activating Global Administrator, acknowledging the extra monitoring. Enforce it through the authentication context that PIM requires at activation.

## Cross-tenant and B2B collaboration

### B2B collaboration

B2B collaboration lets external users access resources in your tenant as guest users. The guest lifecycle has five steps:

- Invitation. Sent by an authorized internal sponsor, or generated when a partner user’s access package request is approved.

- Redemption. The guest redeems the invitation with home tenant credentials or another supported identity provider.

- Access. Governed by group memberships, application assignments, and Conditional Access, like any other user.

- Review. Quarterly review by the sponsor (see the access review schedule above).

- Offboarding. Disabled or removed when collaboration ends. Guests added through entitlement management are removed automatically when their last assignment expires.

The program’s invitation policies:

- Only users with the Guest Inviter role or higher can invite guests.

- Invitations are limited to an allowlist of partner domains. This is a program setting; B2B collaboration supports allowlists and blocklists.

- Self-service sign-up stays off, except for approved applications and identity providers.

- Invitations across Microsoft clouds (for example, from a GCC High tenant into a commercial or GCC tenant) must use the user’s UPN, not an email address.

### Cross-tenant access settings

Cross-tenant access settings govern the relationship between your tenant and other Microsoft Entra tenants. By default, B2B collaboration with all other Entra organizations is allowed and B2B direct connect is blocked; organization-specific settings override the defaults.

| Setting | Inbound (external users into your tenant) | Outbound (your users into other tenants) |
| --- | --- | --- |
| B2B collaboration | Allowed for all by default; the program restricts it to an allowlist of partners | Allow your users to be guests in specific external tenants |
| B2B direct connect | Blocked by default; enable per partner for Teams shared channels | Allow your users into a partner’s shared channels |
| Trust settings | Trust MFA, compliant device, and hybrid joined device claims from the partner tenant | Not applicable |
| Automatic redemption | Suppress the consent prompt for a trusted partner | Same, in the other direction |

Trusting a partner’s MFA claims means your Conditional Access MFA requirements are still enforced, but a user who already completed MFA at home isn’t prompted again. For organizations that run several tenants of their own, cross-tenant synchronization creates and maintains B2B users across them automatically; syncing users within the same cloud needs P1, and syncing groups or syncing across clouds needs Entra ID Governance.

### B2B direct connect and B2B collaboration compared

| Criterion | B2B collaboration | B2B direct connect |
| --- | --- | --- |
| Guest object in your tenant | Yes | No; the user signs in with home credentials and has no directory object |
| Scope | Any application your Conditional Access governs | Microsoft Teams shared channels only |
| Setup | Your tenant’s settings | Both tenants must enable it mutually |
| Governance visibility | Full: directory object, access reviews, sign-in logs | Limited: managed in the application by channel owners |
| Conditional Access | Applies fully | Applies, but needs inbound MFA trust if your policies require MFA |
| Program position | Preferred for sharing resources and applications | Acceptable for Teams-only collaboration with trusted partners |

### External identity providers

For guests from organizations that don’t use Entra ID, B2B collaboration supports:

- Microsoft accounts, built in.

- Google federation, for Google Workspace users.

- SAML/WS-Fed identity provider federation, for partners with a non-Microsoft enterprise identity provider.

- Email one-time passcode, the fallback for guests who can’t use any of the above. It’s on by default in new tenants. Conditional Access authentication strengths can’t be applied to these guests; use the “require MFA” grant control instead.

### Mapping AD trusts to cross-tenant access

Forest and external trusts don’t migrate; each becomes a cross-tenant or federation configuration. The trust inventory itself comes from Chapter 08. The equivalences are the program’s design:

| AD trust type | Entra ID equivalent | Migration approach |
| --- | --- | --- |
| Two-way forest trust | Cross-tenant access settings, inbound and outbound | Configure both tenants; trust MFA |
| One-way forest trust (incoming) | Inbound cross-tenant access for the partner tenant | Configure inbound B2B collaboration |
| External trust (domain-level) | Organization-specific cross-tenant settings | Configure per-organization settings |
| Realm trust (Kerberos) | SAML/WS-Fed federation with the external identity provider | Establish federation |

## Authentication modernization

### Password hash sync as the foundation

Whatever the sign-in method, password hash sync (PHS) stays on. It gives three things the other methods don’t:

- Leaked-credential detection. ID Protection checks synced credentials against leaked credential lists. The detection itself isn’t a premium feature, but its full reporting and risk-based Conditional Access require P2.

- A fallback. If pass-through agents or AD FS fail, an administrator can switch the sign-in method to PHS. The switch is manual.

- Cloud smart lockout, which protects against password spray in the cloud without locking the on-premises account.

### The phishing-resistant authentication roadmap

OMB M-22-09 requires phishing-resistant MFA for agency staff, contractors, and partners, and requires that it be an option for public users. For routine self-service access, agencies must stop supporting methods that fail to resist phishing, including SMS or voice codes, one-time codes, and push notifications. It names PIV (including derived PIV) as the simplest route and allows FIDO2 and WebAuthn authenticators where PIV isn’t practical, and it notes that OMB M-19-17 makes PIV the primary means of authentication to federal systems. The memo set its targets for the end of fiscal year 2024, so as of October 2026 these are requirements to meet, not goals to plan toward.

That changes the order of the program’s roadmap. The earlier version treated certificate-based authentication for smart cards as the last phase, for “high-security users.” For a federal workforce that already carries PIV or CAC cards, Microsoft Entra certificate-based authentication (CBA) is the fastest path to phishing-resistant MFA, because the credential is already issued. CBA supports PIV, CAC, and derived PIV credentials directly against Entra ID, without a federation server.

| Phase | Population | Method | Prerequisites | Duration (program estimate) |
| --- | --- | --- | --- | --- |
| 1 | Privileged accounts (PIM-eligible users) | FIDO2 security keys (passkeys), plus PIV/CAC through CBA where the admin holds a card | Keys procured; passkey profile with attestation enforced; CBA trusted certificate authorities configured | 4–6 weeks |
| 2 | PIV and CAC holders | Microsoft Entra certificate-based authentication | Certificate authorities and revocation checking configured; username bindings validated; workbook PKI material | 8–12 weeks |
| 3 | Managed Windows devices | Windows Hello for Business | Intune enrollment; Windows Hello for Business policy; TPM 2.0 | 8–12 weeks |
| 4 | Remaining users, including mobile | Passkeys in Microsoft Authenticator | Android 14 or iOS 17 or later; a passkey profile targeting the Authenticator AAGUIDs; registration campaign | 8–12 weeks |

All four methods meet the built-in phishing-resistant MFA authentication strength (passkeys in Authenticator count as FIDO2 passkeys). Passkey profiles let you set different rules for different groups; for example, device-bound passkeys with attestation enforced for administrators, and synced passkeys allowed for lower-risk populations.

### Authentication methods policy

The Authentication methods policy decides which methods are available to which users. The program’s configuration:

- Passkeys (FIDO2). Enabled for the Admins group in phase 1, then all users. Use passkey profiles: device-bound with attestation enforced for privileged users. Users must have completed MFA within the past five minutes before they can register a passkey.

- Certificate-based authentication. Enabled for PIV and CAC holders in phase 2, configured as multifactor so that it meets the phishing-resistant strength.

- Microsoft Authenticator. Enabled for all users during the transition. Number matching is always on for Authenticator push notifications and users can’t opt out. Turn on the additional context (application name and sign-in location). Authenticator push doesn’t satisfy M-22-09 for staff on its own; Microsoft’s guidance pairs it with managed-device Conditional Access during the transition.

- Windows Hello for Business. Enabled for all users on managed devices.

- Temporary Access Pass (TAP). Enabled for onboarding and credential replacement, issued by the help desk and by the pre-hire workflow. Microsoft’s defaults are a 1-hour default lifetime (configurable from 10 minutes to 30 days) and multi-use allowed; the program sets one-time use and a 1-hour lifetime. With a one-time TAP, the user has 10 minutes after sign-in to finish registering the new credential.

- SMS and voice. Disabled for staff. M-22-09 requires discontinuing them for routine access.

- Email one-time passcode. Guests only.

- Registration campaigns. On, to prompt users without a strong method to register one at sign-in. The program allows three snoozes.

### Blocking legacy authentication

Legacy protocols that send a username and password with each request can’t do MFA and are a common path for password spray and credential stuffing. Exchange Online has already removed Basic authentication for Exchange ActiveSync, POP, IMAP, Remote PowerShell, Exchange Web Services, the Offline Address Book, Autodiscover, and Outlook for Windows and Mac, and has disabled SMTP AUTH in tenants that weren’t using it. SMTP AUTH with Basic authentication is the remaining case; Microsoft has announced its retirement and updated the timeline, so check the current Exchange announcement before planning around a date.

The remediation sequence:

- Discover remaining legacy sign-ins with the sign-in logs, using the queries below or the “Sign-ins using legacy authentication” workbook.

- Remediate applications and devices onto modern authentication (OAuth 2.0), the Microsoft Graph mail APIs, or a supported relay.

- Block with policy CA001 from Chapter 09.

- Monitor for 30 days after enforcement and confirm zero successful legacy sign-ins.

## Illustrative code

The KQL and PowerShell in this chapter are illustrative. They haven’t been tested against a production tenant. Review them, check table and column names against your own Log Analytics workspace, and run them first against a test tenant with read-only permissions.

This query runs in a Log Analytics workspace that receives the Entra sign-in logs:

// Legacy authentication sign-in discovery, last 30 days, successful sign-ins only
SigninLogs
| where TimeGenerated > ago(30d)
| where ClientAppUsed in (
    "Exchange ActiveSync", "Authenticated SMTP", "POP3", "IMAP4", "AutoDiscover",
    "Exchange Online PowerShell", "Exchange Web Services", "MAPI Over HTTP",
    "Offline Address Book", "Other clients", "Outlook Anywhere (RPC over HTTP)",
    "Reporting Web Services")
| where ResultType == 0
| summarize SignInCount = count(), LastSignIn = max(TimeGenerated)
    by ClientAppUsed, AppDisplayName, UserPrincipalName
| order by SignInCount desc

Without a workspace, the same question can be asked through Microsoft Graph PowerShell. The Get-FMPLegacyAuthReport function in Appendix C wraps this pattern and adds a suggested remediation per client type.

#Requires -Modules Microsoft.Graph.Reports
Connect-MgGraph -Scopes 'AuditLog.Read.All'

$legacyClients = @('Exchange ActiveSync', 'Authenticated SMTP', 'POP3', 'IMAP4', 'Other clients')
$startDate = (Get-Date).ToUniversalTime().AddDays(-30).ToString('yyyy-MM-ddTHH:mm:ssZ')
$filter = "createdDateTime ge $startDate and status/errorCode eq 0"

$signIns = Get-MgAuditLogSignIn -Filter $filter -All |
    Where-Object { $_.ClientAppUsed -in $legacyClients }

$signIns |
    Group-Object -Property UserPrincipalName, ClientAppUsed |
    Select-Object @{N = 'User';       E = { ($_.Name -split ', ')[0] } },
                  @{N = 'ClientApp';  E = { ($_.Name -split ', ')[1] } },
                  @{N = 'Count';      E = { $_.Count } },
                  @{N = 'LastSignIn'; E = { ($_.Group | Sort-Object CreatedDateTime -Descending |
                                              Select-Object -First 1).CreatedDateTime } } |
    Sort-Object Count -Descending |
    Format-Table -AutoSize

Disconnect-MgGraph

The Graph sign-ins API covers interactive sign-ins; legacy clients usually appear there, but the workspace query sees more. In a large tenant, narrow the date range rather than pulling 30 days at once.

## The compliance amendment: phishing-resistant authenticators and privileged access

This section maps the authenticators and privileged-access controls above to the federal requirements they answer. Control text is from NIST SP 800-53 Rev. 5 as published in FedRAMP’s catalog (release 5.2.0).

### Multifactor authentication and separate devices (IA-2)

- IA-2(1) and IA-2(2) require MFA for access to privileged and non-privileged accounts. FedRAMP’s guidance adds that the MFA must be phishing-resistant, per current CISA guidance.

- IA-2(6), Access to Accounts — Separate Device, requires MFA for local, network, or remote access to privileged or non-privileged accounts such that one factor is provided by a device separate from the system gaining access, and the device meets organization-defined strength-of-mechanism requirements. FedRAMP sets the parameters to local, network, and remote access for both privileged and non-privileged accounts, and its guidance treats a PIV card as the separate device.

The earlier version of this section described IA-2(6) as “access to privileged accounts using a hardware-based authenticator.” That isn’t the control’s wording; the requirement is a separate device meeting a stated strength of mechanism. The program maps authenticators as follows:

- PIV and CAC smart cards through Entra certificate-based authentication are separate devices and the federal standard credential. They’re the program’s primary answer to IA-2(6) for staff who hold them.

- FIDO2 security keys are roaming authenticators separate from the computer gaining access. They’re the primary method for cloud administrators and for staff without a card. Microsoft notes that hardware security keys carrying certificates also meet the requirement for MFA on a separate device.

- Windows Hello for Business and platform passkeys are phishing-resistant, but the key lives in the device that’s gaining access. The program doesn’t count them toward IA-2(6) for privileged accounts; it uses them for non-privileged access, where the organization’s assessor accepts that.

- Passwords, SMS, and voice aren’t allowed for privileged roles.

The FedRAMP 20x Key Security Indicator for this area, KSI-IAM-APM (Adopting Passwordless Methods), states the same direction: passwordless methods where feasible, otherwise strong passwords with phishing-resistant MFA.

### Reviewing privileged access (AC-6(7))

The earlier version of this section mapped AC-6(7) to privileged access workstations. That was wrong. AC-6(7), Review of User Privileges, requires the organization to review, at a defined frequency, the privileges assigned to defined roles and classes of users to validate the need for them, and to reassign or remove privileges as necessary. The program meets it with the quarterly PIM access reviews in the access review schedule, which remove privileges that reviewers deny, and with the 12-month expiry on eligible assignments from Chapter 09. The review results and the PIM audit log are the evidence.

### Privileged access workstations

Privileged access workstations (PAWs) are still part of the design; they just answer different requirements. A PAW is a hardened, separately managed device with no general productivity or browsing surface, used only for administration. Microsoft’s guidance builds them with Intune and Windows Autopilot, identifies them with a dynamic device group, and enforces their use with Conditional Access device filters and compliance requirements. The program’s standard:

- Administration of privileged roles happens only from a PAW.

- PAWs are Intune-managed from first boot, provisioned through Autopilot, and identified by a dynamic device group.

- Conditional Access policy CA004 requires a compliant device for the Admins persona, and block policy CA025 in Book 04, Chapter 07 restricts administrator sign-in to the PAW group; protected actions require the same authentication context.

- Administrative sign-ins from any other device are blocked.

## Monitoring, audit, and compliance

### The Entra ID logs

Entra ID’s activity logs are kept for a short time in the service itself. As of October 2026:

| Log | Content | Retention in Entra ID | Program retention in Log Analytics |
| --- | --- | --- | --- |
| Sign-in logs | Interactive, non-interactive, service principal, and managed identity sign-ins | 7 days (Free); 30 days (P1, P2) | 365 days |
| Audit logs | Directory changes: users, groups, roles, policies, application registrations | 7 days (Free); 30 days (P1, P2) | 365 days |
| Provisioning logs | Provisioning to and from applications and directories | See Microsoft’s retention reference | 180 days |
| Risky sign-ins | ID Protection risk detections on sign-ins | 7 days (Free); 30 days (P1); 90 days (P2) | 365 days |
| Risky users | Users at risk | Kept until the risk is remediated | 365 days |
| Microsoft Graph activity logs | API calls to Microsoft Graph | Not retained; P1 or P2, export only | 180 days |

Upgrading licenses doesn’t recover older data: after moving from Free to P1, only the last seven days are available. Route the logs to a workspace before you need them.

### Log Analytics integration

All Entra ID logs go to a Log Analytics workspace for retention, correlation, and detection:

- Create a Log Analytics workspace in an Azure subscription. This is an Azure resource and the documented exception to the program’s Microsoft 365 boundary.

- In Entra ID diagnostic settings, stream every log category to the workspace. You need at least Security Administrator in the tenant and access to the workspace.

- Set workspace retention to 365 days, or longer if the authorization requires it.

- Create scheduled query rules for the detections below.

Integrating the logs with Azure Monitor also enables the Microsoft Entra data connector for Microsoft Sentinel, if the program uses it.

### Detection rules

| Detection | Description | Query pattern | Severity | Response |
| --- | --- | --- | --- | --- |
| Stale accounts | No sign-in for more than 90 days | Graph signInActivity/lastSignInDateTime (needs P1 and AuditLog.Read.All); sign-in logs alone miss users who never signed in during retention | Medium | Flag for access review; disable if confirmed unused |
| PIM activation outside business hours | Role activated between 22:00 and 06:00 local time, or at a weekend | AuditLogs \¦ where OperationName == "Add member to role completed (PIM activation)" \¦ extend Hour = hourofday(TimeGenerated) (convert from UTC to local time first) | High | Investigate; review the justification |
| Sign-ins with no Conditional Access applied | Interactive sign-ins that no policy covered | SigninLogs \¦ where ConditionalAccessStatus == "notApplied", or the Conditional Access gap analyzer workbook | Medium | Close the coverage gap |
| Expiring application credentials | Secrets or certificates expiring within 30 days | Microsoft Graph list of applications, filtered client-side on passwordCredentials and keyCredentials end dates | High | Notify owners; rotate or replace with federated credentials |
| Emergency account sign-in | Any sign-in by an emergency access account | SigninLogs \¦ where UserPrincipalName in ("<ea1>@<tenant>.onmicrosoft.com", "<ea2>@<tenant>.onmicrosoft.com") | Critical | Immediate incident response |
| Mass group membership change | More than 50 members added or removed from one group in an hour | AuditLogs \¦ where OperationName in ("Add member to group", "Remove member from group") \¦ summarize count() by bin(TimeGenerated, 1h), <group> (check which TargetResources entry holds the group in your logs) | High | Confirm the change was authorized |

The PIM activation operation name comes from Microsoft’s audit activity reference, which lists “Add member to role completed (PIM activation)” under the RoleManagement category. Microsoft’s security operations guide recommends alerting on every elevation that falls outside a user’s normal pattern.

### Workbooks

Microsoft Entra workbooks need the Log Analytics integration above. The program uses these public templates:

- Conditional Access insights and reporting: policy impact, report-only analysis, failure reasons by policy.

- Conditional Access gap analyzer: sign-ins, applications, and locations that no policy covered.

- Sign-ins using legacy authentication.

- Multifactor authentication gaps and Authentication prompts analysis.

- Sensitive operations report: privileged role changes, policy changes, and credential changes on applications.

- Risk analysis and Cross-tenant access activity.

### Compliance Manager and the FedRAMP 20x indicators

Microsoft Purview Compliance Manager has regulation templates for NIST SP 800-53 Rev. 5, FedRAMP Moderate, and CMMC; GCC tenants get CMMC included alongside the default data protection baseline, and the others are premium templates. The identity controls in this book map to these families:

- AC-2 (Account Management): Lifecycle Workflows and access reviews.

- AC-6 (Least Privilege): PIM and attribute-based group access (Chapter 09); AC-6(7) through privileged access reviews.

- IA-2 (Identification and Authentication): Conditional Access, authentication strengths, and the phishing-resistant roadmap.

- IA-5 (Authenticator Management): the Authentication methods policy and service principal credential rotation.

- AU-2 (Event Logging): Log Analytics integration and the detection rules.

Under FedRAMP 20x, the Consolidated Rules for 2026 (launched June 24, 2026) express these as Key Security Indicators, which are what a 20x package evidences. Compliance Manager’s templates follow the Rev. 5 control structure and don’t produce indicator evidence, so use them as a readiness check, not the deliverable.

| Controls | FedRAMP 20x indicator | Where in this book |
| --- | --- | --- |
| AC-2 | KSI-IAM-AAM, Automating Account Management | Lifecycle Workflows; access reviews |
| AC-6 | KSI-IAM-ELP, Ensuring Least Privilege; KSI-IAM-JIT, Authorizing Just-in-Time | Chapter 09 groups and PIM |
| IA-2, IA-5 | KSI-IAM-APM, Adopting Passwordless Methods | Authentication strengths; the roadmap; the Authentication methods policy |
| IA-5 (non-user) | KSI-IAM-SNU, Securing Non-User Authentication | Chapter 09 service account modernization |
| AU-2 | KSI-MLA-LET, Logging Event Types; KSI-MLA-RVL, Reviewing Logs | Log Analytics integration; detection rules |

The indicator IDs and titles are from FedRAMP’s published indicator pages. The control-to-indicator mapping is the program’s.

## The migration execution playbook

The migration runs in eleven phases, grouped into five waves. Each phase has prerequisites, steps, validation criteria, a rollback procedure, and a duration estimate. Phases run in order: a phase’s validation criteria must be met before the next begins. The durations are the program’s planning estimates, not measured results; the total runs 40 to 70 weeks.

The eleven playbook phases in five waves: foundation, objects, privilege and policy, authentication, and sustain.

### Phase 0: Assessment

| Element | Detail |
| --- | --- |
| Prerequisites | Read access to the forest; the Git repository provisioned; the program’s PowerShell modules installed |
| Steps | 1. Run Invoke-FMPADAssessment (Chapter 07 and Chapter 08) to inventory the forest. 2. Run Export-FMPIdentityBaseline (Appendix C) for user, group, and service account inventories. 3. Find UPN suffix mismatches and non-routable suffixes. 4. Map the OU structure to proposed administrative units. 5. Document every trust for cross-tenant planning. 6. Commit the assessment output (JSON) to Git. |
| Validation | Complete inventory in Git; UPN remediation plan documented; a recorded decision for every group; service account risk classification complete |
| Rollback | Not applicable; assessment is read-only |
| Duration | 2–4 weeks |

### Phase 1: Sync deployment and initial sync

| Element | Detail |
| --- | --- |
| Prerequisites | Phase 0 complete; the sync engine chosen (Chapter 09); servers built to the workbook’s server standards; OU scoping finalized; UPN remediation complete; soft and hard match blocks reviewed |
| Steps | 1. Deploy Cloud Sync agents (at least two), or install Connect Sync where a Connect-only requirement applies. 2. Configure OU scoping. 3. Configure attribute mappings. 4. Enable PHS, even if PTA or federation is primary. 5. For Connect Sync, run the initial sync in staging mode and check object counts and attribute mapping; for Cloud Sync, test with on-demand provisioning. 6. Enable export after validation. 7. For Connect Sync, build the staging-mode standby server. 8. Commit the sync configuration export to Git. |
| Validation | Object counts in Entra ID match the expected count (±1%); no sync errors; attribute spot-check (10 users, 5 groups) correct; standby verified |
| Rollback | Stop sync; remove the synced objects from scope (they’re soft-deleted and recoverable for 30 days); reconfigure from a clean state. Don’t hard-delete during rollback. |
| Duration | 2–3 weeks |

### Phase 2: Sign-in method and Conditional Access in report-only

| Element | Detail |
| --- | --- |
| Prerequisites | Phase 1 complete; emergency access accounts created with passkeys; Conditional Access policies drafted |
| Steps | 1. Confirm PHS is active. 2. If PTA is kept for now, deploy at least three agents. 3. Configure Seamless SSO only for devices that are domain joined but not hybrid joined or Entra joined; Entra joined and hybrid joined devices already get single sign-on. 4. Deploy every Conditional Access policy in report-only mode. 5. Create the break-glass exclusion group and confirm it’s excluded from every policy. 6. Watch the Conditional Access insights workbook for 2–4 weeks. 7. Fix users and devices the policies would block. |
| Validation | PHS verified (a test password change propagates); PTA agents healthy; every policy shows the expected impact in report-only; an emergency account sign-in tested and logged |
| Rollback | Remove PTA agents; return to PHS; set the policies off |
| Duration | 3–4 weeks |

### Phase 3: Group migration and dynamic group conversion

| Element | Detail |
| --- | --- |
| Prerequisites | Phase 2 complete; group decisions final (Chapter 09); extension attributes populated at the source |
| Steps | 1. Create dynamic groups. 2. Validate dynamic membership against the expected populations. 3. Create cloud-only security groups for the groups marked cloud-only. 4. Move resource assignments from synced groups to cloud groups, in phases. 5. Apply Microsoft 365 group governance (naming, expiration, labels). 6. Configure self-service group management. 7. Configure Cloud Sync group provisioning to AD for cloud groups that still guard Kerberos applications. 8. Retire AD groups that are fully migrated. |
| Validation | Dynamic groups contain the expected members (±2%); resource access unchanged after migration; no help desk tickets attributable to group changes |
| Rollback | Reassign resources to the original synced groups; delete the cloud groups; restore AD groups from the recycle bin or backup |
| Duration | 4–6 weeks |

### Phase 4: Service account modernization

| Element | Detail |
| --- | --- |
| Prerequisites | Phase 3 complete; service account inventory classified (Chapter 09); application owners identified |
| Steps | 1. Convert HIGH-risk accounts first (password never expires, over-privileged). 2. Create workload identities: managed identities for Azure-hosted workloads, federated credentials for pipelines and other OIDC-capable hosts, certificates only where neither applies. 3. Configure Conditional Access for workload identities (single-tenant service principals). 4. Set credential rotation schedules and two human owners per application. 5. Run old and new credentials in parallel for 30 days, then disable the legacy accounts. |
| Validation | Every HIGH-risk account converted or retired; new identities authenticate without stored secrets where possible; no service disruption during the parallel run; workload identity policies enforced |
| Rollback | Re-enable the legacy accounts; revert application configuration |
| Duration | 6–8 weeks |

### Phase 5: PIM rollout

| Element | Detail |
| --- | --- |
| Prerequisites | Phase 4 complete; role mapping final (Chapter 09); every administrator registered for a phishing-resistant method |
| Steps | 1. Configure PIM role settings per the standards. 2. Convert every permanent active assignment to eligible, except the emergency accounts. 3. Configure PIM for Groups for resource-level just-in-time access. 4. Create quarterly access reviews for all eligible assignments. 5. Add protected actions for Conditional Access, cross-tenant settings, named locations, and hard deletion. 6. Train administrators on activation. 7. Watch the PIM audit log for the first two weeks. |
| Validation | Zero permanent active assignments except the emergency accounts; every administrator can activate; the first review cycle started; protected actions enforced |
| Rollback | Convert eligible assignments back to active, using an emergency account if activation fails |
| Duration | 2–3 weeks |

### Phase 6: Conditional Access enforcement

| Element | Detail |
| --- | --- |
| Prerequisites | Phase 5 complete; report-only analysis complete; MFA registration above 95% for each targeted population |
| Steps | 1. Turn policies on for wave 1 (IT and security teams). 2. Watch for a week; work the help desk tickets. 3. Wave 2 (corporate staff), one week. 4. Wave 3 (field and remote workers), one week. 5. Wave 4 (everyone remaining), two weeks. 6. Turn on the risk policies (CA013, CA014) once the baseline is stable. 7. Final check: every policy enforcing, no unintended blocks. |
| Validation | Every policy on; help desk volume back to baseline within a week of each wave; no reports of legitimate access blocked for more than an hour |
| Rollback | Set the affected policies back to report-only; fix; re-enable |
| Duration | 4–6 weeks |

### Phase 7: Phishing-resistant authentication

| Element | Detail |
| --- | --- |
| Prerequisites | Phase 6 complete; FIDO2 keys procured; CBA configured; Windows Hello for Business policy in Intune; Authenticator deployed |
| Steps | 1. FIDO2 keys and CBA for privileged accounts (roadmap phase 1). 2. CBA for PIV and CAC holders (phase 2). 3. Windows Hello for Business on managed Windows devices (phase 3). 4. Authenticator passkey registration campaign (phase 4). 5. Track registration in the authentication methods reports. 6. Raise Conditional Access authentication strengths to phishing-resistant as each population crosses its threshold. |
| Validation | 100% of privileged accounts on FIDO2 or CBA; more than 80% of managed-device users on Windows Hello for Business; more than 70% of all users on a phishing-resistant method; the remainder on a dated plan |
| Rollback | Lower the authentication strength to MFA for the affected population; keep the existing methods |
| Duration | 8–16 weeks |

### Phase 8: Legacy authentication cutoff

| Element | Detail |
| --- | --- |
| Prerequisites | Phase 7 complete or running in parallel; legacy discovery complete; every dependency remediated |
| Steps | 1. Confirm zero successful legacy sign-ins for 30 consecutive days. 2. Enforce CA001 if it isn’t already. 3. Confirm Basic authentication is off for every Exchange Online protocol; Microsoft has already removed it for most. 4. Disable SMTP AUTH on every mailbox except documented, approved exceptions, and move those to OAuth or a relay before Microsoft’s retirement date. 5. Monitor for 30 days. |
| Validation | Zero legacy sign-ins for 30 days after enforcement; no disruption; every exception documented and approved |
| Rollback | Re-enable SMTP AUTH for a specific mailbox if a critical dependency appears; file an exception and a remediation plan |
| Duration | 2–4 weeks |

### Phase 9: Federation decommission (if applicable)

| Element | Detail |
| --- | --- |
| Prerequisites | Phase 8 complete; PHS verified; every federated domain identified; staged rollout tested |
| Steps | 1. Use staged rollout to move users from federation to PHS in waves; staged rollout tests cloud authentication but doesn’t convert domains. 2. Wave 1: the IT team, one week. 3. Wave 2: a pilot group, two weeks. 4. Wave 3: everyone else. 5. Document and back up the federation settings (Get-MgDomainFederationConfiguration). 6. Convert each domain with Update-MgDomain -DomainId <domain> -AuthenticationType "Managed"; conversion can take up to 60 minutes per domain. The retired Convert-MsolDomainToStandard cmdlet must not be used. 7. Decommission AD FS (servers, Web Application Proxy, certificates). 8. Remove the AD FS DNS records. 9. Update documentation and the Git records. |
| Validation | Every domain managed; every user authenticating through PHS; AD FS decommissioned; no authentication failures from the cutover |
| Rollback | Re-federate the domain with New-MgDomainFederationConfiguration, which needs the AD FS infrastructure, so keep it recoverable for 90 days after decommission |
| Duration | 4–8 weeks |

### Phase 10: Steady-state governance

| Element | Detail |
| --- | --- |
| Prerequisites | All earlier phases complete |
| Steps | 1. Turn on the joiner, mover, and leaver workflows. 2. Configure the access packages. 3. Turn on every scheduled access review. 4. Deploy identity drift detection through Git. 5. Hold a weekly identity governance review. 6. Write and approve the steady-state operations runbook. |
| Validation | Every governance workflow running; access reviews producing results; drift alerts working; the runbook approved and committed to Git |
| Rollback | Not applicable; handle workflow problems individually |
| Duration | Ongoing; initial setup 2–4 weeks |

## Git-based drift detection

### The assessment pipeline

The identity assessment produces structured JSON inventories that go into Git, where version control turns them into a drift record. The program’s reference build uses Gitea; any Git host with an issues API works the same way.

- Run the assessment. Invoke-FMPIdentityAssessment produces JSON for users, groups, service accounts, privileged access, and legacy authentication.

- Commit. The output goes to the identity-baseline branch of the program’s configuration repository.

- Compare. Each later run is compared with the committed baseline. New objects, removed objects, and attribute changes are drift.

- Raise issues. Drift above a threshold opens an issue with the diff, a severity, and a recommended action.

The design rule is the same as in HR-Driven Identity, Chapter 9: close each finding at the source (fix the record or the rule), never by editing the copy.

### Scheduled tasks

| Task | Schedule (Eastern time) | Command | Output | Status |
| --- | --- | --- | --- | --- |
| Identity drift scan | Weekly, Sunday 02:00 | Invoke-FMPIdentityAssessment -Compare -PreviousBaselinePath <path> -CommitToGitea | Drift report JSON; an issue if drift is found | In the Appendix C module |
| PIM activation audit | Daily, 06:00 | Get-FMPPrivilegedAccessReport -Last24Hours | Privileged access report; review of off-hours activations | In the Appendix C module |
| Conditional Access policy export | Weekly, Sunday 03:00 | Export-FMPConditionalAccessPolicy | Policy JSON and a diff against the previous export | Planned; the export pattern is in Appendix C |
| Application credential audit | Weekly, Monday 06:00 | Get-FMPServicePrincipalCredentialReport -ExpiringWithin 30 | Expiring credentials; an issue per application | Planned |
| Stale account report | Monthly, 1st, 06:00 | Get-FMPStaleAccountReport -InactiveDays 90 | Stale account list; access review trigger | Planned |

The planned functions aren’t in the module yet. Until they are, run the equivalent steps by hand and commit the output; don’t schedule a command that doesn’t exist.

### Raising drift issues through the Git host’s API

Invoke-FMPIdentityAssessment -CommitToGitea calls New-FMPGiteaDriftIssue, which opens an issue through the Gitea REST API. Gitea’s API lives under /api/v1/, takes an API token in an Authorization: token <value> header, and accepts label IDs (integers) when creating an issue. The function, and the small helper that looks up label IDs by name, are in the module in Appendix C. The token comes from an environment variable on the scheduled-task host; keep it in a secret store, scope it to the one repository, and never commit it.

## Troubleshooting reference

| Symptom | Likely cause | Resolution | Prevention |
| --- | --- | --- | --- |
| Sync error InvalidSoftMatch | A soft match on UPN or primary SMTP address found a cloud object that already has a different onPremisesImmutableId, usually because it was synced from another AD object, or two AD objects share a UPN or proxy address | Find the duplicate. If it’s the same person being re-provisioned, set the AD object’s mS-DS-ConsistencyGuid to the value matching the cloud object’s ImmutableId so a hard match succeeds | Clean duplicate UPNs and proxy addresses in Phase 0; keep soft and hard match blocked outside planned matching windows |
| Sync error InvalidHardMatch | Since July 1, 2026, Entra ID blocks a hard match to a cloud account that already has onPremisesObjectIdentifier set or holds or is eligible for a privileged role, or the tenant blocks hard-match takeover | Don’t take over privileged cloud accounts by sync. For a legitimate remap, clear onPremisesObjectIdentifier through Microsoft’s documented Graph recovery call, then retry | Keep administrators cloud-only; don’t sync AD accounts onto existing admin accounts |
| “Unable to update userPrincipalName” | The suffix isn’t a verified domain, or another object already uses the UPN | Verify the domain in the admin center; resolve the duplicate in AD or Entra ID | Verify every UPN suffix as a custom domain before sync; audit UPNs in Phase 0 |
| Cloud group not appearing in AD | Cloud Sync group provisioning isn’t configured for the group or target OU, or the group isn’t a cloud security group | Check the provisioning logs for the group; confirm the scoping and target OU | Configure group provisioning to AD before moving Kerberos applications onto cloud groups. (Connect Sync Group Writeback v2 is discontinued; don’t troubleshoot it, migrate off it.) |
| PIM activation fails: “user does not meet activation requirements” | The user hasn’t registered a method that satisfies the activation authentication context, or Conditional Access blocks the request | Register a phishing-resistant method; check the sign-in logs for the blocking policy | Require registration before granting eligibility; test activation in the pilot |
| Conditional Access blocks legitimate access | The user doesn’t meet a grant control (device compliance, location, MFA) | Find the blocking policy in the sign-in log’s Conditional Access tab; fix the specific condition | Report-only first; keep a documented exception process |
| Password writeback fails | Writeback not enabled, or the AD DS connector account lacks permissions | Enable writeback; grant Reset password, Change password, Write lockoutTime, and Write pwdLastSet on descendant user objects, and Unexpire Password on each domain root; Set-ADSyncPasswordWritebackPermissions sets the core set for Connect Sync | Set permissions during installation; test with a reset |
| Dynamic group not populating | Rule syntax error, or the attribute is empty for the expected users | Use rule validation in the admin center; check the attribute: Get-MgUser -UserId <id> -Property onPremisesExtensionAttributes \¦ Select-Object -ExpandProperty OnPremisesExtensionAttributes | Validate rules before deployment; populate attributes at the source before sync |
| Service principal blocked by workload identity policy | The workload authenticates from an IP outside the trusted named location | Add the service’s egress IP to the named location, or exclude that service principal with a documented exception | Record every workload’s egress IPs before enforcing CA015 |
| B2B guest can’t reach shared resources | Invitation not redeemed, terms of use not accepted, or blocked by a guest policy | Check redemption; check Conditional Access evaluation in the sign-in log | Trust partner MFA in cross-tenant settings; make the terms of use reachable |
| Lifecycle workflow doesn’t fire for a new hire | employeeHireDate isn’t populated in Entra ID (not mapped through provisioning or sync), or the sync cycle hasn’t delivered it | Check the attribute on the user; check the workflow’s run history in the admin center | Map the hire date from HR through provisioning; validate the format at the source |
| No leaked-credential detections | PHS not active for the affected users, or no P2 licensing for the reports and risk policies | Confirm PHS is active (not only in staged rollout); confirm licensing; check ID Protection risk detections | Enable PHS before deploying risk policies |
| Connect Sync staging server shows different counts | Configuration drift between active and staging servers | Export both configurations with Get-ADSyncServerConfiguration -Path <folder> and compare | After any change on the active server, apply it to staging; commit both exports to Git |

## Continue the book

← Previous: Chapter 09 — Building the Entra ID Target · Book index · Next: Chapter 11 — Reference Deployment →

# Chapter 11 — Reference Deployment

Run the migration as a governed sequence and the authorization evidence becomes a byproduct of the work, not a separate project afterward.

## In this chapter

This chapter puts the How chapters together on one representative estate: two Active Directory forests, a SQL Server estate of about ninety instances, and a Microsoft 365 Government Community Cloud (GCC) destination. It walks the five phases (Discover, Normalize, Map, Migrate, Validate), shows what each phase hands to the next, describes the bridge to the agency’s data platform, and lists the evidence bundle an assessor consumes and what the agency keeps when the contract ends.

## A framing pattern, not a real engagement

This chapter describes a pattern: how the Federal Modernization Program’s approach behaves against a typical federal civilian estate. It is not a report on a deployed and attested engagement. The agency is a composite, the counts are illustrative orders of magnitude, and there are no agency names, contractor names or calendar dates. When real engagement material can be released, measured results replace the illustrative figures.

## The archetype

The agency has about fifty thousand users in two Active Directory forests. One belongs to the agency itself. The other came from a component organization absorbed in an earlier reorganization. A forest trust joins them; nobody fully documented it and nobody owns it now. Between them the forests hold about seventy thousand computer accounts, twelve thousand groups and several thousand service accounts whose original owners have moved on. The SQL Server estate has about ninety instances across regional offices and the headquarters data center, plus a few workloads already connected to Azure Arc.

Federal policy pushes from several directions. OMB M-22-09 directs agencies to consolidate identity systems so that protections and monitoring apply consistently, and to give staff enterprise-managed accounts that resist phishing. OMB M-21-31 sets event-logging maturity tiers (EL0 through EL3) for log retention and centralized access. CISA BOD 25-01 requires agencies to inventory their in-scope cloud tenants, run CISA’s SCuBA assessment tools, and put the mandatory Secure Cloud Business Applications (SCuBA) baselines in place for Microsoft 365. The source page called BOD 25-01 a logging directive. That was wrong: logging belongs to M-21-31, and BOD 25-01 covers cloud configuration baselines. Meanwhile FedRAMP 20x is moving cloud service providers toward Key Security Indicators that are validated continuously rather than assessed once a year.

The agency has picked Microsoft 365 GCC (often called GCC-Moderate) as its identity and collaboration destination. In GCC, Microsoft 365 is paired with Microsoft Entra ID in the Azure commercial cloud, not Azure Government. That pairing matters for every service the bridge in this chapter depends on. The agency also wants its data estate to converge on Microsoft Purview for governance, with Microsoft Fabric and OneLake for analytics where the government cloud supports them.

Its compliance posture is familiar. A systems integrator who is no longer on contract assembled the last authorization package after the fact, over most of a year. The service principal name (SPN) inventory lives in spreadsheets that are two years old. The SQL Server estate’s ownership is recorded in component binders that disagree with each other. The agency owns the right tools (Entra ID, Intune, Defender, Purview), but no shared, authoritative record tells those tools how the agency is organized. Chapter 02 describes that structural problem, and Chapter 06 covers who has to own fixing it.

The five phases of the reference deployment and the artifact each phase hands to the next.

The rest of the chapter walks those phases in order. Each phase ends with a readiness bundle: a signed record of what the phase produced and which program documents it was produced against. The next phase starts only from that bundle, never from someone’s memory of what the last phase did. That gating is a program design choice, and it is what makes the evidence bundle at the end possible.

## Phase 1 — Discover

The first job is an honest picture of the current state. The read-only discovery approach in Chapter 07 reads both forests without writing to either. It enumerates the object classes that Chapter 04 catalogs as the hidden migration surface: users, computers, service accounts, security groups, Group Policy objects, DNS and DHCP records, PKI artifacts, RADIUS configuration, LDAP-dependent applications, Kerberos SPNs and the trust between the two forests. The survey uses the same tooling on every engagement. It is not a script written for this agency.

The service-account scan runs in the same pass. For each account it records the delegation configuration, adminCount status and a risk score. Two conditions are flagged as critical before migration starts. The first is an SPN that depends on Active Directory Certificate Services (ADCS). The second is unconstrained Kerberos delegation, which Windows Credential Guard already blocks on current Windows versions, and which Microsoft directs customers to replace with constrained delegation. In the archetype, about four hundred service accounts carry at least one SPN. The scan rates about sixty critical and another hundred high risk. Chapter 08 and Appendix B cover how to read and rank those findings.

The SPN inventory is the artifact the SQL Server work depends on most. Every MSSQLSvc/* registration is captured with a pre_migration phase tag, a discovery timestamp and an organizational attribution. The attribution comes from the service account that owns the SPN where possible, and from the hosting computer otherwise. SQL Server needs that registration to use Kerberos at all. An SPN maps to the Windows account that runs the instance, and if it’s missing or wrong the connection silently falls back to NTLM. About eighty of the ninety instances resolve cleanly. The other ten raise identity findings because their service accounts predate any organizational attribution the agency can defend. They’re recorded as high-severity (P2) conditions, and someone has to explicitly reassign an owner before those instances can migrate.

Discovery ends with its readiness bundle, which records the survey output, the scan, the phase-tagged SPN inventory and the program documents the run used.

## Phase 2 — Normalize

Discovery output is not yet authoritative. Both forests have a top-level “Operations” OU, but they hold different populations, and a merged tenant can’t tolerate that ambiguity. The agency builds an organizational registry from the discovery output and refines it against its organizational chart of record. From then on, the registry is the source of truth for where each principal sits in the organization. The collision gets resolved in the registry, not by renaming groups. Chapter 05 explains why OU placement can’t carry that meaning in Entra ID.

Normalization raises an identity finding for every principal the registry can’t attribute. On the first pass in the archetype, that’s about two thousand users and several hundred service accounts. Each finding comes with a suggested attribution drawn from OU placement, the manager chain or the hosting computer. The program doesn’t assign attributions automatically, because every later policy decision depends on them: Conditional Access targeting, administrative-unit scope, Purview policy scope and access reviews. The agency’s governance team resolves the findings through its change-request workflow before Phase 3 begins. Where the agency’s HR system can supply the attribution directly, that’s the better source, and it’s the subject of the HR-driven identity series.

## Phase 3 — Map

Mapping translates the governance model encoded in Active Directory (OU hierarchy, group nesting, delegated ACLs) into the attribute-driven model Entra ID requires. Chapter 09 designs that target. This chapter adds the per-surface contracts a two-forest estate needs. Each AD-adjacent surface gets an adapter with an explicit contract: what it reads, what it may change, its mission class and whether its target sits inside the GCC boundary. The surfaces are IP address management, PKI, RADIUS, LDAP proxy, the sync engine, device management, time service, DFS and the SQL Server workload.

Four of them carry most of the risk in this archetype:

- Synchronization. Two forests with a trust and about 130,000 directory objects push the choice of sync engine into the design. Microsoft Entra Cloud Sync is the platform Microsoft is now developing, and Microsoft says it will replace Connect Sync once it reaches functional parity. Today Cloud Sync supports up to 150,000 objects per domain and doesn’t support cross-forest references (for example, a manager in the other forest), while Connect Sync does. Chapter 09 works through that decision. The archetype’s cross-forest manager chains are the deciding input.

- PKI. The ADCS hierarchy issues dozens of templates through auto-enrollment. Intune can deliver certificates to managed devices with SCEP profiles. Against an ADCS issuing CA, that requires NDES and the Certificate Connector for Microsoft Intune. Microsoft Cloud PKI can replace the on-premises CA, NDES and connector for Intune-managed devices, but confirm it’s available in your cloud environment before you plan around it. Either way, sequence the cutover so no certificate expires in the middle of it.

- RADIUS. Network access in this archetype uses 802.1X EAP-TLS, which depends on the same ADCS hierarchy. The RADIUS adapter moves in lockstep with the PKI adapter.

- SQL Server. The ninety instances need their SPNs re-registered in step with the service-account migration. Each instance also needs a path to Microsoft Entra authentication. That path requires SQL Server 2022 or later and is usually configured through Azure Arc. Microsoft also documents a configuration without Arc for SQL Server 2022 and later. Entra authentication isn’t supported on failover cluster instances, so any clustered instance in the estate needs its own plan. About forty LDAP-bound internal applications go through the LDAP-proxy adapter.

This chapter doesn’t repeat the SQL Server procedure. The SQL Server Identity Transformation narrative explains the sequence and why it runs in that order: estate consolidation, authentication audit, the identity bridge, login migration, NTLM elimination and the certificate-authority dependency. The Implementation Companion has the runbooks for each step. This chapter’s job is to place that work inside the forest migration, so that SQL Server SPNs and service accounts move under the same gates as everything else.

## Phase 4 — Migrate

The migration runs as a sequence of provenance-chained events. Each adapter operation leaves a record that can’t be altered afterward. The record names the principal that requested the change, the authority for it, the version of the program documents it was made against and a hash of the resulting state. Two contract rules apply throughout. First, adapters read from and write against the authoritative record, but never replace it. Second, every operation is signed with an identity certificate. These are program design rules. The execution mechanics (staged cutover, coexistence, rollback) are in Chapter 10.

Drift findings appear during the migration as it runs. The program classifies them with the five-class drift taxonomy described in the workbook’s Drift Engine page:

| Drift class | Example in this archetype |
| --- | --- |
| DRIFT-SCHEMA | A newly migrated computer object carries an attribute encoding that doesn’t match the current schema version. |
| DRIFT-SEMANTIC | An organizational attribute value slips back into a deprecated geographic OU naming pattern. |
| DRIFT-PROVENANCE | A state change appears with no provenance event in the chain. This is critical (P1): the run halts until someone investigates. |
| DRIFT-AUTHZ | A Conditional Access policy contradicts the authentication assurance level recorded for that principal. |
| DRIFT-IDENTITY | A principal exists in the migrated tenant with no counterpart in the registry, an orphaned migration artifact. |

Assurance levels follow NIST SP 800-63-4, which superseded SP 800-63-3 in July 2025. Be honest about maturity. On the Drift Engine page, schema and provenance detection are shipped, semantic detection is partial, and authorization and identity detection are still design-only. In a real engagement today, the last two classes are found by the assessment modules and by people reviewing them, not by a runtime engine.

The archetype produces about three hundred drift findings across the migration window. Most are medium or low severity (P3 or P4) and are remediated automatically under the drift standard. A representative cycle has one P1. A finance service account’s post-migration role assignment exceeds what the assurance level recorded for it allows, so the dependent SQL Server instance’s migration stops until someone reduces the role assignment.

## Phase 5 — Validate

After migration, the SPN inventory is captured again with a post_migration tag, and the two inventories are compared. The program checks four conditions:

| Condition | Drift class | Severity | How it’s detected |
| --- | --- | --- | --- |
| SPN present before migration, absent after | DRIFT-IDENTITY | P1 | Set difference between the two phase-tagged inventories |
| SPN host or port changed with no provenance record | DRIFT-PROVENANCE | P2 | Same service class and principal, different host or port |
| SPN owner changed with no recorded migration event | DRIFT-AUTHZ | P1 | Same SPN, different principal, no transition record |
| SPN still in AD but no decided authentication path for the instance | DRIFT-IDENTITY | P2 | The instance has neither a configured Entra authentication path nor a recorded decision to keep Kerberos |

The fourth row is restated from the source page, which described it as a cross-check against “Entra Kerberos delegation” and workload-identity federation. Entra ID doesn’t take over Kerberos delegation for on-premises SQL Server SPNs. Those SPNs stay in Active Directory until the instance stops using Windows authentication. What gets validated is whether every instance has a decided path.

The third row is common, and it’s easy to miss. When a SQL Server service account changes, for example to a group managed service account, the SPNs registered on the old account stay there until someone moves or removes them. Microsoft’s guidance is that each MSSQLSvc SPN should have exactly one owner: the account that now runs the service. The checks below show how to confirm that on one instance.

## Illustrative commands

These commands are illustrative and haven’t been tested against a production forest. Review them, and substitute your own host, port and account names, before you run them.

# List the SPNs registered on the account that now runs the instance
# (a gMSA needs the trailing $).
setspn -L CONTOSO\SQLgMSA$

# Find which account owns a given SQL Server SPN. Exactly one should.
setspn -Q MSSQLSvc/sql01.contoso.com:1433

# Clear cached tickets on the test client before reconnecting.
klist purge

-- From a remote Windows-authenticated session: KERBEROS is expected,
-- NTLM means the SPN is still missing or misplaced.
SELECT auth_scheme
FROM sys.dm_exec_connections
WHERE session_id = @@SPID;

In the archetype, about three SPNs come back as P1 identity findings. These are SPNs whose re-registration step was skipped during the SQL Server sequence. Under the severity model, they halt the run and raise an alert. The operations team re-registers the SPNs against the migrated principals and recaptures the post-migration inventory, and repeats until no P1 findings remain. The SQL Server series covers the same check from the database side, in its NTLM-elimination book.

## The Azure SSOT bridge

When the identity migration is complete, the agency’s data platform joins the same single source of truth. The organizational registry from Phase 2 becomes the scope for data governance as well as identity.

On the Microsoft 365 side, Purview adaptive scopes target policies by Entra ID attributes, so they follow the registry without hand-maintained groups. Adaptive scopes apply to retention policies, retention label policies, auto-labeling policies and communication compliance policies. The source page also listed DLP and eDiscovery custodian queries as adaptive-scope targets. Microsoft doesn’t list those, so this chapter doesn’t claim them.

On the data side, the SQL Server instances are registered in the Purview Data Map under collections that follow the organizational structure. Purview supports registering and scanning SQL Server instances enabled by Azure Arc, with a self-hosted integration runtime, for SQL Server 2012 and later. Fabric domains mirror the same hierarchy. Each workspace is assigned to the domain of the segment that owns it, and every item in the workspace inherits that association. The instances that migrated cleanly can then be mirrored into OneLake. Fabric mirroring supports on-premises SQL Server 2016 through 2025, and SQL Server 2025 mirroring requires an Arc connection. The instances still remediating drift wait until their drift cycle closes.

That last step depends on the cloud. Fabric’s feature set in the US government clouds is narrower than in the commercial cloud. In GCC High, for example, Azure SQL Database is the only supported mirroring source. Fabric (F SKU) capacities aren’t supported in GCC; only EM and P SKUs are. Treat OneLake mirroring as conditional, and confirm it against Microsoft’s current availability pages for your environment before you commit it to a schedule.

The GCC boundary has a structural limit: the agency can’t independently verify some of the service-side telemetry that sensitivity-label decisions rely on. The program doesn’t claim to remediate that. It records the compensating controls the agency has put in place and verifies them on a schedule. Those records go into the evidence bundle.

## The evidence bundle the assessor consumes

From Phase 2 on, the agency can produce an evidence bundle at any time from the artifacts the phases have accumulated:

- the signed readiness bundle from each phase

- both phase-tagged SPN inventories, with the results of comparing them

- the provenance chain for every adapter operation

- every drift finding, with its severity, drift class and remediation evidence

- the GCC boundary finding, with the agency’s catalog of compensating controls and when each was last verified

- the Purview Data Map registration state, with an owner attributed for each asset

- the Fabric domain assignment state, with an owner attributed for each workspace

The evidence bundle assembles identity, drift and data-platform artifacts into one package the authorizing official and the assessor consume.

The source page said a FedRAMP 3PAO would consume this bundle in the agency’s next FedRAMP cycle. That needs correcting. FedRAMP authorizes cloud service offerings, and 3PAOs assess cloud service providers. FedRAMP 20x is likewise aimed mainly at providers, with agencies as consumers of what it produces. The agency’s own systems are authorized by the agency’s authorizing official under the NIST Risk Management Framework (SP 800-37 Rev. 2), which supports ongoing authorization driven by continuous monitoring. So the bundle goes to the agency’s security control assessor and authorizing official. It also shows how the agency’s side of the shared-responsibility model holds up on top of its providers’ FedRAMP packages.

The difference from the archetype’s last authorization is timing. The bundle comes out of operations as they happen; nobody assembles it over most of a year afterward. The authorizing official sees current state, not a snapshot that’s out of date by the time it’s signed.

## What survives the engagement

The registry, the schemas, the drift findings and the evidence bundle don’t belong to the systems integrator who delivered the migration. They belong to the agency. The next authorization cycle uses the existing record instead of rebuilding it. The next engagement, whether another consolidation, a data-governance expansion or the HR-driven identity work, starts from the current state, not from zero. That’s the cost shift the Federal SSOT Alignment whitepaper argues for: later engagements consume the record instead of rediscovering it.

A real engagement would measure the things this pattern is built to report:

- time to produce evidence, compared with the prior baseline of most of a year

- drift-finding rate over the migration window, by class and severity

- SPN drift per ten SQL Server instances migrated

- how often the GCC compensating controls are verified, and their false-positive rate

- the number of Purview policy decisions whose scope rests on continuously verified identity state

When engagement data can be released, those measurements replace the illustrative figures in this chapter.

## Where to go next

This book ends with identity moved and governed. It doesn’t answer where attribution should come from in the first place. In this chapter, Phase 2 resolved two thousand unattributed users by hand, because the HR system of record wasn’t connected to identity. The HR-driven identity series picks up at that point. It covers making the HR system the source of authority for workforce attributes, joiner-mover-leaver automation with Lifecycle Workflows, and an illustrative reference deployment of its own. For the SQL Server estate, continue with the narrative series and its Implementation Companion.

## Continue the book

← Previous: Chapter 10 — Migrating and Governing · Book index · Next: Appendix A — Federal Requirements Crosswalk →

# Appendix A — Federal Requirements Crosswalk

A baseline check is a ten-minute toggle in one tenant and a nine-month program in another; the difference is the Active Directory estate behind it.

## In this appendix

Microsoft’s Entra security checklist and the three filters that decide what a federal agency can do with it. How to read the crosswalk, and a scored set of identity controls tied to the CISA BOD 25-01 required configurations. The contract requirements of the program’s identity modernization specification, and the NIST SP 800-53 Rev. 5 controls the identity work supports.

## The assessment in one paragraph

An agency with twenty years of Active Directory behind its Entra ID tenant can put a meaningful part of Microsoft’s baseline in place quickly. The consent, guest, logging, emergency-access, legacy-authentication, and privileged-identity checks are mostly covered by licenses the agency already holds, and most are configuration only. Three filters then remove or defer a large share of the checklist before any work starts. Much of the “Protect networks” theme depends on Global Secure Access, which isn’t yet available in every government cloud. The AI theme is new, and its availability has to be confirmed cloud by cloud. And the heaviest identity checks (sign-in only from managed devices, token protection, phishing-resistant authentication for everyone, cloud authentication) are gated on device, device-management, and federation modernization that two decades of Active Directory turn into multi-quarter work. The agency’s structural advantage is the PIV/CAC card it already issues: Entra certificate-based authentication turns that card into a phishing-resistant credential without a federation server, which speeds up several of the hardest checks.

## The baseline

Microsoft publishes a checklist, “Configure Microsoft Entra for increased security,” that groups its Entra security recommendations into themes based on the Secure Future Initiative and lists a minimum license for each check. The page is labeled preview, covers workforce tenants, and says Microsoft will add controls over time. Its seven themes are:

- Protect identities and secrets

- Protect tenants and isolate production systems

- Protect networks

- Protect engineering systems

- Monitor and detect cyberthreats

- Accelerate response and remediation

- AI

Microsoft’s Zero Trust Assessment tool tests a tenant against these checks automatically, which is faster and less error-prone than checking by hand. The crosswalk below uses the checklist’s own check names so that results from the assessment tool can be joined to it directly. Because the checklist changes, an agency should re-pull it before each planning cycle rather than treating this appendix as the current list.

## The three filters

### Filter 1: government-cloud availability

Filter 1 — availability by theme

| Theme | What to expect |
| --- | --- |
| Protect identities and secrets | Available. Two checks for private applications need Entra Internet Access or Private Access licenses, so they follow the network row. |
| Protect tenants and isolate production systems | Available. |
| Protect networks | Mixed. Named locations and Tenant restrictions v2 need only Entra ID P1. Most of the remaining checks need Microsoft Entra Internet Access or Private Access, part of Global Secure Access, which is available in GCC but not yet in GCC High, the Department of Defense cloud, or other sovereign clouds. Treat these as an evaluation, not a quick win. |
| Protect engineering systems | Available. |
| Monitor and detect cyberthreats | Available, except the network-access log checks, which follow Global Secure Access availability. |
| Accelerate response and remediation | Available; needs Entra ID P2 or Microsoft Entra Workload ID, so confirm entitlement. |
| AI | New checks for agent identities. Confirm availability in the agency’s cloud before planning; defer otherwise. |

The source material said the network theme was “gated or non-FIPS in government clouds.” Microsoft’s current limitation is narrower and more useful for planning: Global Secure Access runs in GCC, whose tenants use the commercial Entra ID service, and isn’t yet supported in GCC High or DoD. The FIPS claim couldn’t be verified and is dropped.

### Filter 2: licensing

Each check in the checklist names a minimum license: none (included with Entra ID), Entra ID P1, Entra ID P2 or Microsoft Entra ID Governance, Entra Internet Access, Entra Private Access, the Microsoft Entra Suite, or Workload ID. Most identity, tenant, and engineering checks need P1 or P2, which many federal enterprise agreements already include. In the program’s experience the constraint for the majority of checks is operational, not entitlement. The exception is the network theme, where the Internet Access and Private Access licenses are separate purchases and run into Filter 1 as well.

### Filter 3: Active Directory friction

The same check can be a ten-minute toggle or a nine-month program depending on the hybrid estate behind it: directory synchronization, federation through AD FS, applications that still use basic authentication, decades of service accounts, domain-joined devices, and password policy set by on-premises Group Policy. The friction column in the crosswalk names that entanglement and the effort tier prices it. Both are the program’s assessment, not Microsoft’s.

## How to read the crosswalk

Government-cloud availability:

- Available: works in the agency’s cloud today.

- Caveated: works, with a license, preview, or feature limit noted.

- Not available: not supported in the agency’s cloud yet.

Active Directory friction:

- Cloud-only: no on-premises entanglement.

- Hybrid-touching: needs coordination with sync, devices, or users.

- Legacy-blocking: gated on retiring or modernizing a long-standing Active Directory dependency.

Effort tier:

- T0, this week: a tenant setting with no legacy dependency.

- T1, days: the setting is fast; discovery, coordination, and rollout are the work.

- T2, weeks: inventory and remediation, or a staged rollout.

- T3, multi-quarter: gated on device, identity, or federation modernization.

## The crosswalk: identity controls

The first three columns come from Microsoft’s checklist. The SCuBA column gives the matching mandatory policy from the CISA BOD 25-01 required configurations, where one exists. The NIST column is the program’s mapping to SP 800-53 Rev. 5 controls; the control titles are in the last section. Friction and tier are the program’s assessment.

Identity controls scored for a long-standing Active Directory estate

| Check (Microsoft name) | Theme | Minimum license | Friction | Tier | SCuBA mandatory policy | NIST SP 800-53 Rev. 5 |
| --- | --- | --- | --- | --- | --- | --- |
| User consent settings are restricted | Identities | None | Cloud-only | T0 | MS.AAD.5.2v1 | AC-6, CM-6 |
| Admin consent workflow is enabled | Identities | None | Cloud-only | T0 | MS.AAD.5.3v1 | AC-6 |
| Creating new applications and service principals is restricted to privileged users | Engineering | P1 | Cloud-only | T0 | MS.AAD.5.1v1 | AC-6, CM-7 |
| Emergency access accounts are configured appropriately | Engineering | P1 | Cloud-only | T0 | — | AC-2 |
| Diagnostic settings are configured for all Microsoft Entra logs | Monitor | P1 | Cloud-only | T0 | — | AU-2, AU-12 |
| Guests can’t invite other guests | Tenants | Free | Cloud-only | T0 | — | IA-8, AC-2 |
| Block legacy authentication policy is configured | Identities | P1 | Legacy-blocking | T1, report-only first | MS.AAD.1.1v1 | IA-2, AC-3 |
| Restrict high risk sign-ins | Response | P2 | Cloud-only | T1 | MS.AAD.2.3v1 | SI-4, AC-3 |
| Restrict access to high risk users | Response | P2 | Cloud-only | T1 | MS.AAD.2.1v1 | SI-4, AC-2 |
| Password expiration is disabled | Identities | P1 | Hybrid-touching | T1 | MS.AAD.6.1v1 | IA-5(1) |
| Global Administrator role activation triggers an approval workflow | Engineering | P2 | Cloud-only | T1 | MS.AAD.7.6v1 | AC-6(5) |
| Privileged accounts have phishing-resistant methods registered | Identities | P1 | Hybrid-touching; CBA accelerates | T1 to T2 | MS.AAD.3.6v1 | IA-2(1), IA-2(8), IA-2(12) |
| All privileged role assignments are activated just in time and not permanently active | Identities | P2 | Hybrid-touching | T2 | MS.AAD.7.4v1 | AC-2(7), AC-6(5) |
| Privileged accounts are cloud native identities | Identities | None | Legacy-blocking | T2 to T3 | MS.AAD.7.3v1 | AC-2(7), AC-6(5) |
| All user sign-in activity uses phishing-resistant authentication methods | Identities | P1 | Legacy-blocking; CBA accelerates | T2 to T3 | MS.AAD.3.1v1 | IA-2(1), IA-2(2), IA-2(8), IA-2(12) |
| Use cloud authentication | Identities | P1 | Legacy-blocking (federation migration) | T3 | — | IA-2, IA-5 |
| All sign-in activity comes from managed devices | Identities | P1 | Legacy-blocking (device-management maturity) | T3 | — | AC-3, IA-3 |
| Token protection policies are configured | Identities | P1 | Legacy-blocking (device-join maturity) | T3 | — | SC-23, IA-3 |

Notes on the rows that the Active Directory estate changes most:

- Password expiration is disabled. For users in scope of password hash synchronization, the cloud password is set to never expire by default, and the on-premises password policy still governs the password itself. Meeting the SCuBA policy for synced users means changing the on-premises policy too, which is why this row is hybrid-touching.

- Use cloud authentication. Microsoft’s reasoning is that an on-premises federation server is a central point an attacker can use to forge tokens and pivot into the cloud; the remediation is migrating from federation to password hash synchronization or another cloud method. For a federated agency, that is a domain-by-domain migration, not a toggle.

- Phishing-resistant authentication. OMB M-22-09 requires agency staff to use phishing-resistant multifactor authentication. SCuBA makes it mandatory for all users (MS.AAD.3.1v1), with an alternative MFA method required in the meantime (MS.AAD.3.2v1). Entra certificate-based authentication with PIV/CAC, FIDO2 security keys, and Windows Hello for Business are the qualifying methods Microsoft lists for M-22-09; Microsoft Authenticator alone isn’t phishing-resistant.

- The source’s control names. Several names in the source material were shortened (“All privileged role assignments are just-in-time”). The table uses Microsoft’s current wording so assessment output joins cleanly.

## Sequencing

Start with the T0 and T1 cloud-only checks: consent, application registration, guests, emergency access, logging, risk policies, and legacy authentication in report-only mode. Several of these are also SCuBA mandatory policies, so they close BOD 25-01 findings at the same time. Treat the network and AI themes as gated evaluations, decided by Filter 1. Treat the device-dependent and federation-dependent checks as multi-quarter programs that depend on the attribute and device modernization work in Chapter 09 and the cutover sequencing in Chapter 10.

## Federal mandates behind the baseline

### CISA BOD 25-01 and the SCuBA baselines

CISA issued Binding Operational Directive 25-01, Implementing Secure Practices for Cloud Services, on December 17, 2024. It applies to Federal Civilian Executive Branch agencies and covers production cloud tenants for products that have a final SCuBA Secure Configuration Baseline. Its deadlines were:

BOD 25-01 required actions

| Action | Deadline |
| --- | --- |
| Report an inventory of in-scope cloud tenants (name and owning agency or component), then update it annually | February 21, 2025 |
| Deploy the SCuBA assessment tools (ScubaGear for Microsoft 365) and begin continuous reporting to CISA, or submit results quarterly | April 25, 2025 |
| Implement all mandatory SCuBA policies on the Required Configurations list | June 20, 2025 |
| Implement future mandatory policy updates | On the timeline CISA posts |
| New in-scope tenants | Mandatory policies and continuous monitoring in place before an Authorization to Operate is granted |

The directive distinguishes mandatory “shall” policies from recommended “should” policies, which are left to the agency. For Microsoft Entra ID, the Required Configurations page lists twenty mandatory policies, from blocking legacy authentication (MS.AAD.1.1v1) through alerting on Global Administrator activation (MS.AAD.7.8v1). Policies the crosswalk table doesn’t already show:

Remaining BOD 25-01 mandatory Entra ID policies

| SCuBA policy | Requirement (paraphrased) |
| --- | --- |
| MS.AAD.3.2v1 | If phishing-resistant MFA isn’t yet enforced, enforce an alternative MFA method for all users |
| MS.AAD.3.3v2 | If Microsoft Authenticator is enabled, show login context information |
| MS.AAD.3.4v1 | Set the Authentication Methods Manage Migration feature to Migration Complete |
| MS.AAD.7.1v1 | Assign the Global Administrator role to between two and eight users |
| MS.AAD.7.2v1 | Give privileged users finer-grained roles instead of Global Administrator |
| MS.AAD.7.5v1 | Don’t provision highly privileged roles outside a privileged access management system |
| MS.AAD.7.7v1 | Alert on eligible and active highly privileged role assignments |
| MS.AAD.7.8v1 | Alert when a user activates the Global Administrator role |

Two of these interact with Active Directory directly. MS.AAD.7.3v1, cloud-only privileged accounts, means every synced on-premises admin account that holds an Entra role is a finding. MS.AAD.3.4v1 retires the legacy per-user MFA and self-service password reset policies, which many hybrid tenants still carry. The required list changes; CISA notifies agencies of changes to mandatory policies, so the list on cisa.gov, not this table, is authoritative.

### OMB M-22-09

OMB M-22-09, Moving the U.S. Government Toward Zero Trust Cybersecurity Principles, sets the identity goals that the phishing-resistant rows serve: enterprise-managed identities for agency staff, protected by phishing-resistant multifactor authentication.

## The identity modernization specification

The program’s identity modernization specification is the cross-adapter contract for modernizing identity without building any vendor’s quirks into the authoritative source. It’s the program’s design, not an external requirement, and it’s what the crosswalk’s evidence rests on.

### Contract requirements

- Dynamic groups are defined by rules over directory attributes.

- Administrative units and scoped roles replace delegation through organizational units.

- Access is computed from attributes, not assigned by hand.

- The rule set that turns attributes into access is itself the audit evidence.

### Integration shape

- Attribute writes for synced users are mastered in the directory, so the directory sync interval is the provisioning floor. With Microsoft Entra Connect Sync, that interval is 30 minutes by default.

- Device attributes are mastered in the cloud and written through the cloud API.

- Downstream systems reference or synchronize from the authoritative origin; they don’t keep independent copies.

Chapter 05 describes how requirement 2 is built, and Chapter 09 describes the target the requirements produce.

## NIST SP 800-53 Rev. 5 control mapping

The specification supports account management, access enforcement, and continuous monitoring controls by making access a computed property that can be regenerated from the authoritative attributes. The table maps the specification and the crosswalk to SP 800-53 Rev. 5 controls. Control identifiers and titles are checked against Release 5.2.0 of the catalog, issued August 27, 2025. The mapping itself is the program’s: it shows where identity evidence supports a control, not a claim that any configuration satisfies a control by itself. The agency’s authorizing official and assessors decide that.

NIST SP 800-53 Rev. 5 controls the identity work supports

| Control | Title | What the identity work contributes |
| --- | --- | --- |
| AC-2 | Account Management | Lifecycle workflows driven by HR attributes; emergency access accounts defined and monitored |
| AC-2(1) | Automated System Account Management | Provisioning and dynamic group membership computed from attributes |
| AC-2(3) | Disable Accounts | Inactive and departed identities disabled by workflow, not by ticket |
| AC-2(7) | Privileged User Accounts | Cloud-only privileged accounts with just-in-time activation |
| AC-3 | Access Enforcement | Conditional Access evaluates every sign-in to Entra ID |
| AC-3(13) | Attribute-based Access Control | The attribute-to-access rule set (contract requirements 1, 3, and 4) |
| AC-6 | Least Privilege | Restricted consent and app registration; administrative units and scoped roles |
| AC-6(5) | Privileged Accounts | Privileged roles limited, managed in PIM, approval-gated |
| AC-6(7) | Review of User Privileges | Access reviews over groups, roles, and access packages |
| AU-2 | Event Logging | Entra sign-in and audit logs exported through diagnostic settings |
| AU-6 | Audit Record Review, Analysis, and Reporting | Sign-in and audit logs reviewed in the SIEM |
| AU-12 | Audit Record Generation | Every token issuance and directory change produces a record |
| CA-7 | Continuous Monitoring | ScubaGear reporting to CISA and the Zero Trust Assessment run on a schedule against the tenant |
| CM-6 | Configuration Settings | The baseline held as code and compared with the live tenant |
| IA-2 | Identification and Authentication (Organizational Users) | Cloud authentication to Entra ID for all workforce users |
| IA-2(1) | Multi-factor Authentication to Privileged Accounts | Phishing-resistant methods required for privileged roles |
| IA-2(2) | Multi-factor Authentication to Non-privileged Accounts | Phishing-resistant or alternative MFA for all users |
| IA-2(8) | Access to Accounts — Replay Resistant | Certificate-based authentication and FIDO2 credentials |
| IA-2(12) | Acceptance of PIV Credentials | Entra certificate-based authentication with PIV/CAC |
| IA-3 | Device Identification and Authentication | Managed-device and token-protection requirements |
| IA-5 | Authenticator Management | Authentication methods policy; legacy methods retired |
| IA-5(1) | Password-based Authentication | Banned-password list, smart lockout, no forced expiration |
| IA-8 | Identification and Authentication (Non-organizational Users) | Guest restrictions, sponsors, and inactive-guest removal |
| SC-23 | Session Authenticity | Device-bound sign-in session tokens |
| SI-4 | System Monitoring | Risky user and sign-in detection with blocking policies |

## Continue the book

← Previous: Chapter 11 — Reference Deployment · Book index · Next: Appendix B — Forest Assessment Module →

# Appendix B — Forest Assessment Module

The code behind Chapter 08: one module, one output tree, one manifest per run.

## In this appendix

The FMPADAssessment module manifest and module file, function by function, followed by installation steps and the schema of every output file with JSON examples. The module is the source design restored from a damaged conversion, with the cmdlet, parameter and logic errors that review found corrected. Each correction is noted where it’s made. Chapter 08 explains what each collector is for.

## Illustrative code

This module is illustrative. It hasn’t been tested against a production forest. Review every function, sign the module, and run it first in a test forest under the narrow rights in Chapter 08. It reads the directory and writes only to the output path and, when you call the Gitea functions, to the repository you name. It changes nothing in Active Directory, DNS or AD CS.

## Corrections to the source design

The source module was flattened onto single lines during conversion, and several functions didn’t work as written. The table lists what changed and why.

| Area | Source | Corrected to | Reason |
| --- | --- | --- | --- |
| Syntax | param with no parentheses, @ for empty arrays, .ToString and ::NewGuid without () | Valid PowerShell | Conversion damage |
| Version check | String comparison of Win32_OperatingSystem.Version | [version] comparison | "10.0.9" -ge "10.0.26100" is true as strings |
| Required modules | ADCSAdministration required | Removed; PSPKI optional | Neither is needed; PSPKI is no longer actively supported by its publisher |
| DNS servers | Global catalogs only | All DCs, or a list you pass | DNS servers and GCs are different sets |
| DNS record data | PowerShell 7 ?? operator | switch on record type | The module declares PowerShell 5.1 |
| GPO links | OUs and domain root only | Also sites | Site-linked GPOs were reported as unlinked |
| Empty GPO check | $Report = \xml\ (damaged) | [xml](Get-GPOReport ... -ReportType Xml) | Conversion damage |
| CA discovery | certutil -config - -ping | Directory query of Enrollment Services | -config - prompts for a CA interactively |
| PSPKI calls | Get-CACertificate, Get-CACrlDistributionPoint, Get-CAAuthorityInformationAccess | certutil -ca.cert, directory CDP and AIA objects | The first doesn’t exist; the PSPKI names are Get-CRLDistributionPoint and Get-AuthorityInformationAccess |
| ESC1 check | Key usage contains Digital Signature | Authentication EKU present, enrollee supplies subject, no approval or signature, broad enroll right | Key usage isn’t EKU; nearly every template has Digital Signature |
| Delegation | TrustedToAuthForDelegation alone labeled protocol transition; RBCD missing | Four-way classification, DCs excluded | See Chapter 08 |
| Trusts | Test-ADTrust; direction text reversed | netdom trust /verify in a separate function; corrected text | Test-ADTrust isn’t an ActiveDirectory cmdlet |
| Orphaned adminCount | Direct MemberOf name match | Recursive membership of protected groups | Nested members were reported as orphans |
| Collector scope | -Domain accepted but ignored | Passed to every cmdlet as -Server or -Domain | Multi-domain runs assessed only the current domain |
| Gitea | One commit per file; labels never resolved | One multi-file commit on a run branch; label IDs looked up | One run, one commit; the API takes label IDs |
| Credentials | Token in a text file; user account with typed password | Token from the credential store; gMSA | No stored secrets |

## C.1 Module manifest (FMPADAssessment.psd1)

Generate a new GUID with New-Guid and paste it in; the source’s placeholder GUID isn’t unique.

@{
    RootModule        = 'FMPADAssessment.psm1'
    ModuleVersion     = '1.1.0'
    GUID              = '<paste the output of New-Guid here>'
    Author            = 'Federal Modernization Program'
    CompanyName       = 'FMP'
    Copyright         = '(c) 2026 Federal Modernization Program'
    Description       = 'Active Directory forest assessment: discovery, assessment and evidence pipeline.'
    PowerShellVersion = '5.1'
    RequiredModules   = @('ActiveDirectory', 'GroupPolicy')
    FunctionsToExport = @(
        'Test-FMPPrerequisites'
        'Get-FMPForestTopology'
        'Get-FMPOUHierarchy'
        'Get-FMPGPOInventory'
        'Export-FMPGPOSettings'
        'Get-FMPDNSAssessment'
        'Get-FMPPKIAssessment'
        'Get-FMPComputerInventory'
        'Get-FMPUserInventory'
        'Get-FMPGroupInventory'
        'Get-FMPTrustMap'
        'Test-FMPTrust'
        'Invoke-FMPADAssessment'
        'Compare-FMPAssessments'
        'Push-FMPAssessmentToGitea'
        'New-FMPSecurityIssue'
        'Invoke-FMPFindingIssues'
    )
    CmdletsToExport   = @()
    VariablesToExport = @()
    AliasesToExport   = @()
    PrivateData       = @{
        PSData = @{
            Tags = @('ActiveDirectory', 'Assessment', 'Governance', 'FMP')
        }
    }
}

## C.2 Module file (FMPADAssessment.psm1)

The module file is one script. It’s shown here in sections, in file order.

### Header and helpers

#Requires -Version 5.1
#Requires -Modules ActiveDirectory, GroupPolicy

<#
.SYNOPSIS
    Federal Modernization Program Active Directory assessment module.
.DESCRIPTION
    Forest discovery, infrastructure assessment and evidence extraction.
    Read-only against the directory. Writes only under -OutputPath.
#>

function Initialize-FMPPath {
    param([Parameter(Mandatory)][string]$Path)
    if (-not (Test-Path -Path $Path)) {
        New-Item -Path $Path -ItemType Directory -Force | Out-Null
    }
    $Path
}

function Write-FMPJson {
    param(
        [Parameter(Mandatory)]$InputObject,
        [Parameter(Mandatory)][string]$Path,
        [int]$Depth = 8
    )
    $InputObject | ConvertTo-Json -Depth $Depth |
        Out-File -FilePath $Path -Encoding UTF8
}

function Get-FMPDomainPath {
    # Returns <OutputPath>\<domain>\<Area>, creating it if needed.
    param(
        [Parameter(Mandatory)][string]$OutputPath,
        [Parameter(Mandatory)][string]$Domain,
        [Parameter(Mandatory)][string]$Area
    )
    Initialize-FMPPath -Path (Join-Path (Join-Path $OutputPath $Domain) $Area)
}

### Prerequisites

function Test-FMPPrerequisites {
    <#
    .SYNOPSIS
        Checks OS build, modules, forest connectivity and the output root.
    #>
    [CmdletBinding()]
    param([string]$OutputPath = 'D:\FMP\Assessment')

    $results = @()

    # Windows Server 2025 and Windows 11 24H2 report build 26100; 25H2 reports 26200.
    $os = Get-CimInstance -ClassName Win32_OperatingSystem
    $osPass = ([version]$os.Version) -ge [version]'10.0.26100'
    $results += [pscustomobject]@{
        Check  = 'Operating system'
        Status = if ($osPass) { 'PASS' } else { 'FAIL' }
        Detail = "$($os.Caption) ($($os.Version))"
    }

    $required = 'ActiveDirectory', 'GroupPolicy', 'DnsServer'
    $optional = 'PSPKI'
    foreach ($name in ($required + $optional)) {
        $mod = Get-Module -ListAvailable -Name $name | Select-Object -First 1
        $status = if ($mod) { 'PASS' } elseif ($name -in $optional) { 'OPTIONAL' } else { 'FAIL' }
        $results += [pscustomobject]@{
            Check  = "Module: $name"
            Status = $status
            Detail = if ($mod) { "Version $($mod.Version)" } else { 'Not installed' }
        }
    }

    try {
        $forest = Get-ADForest -ErrorAction Stop
        $results += [pscustomobject]@{ Check = 'Forest connectivity'; Status = 'PASS'; Detail = "Connected to $($forest.Name)" }
    } catch {
        $results += [pscustomobject]@{ Check = 'Forest connectivity'; Status = 'FAIL'; Detail = $_.Exception.Message }
    }

    $results += [pscustomobject]@{
        Check  = 'Output root'
        Status = if (Test-Path $OutputPath) { 'PASS' } else { 'FAIL' }
        Detail = $OutputPath
    }

    $results | Format-Table -AutoSize | Out-Host
    $failed = @($results | Where-Object Status -eq 'FAIL').Count
    if ($failed -gt 0) { Write-Warning "$failed prerequisite(s) failed. Resolve before running the assessment." }
    $results
}

### Forest topology

function Get-FMPForestTopology {
    <#
    .SYNOPSIS
        Captures forest, domains, DCs, sites, site links, subnets and operations master roles.
    .OUTPUTS
        ForestTopology.json plus Domains\AllDomains.json and Domains\DomainControllers.json.
    #>
    [CmdletBinding()]
    param(
        [string]$Domain = (Get-ADDomain).DNSRoot,
        [string]$OutputPath = 'D:\FMP\Assessment'
    )

    $forest     = Get-ADForest -Server $Domain
    $forestPath = Get-FMPDomainPath -OutputPath $OutputPath -Domain $Domain -Area 'Forest'
    $domainPath = Get-FMPDomainPath -OutputPath $OutputPath -Domain $Domain -Area 'Domains'

    $forestInfo = $forest | Select-Object Name, RootDomain,
        @{ N = 'ForestMode';       E = { "$($_.ForestMode)" } },
        SchemaMaster, DomainNamingMaster,
        @{ N = 'Domains';          E = { @($_.Domains) } },
        @{ N = 'Sites';            E = { @($_.Sites) } },
        @{ N = 'GlobalCatalogs';   E = { @($_.GlobalCatalogs) } },
        @{ N = 'UPNSuffixes';      E = { @($_.UPNSuffixes) } },
        @{ N = 'SPNSuffixes';      E = { @($_.SPNSuffixes) } }

    $domains = foreach ($d in $forest.Domains) {
        Get-ADDomain -Server $d | Select-Object DNSRoot, NetBIOSName,
            @{ N = 'DomainMode'; E = { "$($_.DomainMode)" } },
            @{ N = 'DomainSID';  E = { "$($_.DomainSID)" } },
            PDCEmulator, RIDMaster, InfrastructureMaster,
            DistinguishedName, ParentDomain,
            @{ N = 'ChildDomains'; E = { @($_.ChildDomains) } }
    }

    $dcs = foreach ($d in $forest.Domains) {
        Get-ADDomainController -Filter * -Server $d | Select-Object HostName, Domain, Site,
            IPv4Address, OperatingSystem, OperatingSystemVersion,
            IsGlobalCatalog, IsReadOnly, Enabled,
            @{ N = 'OperationMasterRoles'; E = { @($_.OperationMasterRoles | ForEach-Object { "$_" }) } }
    }

    $sites = Get-ADReplicationSite -Filter * -Server $Domain -Properties Description, Location |
        Select-Object Name, Description, Location,
            @{ N = 'Subnets'; E = {
                $dn = $_.DistinguishedName
                @(Get-ADReplicationSubnet -Filter "Site -eq '$dn'" -Server $Domain |
                    Select-Object -ExpandProperty Name) } }

    $siteLinks = Get-ADReplicationSiteLink -Filter * -Server $Domain -Properties Description, Options |
        Select-Object Name, Cost, ReplicationFrequencyInMinutes, Options, Description,
            @{ N = 'Sites'; E = { @($_.SitesIncluded | ForEach-Object { ($_ -split ',')[0] -replace '^CN=', '' }) } }

    $subnets = Get-ADReplicationSubnet -Filter * -Server $Domain -Properties Description, Location |
        Select-Object Name, Location, Description,
            @{ N = 'Site'; E = { if ($_.Site) { ($_.Site -split ',')[0] -replace '^CN=', '' } } }

    # Two forest-wide roles plus three per domain.
    $fsmo = @(
        [pscustomobject]@{ Role = 'SchemaMaster';       Scope = 'Forest'; Domain = $forest.RootDomain; Holder = $forest.SchemaMaster }
        [pscustomobject]@{ Role = 'DomainNamingMaster'; Scope = 'Forest'; Domain = $forest.RootDomain; Holder = $forest.DomainNamingMaster }
    )
    foreach ($d in $domains) {
        $fsmo += [pscustomobject]@{ Role = 'PDCEmulator';          Scope = 'Domain'; Domain = $d.DNSRoot; Holder = $d.PDCEmulator }
        $fsmo += [pscustomobject]@{ Role = 'RIDMaster';            Scope = 'Domain'; Domain = $d.DNSRoot; Holder = $d.RIDMaster }
        $fsmo += [pscustomobject]@{ Role = 'InfrastructureMaster'; Scope = 'Domain'; Domain = $d.DNSRoot; Holder = $d.InfrastructureMaster }
    }

    $topology = [pscustomobject]@{
        AssessmentTimestamp = (Get-Date -Format 'o')
        Forest              = $forestInfo
        Domains             = @($domains)
        DomainControllers   = @($dcs)
        Sites               = @($sites)
        SiteLinks           = @($siteLinks)
        Subnets             = @($subnets)
        FSMORoles           = $fsmo
    }

    Write-FMPJson -InputObject $topology        -Path (Join-Path $forestPath 'ForestTopology.json') -Depth 10
    Write-FMPJson -InputObject $forestInfo      -Path (Join-Path $forestPath 'ForestInfo.json')
    Write-FMPJson -InputObject @($sites)        -Path (Join-Path $forestPath 'Sites.json')
    Write-FMPJson -InputObject @($siteLinks)    -Path (Join-Path $forestPath 'SiteLinks.json')
    Write-FMPJson -InputObject @($subnets)      -Path (Join-Path $forestPath 'Subnets.json')
    Write-FMPJson -InputObject $fsmo            -Path (Join-Path $forestPath 'FSMORoles.json')
    Write-FMPJson -InputObject @($domains)      -Path (Join-Path $domainPath 'AllDomains.json')
    Write-FMPJson -InputObject @($dcs)          -Path (Join-Path $domainPath 'DomainControllers.json')
    foreach ($d in $domains) {
        Write-FMPJson -InputObject $d -Path (Join-Path $domainPath "$($d.DNSRoot).json")
    }

    Write-Verbose "ForestTopology.json written to $forestPath"
    $topology
}

### OU hierarchy and delegation

function Build-OUTree {
    # Recursive nested tree from a parent DN, with direct object counts and links.
    param(
        [Parameter(Mandatory)][string]$ParentDN,
        [Parameter(Mandatory)][string]$Server,
        [int]$Depth = 0
    )
    $children = Get-ADOrganizationalUnit -Filter * -SearchBase $ParentDN -SearchScope OneLevel `
        -Server $Server -Properties Description, ManagedBy, ProtectedFromAccidentalDeletion, LinkedGroupPolicyObjects

    foreach ($ou in $children) {
        $dn = $ou.DistinguishedName
        [pscustomobject]@{
            Name                            = $ou.Name
            DistinguishedName               = $dn
            Description                     = $ou.Description
            ManagedBy                       = $ou.ManagedBy
            ProtectedFromAccidentalDeletion = $ou.ProtectedFromAccidentalDeletion
            LinkedGPOs                      = @($ou.LinkedGroupPolicyObjects)
            Depth                           = $Depth
            ObjectCounts                    = [pscustomobject]@{
                Users     = @(Get-ADUser     -Filter * -SearchBase $dn -SearchScope OneLevel -Server $Server).Count
                Computers = @(Get-ADComputer -Filter * -SearchBase $dn -SearchScope OneLevel -Server $Server).Count
                Groups    = @(Get-ADGroup    -Filter * -SearchBase $dn -SearchScope OneLevel -Server $Server).Count
            }
            Children = @(Build-OUTree -ParentDN $dn -Server $Server -Depth ($Depth + 1))
        }
    }
}

function Show-OUTree {
    # Indented text rendering for human review.
    param([Parameter(Mandatory)]$TreeNodes, [int]$IndentLevel = 0)
    $indent = '    ' * $IndentLevel
    foreach ($node in $TreeNodes) {
        $c = $node.ObjectCounts
        "{0}+-- {1} [U:{2} C:{3} G:{4} GPO:{5}]" -f $indent, $node.Name, $c.Users, $c.Computers, $c.Groups, @($node.LinkedGPOs).Count
        if (@($node.Children).Count -gt 0) {
            Show-OUTree -TreeNodes $node.Children -IndentLevel ($IndentLevel + 1)
        }
    }
}

function Get-OUGPOLinks {
    # Links and inheritance for one domain or OU, from Get-GPInheritance.
    param(
        [Parameter(Mandatory)][string]$DistinguishedName,
        [Parameter(Mandatory)][string]$Domain
    )
    $som = Get-GPInheritance -Target $DistinguishedName -Domain $Domain
    [pscustomobject]@{
        Container          = $DistinguishedName
        InheritanceBlocked = "$($som.GpoInheritanceBlocked)"
        GPOLinks           = @($som.GpoLinks | ForEach-Object {
            [pscustomobject]@{
                GPOName   = $_.DisplayName
                GPOGUID   = "$($_.GpoId)"
                LinkOrder = $_.Order
                Enabled   = $_.Enabled
                Enforced  = $_.Enforced
            } })
    }
}

function Get-FMPOUHierarchy {
    <#
    .SYNOPSIS
        Extracts the OU tree, flat list, GPO links, delegations and a text rendering.
    .OUTPUTS
        OUHierarchy.json, OUFlatList.csv, OUFlatExport.json, OUGPOLinks.json, OUDelegations.json, OUTreeVisual.txt
    #>
    [CmdletBinding()]
    param(
        [string]$Domain = (Get-ADDomain).DNSRoot,
        [string]$OutputPath = 'D:\FMP\Assessment'
    )
    Import-Module ActiveDirectory    # provides the AD: drive used for ACL reads
    $ouPath   = Get-FMPDomainPath -OutputPath $OutputPath -Domain $Domain -Area 'OUs'
    $domainDN = (Get-ADDomain -Server $Domain).DistinguishedName

    $tree = @(Build-OUTree -ParentDN $domainDN -Server $Domain -Depth 0)
    Write-FMPJson -InputObject $tree -Path (Join-Path $ouPath 'OUHierarchy.json') -Depth 30

    $all = Get-ADOrganizationalUnit -Filter * -Server $Domain -Properties CanonicalName, Description, ManagedBy,
        Created, Modified, ProtectedFromAccidentalDeletion, LinkedGroupPolicyObjects, gPOptions
    $flat = $all | Select-Object Name, DistinguishedName, CanonicalName, Description, ManagedBy,
        Created, Modified, ProtectedFromAccidentalDeletion,
        @{ N = 'LinkedGPOs';         E = { @($_.LinkedGroupPolicyObjects) } },
        @{ N = 'InheritanceBlocked'; E = { $_.gPOptions -eq 1 } },
        @{ N = 'Depth';              E = { ([regex]::Matches($_.DistinguishedName, '(?i)OU=')).Count } }
    Write-FMPJson -InputObject @($flat) -Path (Join-Path $ouPath 'OUFlatExport.json')
    $flat | Select-Object Name, CanonicalName, Description, ManagedBy, ProtectedFromAccidentalDeletion, InheritanceBlocked, Depth |
        Export-Csv -Path (Join-Path $ouPath 'OUFlatList.csv') -NoTypeInformation -Encoding UTF8

    $links = @(Get-OUGPOLinks -DistinguishedName $domainDN -Domain $Domain)
    $links += foreach ($ou in $all) { Get-OUGPOLinks -DistinguishedName $ou.DistinguishedName -Domain $Domain }
    Write-FMPJson -InputObject $links -Path (Join-Path $ouPath 'OUGPOLinks.json')

    # Non-inherited ACEs only, excluding built-in and well-known principals.
    $delegations = foreach ($ou in $all) {
        $acl = Get-Acl -Path "AD:\$($ou.DistinguishedName)"
        [pscustomobject]@{
            OU          = $ou.Name
            DN          = $ou.DistinguishedName
            Delegations = @($acl.Access | Where-Object {
                    -not $_.IsInherited -and
                    "$($_.IdentityReference)" -notmatch '^(NT AUTHORITY|BUILTIN)\\|^S-1-5-'
                } | ForEach-Object {
                    [pscustomobject]@{
                        IdentityReference     = "$($_.IdentityReference)"
                        ActiveDirectoryRights = "$($_.ActiveDirectoryRights)"
                        AccessControlType     = "$($_.AccessControlType)"
                        ObjectType            = "$($_.ObjectType)"
                        InheritedObjectType   = "$($_.InheritedObjectType)"
                        InheritanceType       = "$($_.InheritanceType)"
                    } })
        }
    }
    Write-FMPJson -InputObject @($delegations) -Path (Join-Path $ouPath 'OUDelegations.json')

    Show-OUTree -TreeNodes $tree | Out-File -FilePath (Join-Path $ouPath 'OUTreeVisual.txt') -Encoding UTF8
    Write-Verbose "OU hierarchy written to $ouPath"
}

### Group Policy

function Export-FMPGPOSettings {
    <#
    .SYNOPSIS
        Decomposes GPO XML reports into settings grouped by configuration area.
    .OUTPUTS
        GPOSettingsDecomposed.json
    #>
    [CmdletBinding()]
    param(
        [Parameter(Mandatory)][string]$GPOSettingsPath,
        [Parameter(Mandatory)][string]$OutputPath
    )
    $areas = 'Security', 'Administrative Templates', 'Preferences', 'Scripts',
             'Software Installation', 'Folder Redirection', 'Registry'

    $decomposed = foreach ($file in Get-ChildItem -Path $GPOSettingsPath -Filter '*.xml') {
        [xml]$x = Get-Content -Path $file.FullName -Raw
        $entry = [ordered]@{
            GPOName  = $x.GPO.Name
            GPOGUID  = $x.GPO.Identifier.Identifier.'#text'
            Computer = [ordered]@{}
            User     = [ordered]@{}
        }
        foreach ($half in 'Computer', 'User') {
            $ext = @($x.GPO.$half.ExtensionData)
            foreach ($area in $areas) {
                $entry[$half][$area] = @($ext | Where-Object { $_.Name -match [regex]::Escape($area) } |
                    Select-Object -ExpandProperty Name)
            }
        }
        [pscustomobject]$entry
    }
    Write-FMPJson -InputObject @($decomposed) -Path (Join-Path $OutputPath 'GPOSettingsDecomposed.json') -Depth 15
    Write-Verbose "Decomposed $(@($decomposed).Count) GPO reports."
}

function Find-GPOConflicts {
    # Settings that appear in more than one GPO, keyed by extension element and name.
    param(
        [Parameter(Mandatory)][string]$GPOSettingsPath
    )
    $map = @{}
    foreach ($file in Get-ChildItem -Path $GPOSettingsPath -Filter '*.xml') {
        [xml]$x = Get-Content -Path $file.FullName -Raw
        foreach ($half in 'Computer', 'User') {
            foreach ($ext in @($x.GPO.$half.ExtensionData)) {
                if (-not $ext.Extension) { continue }
                foreach ($node in $ext.Extension.ChildNodes) {
                    if (-not $node.Name) { continue }
                    $key = '{0}|{1}|{2}' -f $half, $node.LocalName, $node.Name
                    if (-not $map.ContainsKey($key)) { $map[$key] = @() }
                    $map[$key] += [pscustomobject]@{
                        GPOName = $x.GPO.Name
                        State   = $node.State
                    }
                }
            }
        }
    }
    $map.GetEnumerator() | Where-Object { @($_.Value).Count -gt 1 } | ForEach-Object {
        [pscustomobject]@{
            SettingKey     = $_.Key
            GPOCount       = @($_.Value).Count
            DifferentState = @($_.Value.State | Select-Object -Unique).Count -gt 1
            GPOs           = @($_.Value)
        }
    }
}

function Get-FMPGPOInventory {
    <#
    .SYNOPSIS
        GPO inventory, XML and HTML reports, links (domain, OU and site), permissions,
        unlinked, empty and overlapping GPOs, and a native backup.
    #>
    [CmdletBinding()]
    param(
        [string]$Domain = (Get-ADDomain).DNSRoot,
        [string]$OutputPath = 'D:\FMP\Assessment',
        [switch]$SkipBackup
    )
    $gpoPath = Get-FMPDomainPath -OutputPath $OutputPath -Domain $Domain -Area 'GPOs'
    $setPath = Initialize-FMPPath -Path (Join-Path $gpoPath 'GPOSettings')
    $bakPath = Initialize-FMPPath -Path (Join-Path $gpoPath 'GPOBackups')

    $gpos = @(Get-GPO -All -Domain $Domain)

    $inventory = $gpos | Select-Object DisplayName,
        @{ N = 'Id';              E = { "$($_.Id)" } },
        @{ N = 'GpoStatus';       E = { "$($_.GpoStatus)" } },
        CreationTime, ModificationTime, Owner, Description,
        @{ N = 'WmiFilterName';   E = { if ($_.WmiFilter) { $_.WmiFilter.Name } } },
        @{ N = 'ComputerEnabled'; E = { "$($_.GpoStatus)" -notmatch 'ComputerSettingsDisabled|AllSettingsDisabled' } },
        @{ N = 'UserEnabled';     E = { "$($_.GpoStatus)" -notmatch 'UserSettingsDisabled|AllSettingsDisabled' } }
    Write-FMPJson -InputObject @($inventory) -Path (Join-Path $gpoPath 'GPOInventory.json')

    foreach ($g in $gpos) {
        $id = "$($g.Id)"
        Get-GPOReport -Guid $g.Id -Domain $Domain -ReportType Xml  -Path (Join-Path $setPath "$id.xml")
        Get-GPOReport -Guid $g.Id -Domain $Domain -ReportType Html -Path (Join-Path $setPath "$id.html")
    }

    # Every container with a gPLink: domain, OUs and sites (sites live in the configuration partition).
    $config = (Get-ADRootDSE -Server $Domain).configurationNamingContext
    $domainDN = (Get-ADDomain -Server $Domain).DistinguishedName
    $containers = @(Get-ADObject -Identity $domainDN -Server $Domain -Properties gPLink)
    $containers += @(Get-ADOrganizationalUnit -Filter * -Server $Domain -Properties gPLink)
    $containers += @(Get-ADObject -SearchBase "CN=Sites,$config" -Server $Domain `
        -LDAPFilter '(&(objectClass=site)(gPLink=*))' -Properties gPLink)

    $links = foreach ($g in $gpos) {
        $guid = [regex]::Escape("$($g.Id)")
        $where = @($containers | Where-Object { $_.gPLink -match "(?i)\{$guid\}" } |
            Select-Object -ExpandProperty DistinguishedName)
        [pscustomobject]@{
            GPOName     = $g.DisplayName
            GPOGUID     = "$($g.Id)"
            LinkedTo    = $where
            SiteLinked  = @($where | Where-Object { $_ -match '(?i),CN=Sites,' }).Count -gt 0
            TotalLinks  = $where.Count
            IsUnlinked  = $where.Count -eq 0
        }
    }
    Write-FMPJson -InputObject @($links) -Path (Join-Path $gpoPath 'GPOLinks.json')

    $empty = foreach ($g in $gpos) {
        [xml]$r = Get-Content -Path (Join-Path $setPath "$($g.Id).xml") -Raw
        if (-not $r.GPO.Computer.ExtensionData -and -not $r.GPO.User.ExtensionData) {
            [pscustomobject]@{ GPOName = $g.DisplayName; GPOGUID = "$($g.Id)"; CreationTime = $g.CreationTime; Owner = $g.Owner }
        }
    }
    Write-FMPJson -InputObject @($empty) -Path (Join-Path $gpoPath 'GPOEmpty.json')

    $perms = foreach ($g in $gpos) {
        [pscustomobject]@{
            GPOName     = $g.DisplayName
            GPOGUID     = "$($g.Id)"
            Permissions = @(Get-GPPermission -Guid $g.Id -DomainName $Domain -All | ForEach-Object {
                [pscustomobject]@{
                    Trustee     = $_.Trustee.Name
                    TrusteeType = "$($_.Trustee.SidType)"
                    Permission  = "$($_.Permission)"
                    Inherited   = $_.Inherited
                } })
        }
    }
    Write-FMPJson -InputObject @($perms) -Path (Join-Path $gpoPath 'GPOPermissions.json')

    Export-FMPGPOSettings -GPOSettingsPath $setPath -OutputPath $gpoPath
    Write-FMPJson -InputObject @(Find-GPOConflicts -GPOSettingsPath $setPath) -Path (Join-Path $gpoPath 'GPOConflicts.json') -Depth 6

    if (-not $SkipBackup) { Backup-GPO -All -Domain $Domain -Path $bakPath | Out-Null }
    Write-Verbose "GPO inventory written to $gpoPath"
}

Get-GPPermission returns GPPermission objects whose Trustee property identifies the principal; check the property names against Get-GPPermission ... | Get-Member on your GroupPolicy module version before relying on the TrusteeType column.

### DNS

function Get-FMPDnsRecordData {
    # PowerShell 5.1-compatible replacement for the source's ?? chain.
    param([Parameter(Mandatory)]$Record)
    $d = $Record.RecordData
    switch ($Record.RecordType) {
        'A'     { "$($d.IPv4Address)" }
        'AAAA'  { "$($d.IPv6Address)" }
        'CNAME' { $d.HostNameAlias }
        'NS'    { $d.NameServer }
        'PTR'   { $d.PtrDomainName }
        'MX'    { "$($d.Preference) $($d.MailExchange)" }
        'SRV'   { "$($d.Priority) $($d.Weight) $($d.Port) $($d.DomainName)" }
        'TXT'   { $d.DescriptiveText }
        'SOA'   { $d.PrimaryServer }
        default { '' }
    }
}

function Get-FMPDNSAssessment {
    <#
    .SYNOPSIS
        Zones, records, forwarders, stub zones, DNSSEC, scavenging, stale records and DC locator SRV checks.
    .OUTPUTS
        DNSInventory.json, DNSHealthReport.json, DNSRecordInventory.json
    #>
    [CmdletBinding()]
    param(
        [string]$Domain = (Get-ADDomain).DNSRoot,
        [string]$OutputPath = 'D:\FMP\Assessment',
        [string[]]$DnsServer,
        [int]$StaleThresholdDays = 90
    )
    $dnsPath = Get-FMPDomainPath -OutputPath $OutputPath -Domain $Domain -Area 'DNS'
    if (-not $DnsServer) {
        # Every DC in the domain, not only global catalogs; unreachable servers are reported, not fatal.
        $DnsServer = Get-ADDomainController -Filter * -Server $Domain | Select-Object -ExpandProperty HostName
    }
    $primary   = (Get-ADDomain -Server $Domain).PDCEmulator
    $stale     = (Get-Date).AddDays(-$StaleThresholdDays)

    $zonesByServer = foreach ($s in $DnsServer) {
        try {
            Get-DnsServerZone -ComputerName $s -ErrorAction Stop | Select-Object ZoneName,
                @{ N = 'ZoneType'; E = { "$($_.ZoneType)" } },
                IsAutoCreated, IsDsIntegrated, IsReverseLookupZone, IsSigned,
                @{ N = 'DynamicUpdate'; E = { "$($_.DynamicUpdate)" } },
                @{ N = 'DnsServer'; E = { $s } },
                @{ N = 'Partition'; E = {
                    if (-not $_.IsDsIntegrated) { 'File-backed' }
                    elseif ($_.DirectoryPartitionName -match '(?i)ForestDnsZones') { 'ForestDnsZones' }
                    elseif ($_.DirectoryPartitionName -match '(?i)DomainDnsZones') { 'DomainDnsZones' }
                    else { 'Domain' } } }
        } catch {
            [pscustomobject]@{ ZoneName = $null; DnsServer = $s; Error = $_.Exception.Message }
        }
    }

    $zones = Get-DnsServerZone -ComputerName $primary | Where-Object { -not $_.IsAutoCreated -and $_.ZoneName -ne 'TrustAnchors' }

    $records = foreach ($z in $zones) {
        $rr = @(Get-DnsServerResourceRecord -ZoneName $z.ZoneName -ComputerName $primary -ErrorAction SilentlyContinue)
        [pscustomobject]@{
            ZoneName      = $z.ZoneName
            RecordCount   = $rr.Count
            RecordsByType = @($rr | Group-Object RecordType | Select-Object Name, Count)
            StaleRecords  = @($rr | Where-Object { $_.Timestamp -and $_.Timestamp -lt $stale } |
                Select-Object HostName, RecordType, Timestamp,
                    @{ N = 'Data';    E = { Get-FMPDnsRecordData -Record $_ } },
                    @{ N = 'AgeDays'; E = { ((Get-Date) - $_.Timestamp).Days } })
        }
    }

    $dnssec = foreach ($z in ($zones | Where-Object IsSigned)) {
        Get-DnsServerDnsSecZoneSetting -ZoneName $z.ZoneName -ComputerName $primary |
            Select-Object ZoneName,
                @{ N = 'DenialOfExistence'; E = { "$($_.DenialOfExistence)" } },
                IsKeyMasterServer, KeyMasterServer,
                @{ N = 'DSRecordGenerationAlgorithm'; E = { @($_.DSRecordGenerationAlgorithm | ForEach-Object { "$_" }) } }
    }

    $srv = foreach ($prefix in '_ldap._tcp', '_kerberos._tcp', '_gc._tcp', '_kpasswd._tcp') {
        $name = "$prefix.$Domain"
        $r = @(Resolve-DnsName -Name $name -Type SRV -Server $primary -ErrorAction SilentlyContinue |
            Where-Object { $_.Type -eq 'SRV' })
        [pscustomobject]@{
            SRVRecord   = $name
            RecordCount = $r.Count
            Status      = if ($r.Count -gt 0) { 'PASS' } else { 'FAIL' }
            Targets     = ($r.NameTarget -join ', ')
        }
    }

    $scav = Get-DnsServerScavenging -ComputerName $primary | Select-Object ScavengingState,
        @{ N = 'ScavengingInterval'; E = { "$($_.ScavengingInterval)" } },
        @{ N = 'RefreshInterval';    E = { "$($_.RefreshInterval)" } },
        @{ N = 'NoRefreshInterval';  E = { "$($_.NoRefreshInterval)" } },
        LastScavengeTime

    $fwd = Get-DnsServerForwarder -ComputerName $primary | Select-Object @{ N = 'IPAddress'; E = { @($_.IPAddress | ForEach-Object { "$_" }) } }, UseRootHint

    $inventory = [pscustomobject]@{
        AssessmentTimestamp   = (Get-Date -Format 'o')
        DnsServer             = $primary
        Zones                 = @($zones | Select-Object ZoneName, @{ N = 'ZoneType'; E = { "$($_.ZoneType)" } },
                                    IsDsIntegrated, IsReverseLookupZone, IsSigned,
                                    @{ N = 'MasterServers'; E = { @($_.MasterServers | ForEach-Object { "$_" }) } })
        ConditionalForwarders = @($zones | Where-Object { "$($_.ZoneType)" -eq 'Forwarder' } | Select-Object -ExpandProperty ZoneName)
        StubZones             = @($zones | Where-Object { "$($_.ZoneType)" -eq 'Stub' } | Select-Object -ExpandProperty ZoneName)
        Forwarders            = $fwd
        Scavenging            = $scav
        DNSSEC                = @($dnssec)
    }
    $health = [pscustomobject]@{
        AssessmentTimestamp = (Get-Date -Format 'o')
        ZonesByServer       = @($zonesByServer)
        SRVChecks           = @($srv)
        StaleThresholdDays  = $StaleThresholdDays
    }

    Write-FMPJson -InputObject $inventory   -Path (Join-Path $dnsPath 'DNSInventory.json') -Depth 10
    Write-FMPJson -InputObject $health      -Path (Join-Path $dnsPath 'DNSHealthReport.json') -Depth 10
    Write-FMPJson -InputObject @($records)  -Path (Join-Path $dnsPath 'DNSRecordInventory.json') -Depth 6
    Write-Verbose "DNS assessment written to $dnsPath"
}

The DnsServer cmdlets used here are documented with these output fields: Get-DnsServerDnsSecZoneSetting for the DNSSEC fields and Get-DnsServerScavenging for the aging settings. A record whose timestamp is empty is static and never scavenged, which is why the stale filter skips it.

### AD CS

The collector reads CA and template configuration from the directory, reads each CA certificate and policy flags with certutil, and evaluates the ESC patterns that Defender for Identity assesses. Constants come from Microsoft’s published flag and right definitions: enrollee supplies subject is 0x1 in msPKI-Certificate-Name-Flag, pend all requests (manager approval) is 0x2 in msPKI-Enrollment-Flag, and the Enroll extended right is 0e10c968-78fb-11d2-90d4-00c04f79dc55. The authentication EKUs are Client Authentication and Smart Card Logon, PKINIT client authentication, and Any Purpose.

$script:FMPAuthEku = @(
    '1.3.6.1.5.5.7.3.2'       # Client Authentication
    '1.3.6.1.4.1.311.20.2.2'  # Smart Card Logon
    '1.3.6.1.5.2.3.4'         # PKINIT client authentication
    '2.5.29.37.0'             # Any Purpose
)
$script:FMPEnrollRight  = [guid]'0e10c968-78fb-11d2-90d4-00c04f79dc55'
$script:FMPBroadPrincipal = '(?i)\\(Authenticated Users|Domain Users|Domain Computers|Everyone)$|^Everyone$'

function Get-FMPPkiData {
    # Enterprise CAs and templates straight from the configuration partition.
    param([Parameter(Mandatory)][string]$Server)
    $config = (Get-ADRootDSE -Server $Server).configurationNamingContext
    $pks    = "CN=Public Key Services,CN=Services,$config"

    $cas = Get-ADObject -SearchBase "CN=Enrollment Services,$pks" -Server $Server `
        -LDAPFilter '(objectClass=pKIEnrollmentService)' -Properties cn, displayName, dNSHostName, certificateTemplates, nTSecurityDescriptor

    $templates = Get-ADObject -SearchBase "CN=Certificate Templates,$pks" -Server $Server `
        -LDAPFilter '(objectClass=pKICertificateTemplate)' `
        -Properties cn, displayName, msPKI-Cert-Template-OID, msPKI-Template-Schema-Version,
                    msPKI-Certificate-Name-Flag, msPKI-Enrollment-Flag, msPKI-RA-Signature,
                    pKIExtendedKeyUsage, msPKI-Certificate-Application-Policy, nTSecurityDescriptor

    [pscustomobject]@{ CAs = @($cas); Templates = @($templates); PksDN = $pks }
}

function Get-PKISecurityFindings {
    <#
    .SYNOPSIS
        Flags ESC1, ESC2, ESC4 template patterns and the ESC6 CA flag. Report only.
    #>
    param([Parameter(Mandatory)]$PkiData)

    $published = @($PkiData.CAs | ForEach-Object { $_.certificateTemplates }) | Select-Object -Unique
    $findings = @()

    foreach ($t in $PkiData.Templates) {
        $name    = $t.displayName
        $isPub   = $t.cn -in $published
        $eku     = @($t.pKIExtendedKeyUsage) + @($t.'msPKI-Certificate-Application-Policy') | Where-Object { $_ }
        $authEku = (@($eku).Count -eq 0) -or @($eku | Where-Object { $_ -in $script:FMPAuthEku }).Count -gt 0
        $supplies = ([int]$t.'msPKI-Certificate-Name-Flag' -band 0x1) -eq 0x1
        $approval = ([int]$t.'msPKI-Enrollment-Flag' -band 0x2) -eq 0x2
        $sigs     = [int]$t.'msPKI-RA-Signature'
        $aces     = @($t.nTSecurityDescriptor.Access | Where-Object { $_.AccessControlType -eq 'Allow' })
        $broadEnroll = @($aces | Where-Object {
                "$($_.IdentityReference)" -match $script:FMPBroadPrincipal -and (
                    ("$($_.ActiveDirectoryRights)" -match 'GenericAll') -or
                    (("$($_.ActiveDirectoryRights)" -match 'ExtendedRight') -and
                     ($_.ObjectType -eq $script:FMPEnrollRight -or $_.ObjectType -eq [guid]::Empty)))
            }).Count -gt 0
        $broadWrite = @($aces | Where-Object {
                "$($_.IdentityReference)" -match $script:FMPBroadPrincipal -and
                "$($_.ActiveDirectoryRights)" -match 'GenericAll|GenericWrite|WriteDacl|WriteOwner|WriteProperty'
            }).Count -gt 0

        if ($isPub -and $supplies -and $authEku -and -not $approval -and $sigs -eq 0 -and $broadEnroll) {
            $findings += [pscustomobject]@{ Finding = 'ESC1'; Severity = 'Critical'; Template = $name
                Description = 'Published template lets broad groups enroll, supply the subject, and obtain an authentication certificate without approval.'
                Remediation = 'Turn off Supply in the request, remove authentication EKUs, restrict enrollment, require manager approval, or unpublish.' }
        }
        $anyOrNone = (@($eku).Count -eq 0) -or ('2.5.29.37.0' -in $eku)
        if ($isPub -and $anyOrNone -and $broadEnroll) {
            $findings += [pscustomobject]@{ Finding = 'ESC2'; Severity = 'High'; Template = $name
                Description = 'Published template with Any Purpose or no EKU is enrollable by broad groups.'
                Remediation = 'Restrict the EKUs to the intended purposes or restrict enrollment.' }
        }
        if ($broadWrite) {
            $findings += [pscustomobject]@{ Finding = 'ESC4'; Severity = 'Critical'; Template = $name
                Description = 'Template ACL grants write or control rights to broad groups.'
                Remediation = 'Remove the entries; limit template write rights to PKI administrators.' }
        }
    }

    foreach ($ca in $PkiData.CAs) {
        $config = "$($ca.dNSHostName)\$($ca.cn)"
        $out = & certutil.exe -config $config -getreg 'policy\EditFlags' 2>&1 | Out-String
        if ($LASTEXITCODE -ne 0) {
            $findings += [pscustomobject]@{ Finding = 'CA-UNREADABLE'; Severity = 'Info'; Template = "N/A ($config)"
                Description = 'Could not read policy EditFlags.'; Remediation = 'Check RPC reachability and rights on the CA.' }
        } elseif ($out -match 'EDITF_ATTRIBUTESUBJECTALTNAME2') {
            $findings += [pscustomobject]@{ Finding = 'ESC6'; Severity = 'Critical'; Template = "N/A ($config)"
                Description = 'CA has EDITF_ATTRIBUTESUBJECTALTNAME2 set; requesters can add a SAN to any request.'
                Remediation = 'certutil -setreg policy\EditFlags -EDITF_ATTRIBUTESUBJECTALTNAME2, then restart the CA service.' }
        }
    }
    $findings
}

function Get-FMPPKIAssessment {
    <#
    .SYNOPSIS
        CA and template inventory, CA certificate details, CDP and AIA objects, and ESC findings.
    .OUTPUTS
        PKIInventory.json, PKISecurityReport.json
    #>
    [CmdletBinding()]
    param(
        [string]$Domain = (Get-ADDomain).DNSRoot,
        [string]$OutputPath = 'D:\FMP\Assessment'
    )
    $pkiPath = Get-FMPDomainPath -OutputPath $OutputPath -Domain $Domain -Area 'PKI'
    $pki = Get-FMPPkiData -Server $Domain

    $caInventory = foreach ($ca in $pki.CAs) {
        $config = "$($ca.dNSHostName)\$($ca.cn)"
        $certFile = Join-Path $pkiPath ("{0}.cer" -f ($ca.cn -replace '[^\w\-]', '_'))
        $cert = $null
        & certutil.exe -config $config -ca.cert $certFile 2>&1 | Out-Null
        if ($LASTEXITCODE -eq 0 -and (Test-Path $certFile)) {
            $cert = New-Object System.Security.Cryptography.X509Certificates.X509Certificate2 -ArgumentList $certFile
        }
        $keySize = $null
        if ($cert) { try { $keySize = $cert.PublicKey.Key.KeySize } catch { $keySize = $null } }
        [pscustomobject]@{
            CAName             = $ca.cn
            DisplayName        = $ca.displayName
            ComputerName       = $ca.dNSHostName
            ConfigString       = $config
            PublishedTemplates = @($ca.certificateTemplates)
            CertSubject        = if ($cert) { $cert.Subject }
            NotBefore          = if ($cert) { $cert.NotBefore.ToString('o') }
            NotAfter           = if ($cert) { $cert.NotAfter.ToString('o') }
            KeySize            = $keySize
            SignatureAlgorithm = if ($cert) { $cert.SignatureAlgorithm.FriendlyName }
        }
    }

    $templates = $pki.Templates | Select-Object @{ N = 'Name'; E = { $_.cn } }, @{ N = 'DisplayName'; E = { $_.displayName } },
        @{ N = 'OID';            E = { $_.'msPKI-Cert-Template-OID' } },
        @{ N = 'SchemaVersion';  E = { $_.'msPKI-Template-Schema-Version' } },
        @{ N = 'NameFlag';       E = { $_.'msPKI-Certificate-Name-Flag' } },
        @{ N = 'EnrollmentFlag'; E = { $_.'msPKI-Enrollment-Flag' } },
        @{ N = 'RASignatures';   E = { $_.'msPKI-RA-Signature' } },
        @{ N = 'EKU';            E = { @($_.pKIExtendedKeyUsage) + @($_.'msPKI-Certificate-Application-Policy') | Where-Object { $_ } } }

    # CRL and AIA publication objects in the directory; HTTP and file locations are in each CA's registry.
    $cdp = Get-ADObject -SearchBase "CN=CDP,$($pki.PksDN)" -Server $Domain -LDAPFilter '(objectClass=cRLDistributionPoint)' |
        Select-Object Name, DistinguishedName
    $aia = Get-ADObject -SearchBase "CN=AIA,$($pki.PksDN)" -Server $Domain -LDAPFilter '(objectClass=certificationAuthority)' |
        Select-Object Name, DistinguishedName

    $inventory = [pscustomobject]@{
        AssessmentTimestamp      = (Get-Date -Format 'o')
        CertificationAuthorities = @($caInventory)
        CertificateTemplates     = @($templates)
        CDPObjects               = @($cdp)
        AIAObjects               = @($aia)
    }
    $findings = @(Get-PKISecurityFindings -PkiData $pki)

    Write-FMPJson -InputObject $inventory -Path (Join-Path $pkiPath 'PKIInventory.json') -Depth 8
    Write-FMPJson -InputObject $findings  -Path (Join-Path $pkiPath 'PKISecurityReport.json')
    Write-Verbose "PKI assessment written to $pkiPath with $($findings.Count) findings."
}

The directory locations are the Public Key Services containers Microsoft documents: Enrollment Services for enterprise CAs, Certificate Templates, AIA and CDP. The certutil verbs (-config, -ca.cert, -getreg) are as documented. The ESC4 check above treats any broad write-type right as a finding; the ESC1 and ESC2 checks require the template to be published by at least one CA, because an unpublished template can’t be requested. ESC7 (CA ACLs) needs the CA’s own security settings and isn’t collected here; Defender for Identity assesses it where a sensor is installed on the CA.

### Computers

function Get-FMPComputerInventory {
    <#
    .SYNOPSIS
        Computer objects, OS classification, staleness and Kerberos delegation.
    .OUTPUTS
        ComputerInventory.json, ComputersByOS.csv, StaleComputers.csv, DelegationReport.csv
    #>
    [CmdletBinding()]
    param(
        [string]$Domain = (Get-ADDomain).DNSRoot,
        [string]$OutputPath = 'D:\FMP\Assessment',
        [int]$StaleThresholdDays = 90
    )
    $objPath = Get-FMPDomainPath -OutputPath $OutputPath -Domain $Domain -Area 'Objects'
    $staleDate = (Get-Date).AddDays(-$StaleThresholdDays)
    $dcNames = @(Get-ADDomainController -Filter * -Server $Domain | ForEach-Object { $_.Name })

    $computers = Get-ADComputer -Filter * -Server $Domain -Properties DNSHostName, OperatingSystem,
        OperatingSystemVersion, Enabled, LastLogonDate, PasswordLastSet, Created, Modified,
        MemberOf, IPv4Address, ServicePrincipalName, TrustedForDelegation, TrustedToAuthForDelegation,
        'msDS-AllowedToDelegateTo', PrincipalsAllowedToDelegateToAccount, 'msDS-SupportedEncryptionTypes', Description |
        Select-Object Name, DNSHostName, OperatingSystem, OperatingSystemVersion, Enabled,
            LastLogonDate, PasswordLastSet, Created, Modified, DistinguishedName, IPv4Address, Description,
            @{ N = 'SID';                      E = { "$($_.SID)" } },
            @{ N = 'IsDomainController';       E = { $_.Name -in $dcNames } },
            @{ N = 'MemberOfCount';            E = { @($_.MemberOf).Count } },
            @{ N = 'SPNs';                     E = { @($_.ServicePrincipalName) } },
            TrustedForDelegation, TrustedToAuthForDelegation,
            @{ N = 'AllowedToDelegateTo';      E = { @($_.'msDS-AllowedToDelegateTo') } },
            @{ N = 'RBCDPrincipals';           E = { @($_.PrincipalsAllowedToDelegateToAccount) } },
            @{ N = 'SupportedEncryptionTypes'; E = { $_.'msDS-SupportedEncryptionTypes' } }

    Write-FMPJson -InputObject @($computers) -Path (Join-Path $objPath 'ComputerInventory.json')

    $computers | Group-Object OperatingSystem | Select-Object @{ N = 'OperatingSystem'; E = { $_.Name } }, Count,
        @{ N = 'EnabledCount';  E = { @($_.Group | Where-Object Enabled).Count } },
        @{ N = 'DisabledCount'; E = { @($_.Group | Where-Object { -not $_.Enabled }).Count } } |
        Sort-Object Count -Descending |
        Export-Csv -Path (Join-Path $objPath 'ComputersByOS.csv') -NoTypeInformation -Encoding UTF8

    # Stale only when both lastLogonTimestamp and the machine password are old.
    $computers | Where-Object {
            ((-not $_.LastLogonDate) -or $_.LastLogonDate -lt $staleDate) -and
            ((-not $_.PasswordLastSet) -or $_.PasswordLastSet -lt $staleDate)
        } | Select-Object Name, DNSHostName, OperatingSystem, Enabled, LastLogonDate, PasswordLastSet, DistinguishedName,
            @{ N = 'DaysSinceLogon'; E = { if ($_.LastLogonDate) { ((Get-Date) - $_.LastLogonDate).Days } else { 'Never' } } } |
        Export-Csv -Path (Join-Path $objPath 'StaleComputers.csv') -NoTypeInformation -Encoding UTF8

    $computers | Where-Object {
            $_.TrustedForDelegation -or @($_.AllowedToDelegateTo).Count -gt 0 -or @($_.RBCDPrincipals).Count -gt 0
        } | Select-Object Name, DNSHostName, OperatingSystem, IsDomainController,
            @{ N = 'DelegationType'; E = {
                if ($_.TrustedForDelegation) { 'Unconstrained' }
                elseif (@($_.AllowedToDelegateTo).Count -gt 0 -and $_.TrustedToAuthForDelegation) { 'Constrained (protocol transition)' }
                elseif (@($_.AllowedToDelegateTo).Count -gt 0) { 'Constrained (Kerberos only)' }
                else { 'Resource-based (inbound)' } } },
            @{ N = 'DelegationTargets'; E = { @($_.AllowedToDelegateTo) -join '; ' } },
            @{ N = 'RBCDPrincipals';    E = { @($_.RBCDPrincipals) -join '; ' } },
            DistinguishedName |
        Export-Csv -Path (Join-Path $objPath 'DelegationReport.csv') -NoTypeInformation -Encoding UTF8

    Write-Verbose "Computer inventory: $(@($computers).Count) objects."
}

PrincipalsAllowedToDelegateToAccount is the ActiveDirectory module’s name for the resource-based delegation attribute, msDS-AllowedToActOnBehalfOfOtherIdentity. Domain controllers carry TrustedForDelegation by design, so IsDomainController lets the finding step exclude them.

### Users, groups and service accounts

$script:FMPPrivilegedGroups = 'Domain Admins', 'Enterprise Admins', 'Schema Admins', 'Administrators',
                              'Account Operators', 'Server Operators', 'Backup Operators', 'Print Operators'

function Find-CircularGroupNesting {
    # Groups that are members of themselves through nesting.
    param([Parameter(Mandatory)][string]$Server)
    $groups = @(Get-ADGroup -Filter * -Server $Server -Properties MemberOf)
    $parents = @{}
    foreach ($g in $groups) { $parents[$g.DistinguishedName] = @($g.MemberOf) }

    foreach ($g in $groups) {
        $start = $g.DistinguishedName
        $seen  = @{}
        $queue = New-Object System.Collections.Queue
        foreach ($p in $parents[$start]) { $queue.Enqueue($p) }
        while ($queue.Count -gt 0) {
            $current = $queue.Dequeue()
            if ($current -eq $start) {
                [pscustomobject]@{ Group = $g.SamAccountName; DN = $start }
                break
            }
            if ($seen.ContainsKey($current)) { continue }
            $seen[$current] = $true
            if ($parents.ContainsKey($current)) {
                foreach ($p in $parents[$current]) { $queue.Enqueue($p) }
            }
        }
    }
}

function Get-FMPUserInventory {
    <#
    .SYNOPSIS
        Users, privileged membership, AdminSDHolder-protected and orphaned accounts, and service accounts.
    .OUTPUTS
        UserInventory.json, PrivilegedUsers.csv, AdminCountReport.csv, ServiceAccounts.csv,
        ServiceAccounts\MSAInventory.json, ServiceAccounts\gMSAInventory.json
    #>
    [CmdletBinding()]
    param(
        [string]$Domain = (Get-ADDomain).DNSRoot,
        [string]$OutputPath = 'D:\FMP\Assessment',
        [int]$StaleThresholdDays = 90
    )
    $objPath = Get-FMPDomainPath -OutputPath $OutputPath -Domain $Domain -Area 'Objects'
    $saPath  = Get-FMPDomainPath -OutputPath $OutputPath -Domain $Domain -Area 'ServiceAccounts'
    $staleDate = (Get-Date).AddDays(-$StaleThresholdDays)

    $users = Get-ADUser -Filter * -Server $Domain -Properties UserPrincipalName, DisplayName, Enabled,
        LastLogonDate, PasswordLastSet, PasswordNeverExpires, PasswordExpired, LockedOut, AccountExpirationDate,
        MemberOf, AdminCount, TrustedForDelegation, ServicePrincipalName, Created, Modified, Description, Department, Title |
        Select-Object SamAccountName, UserPrincipalName, DisplayName, Enabled, LastLogonDate, PasswordLastSet,
            PasswordNeverExpires, PasswordExpired, LockedOut, AccountExpirationDate, AdminCount, TrustedForDelegation,
            Created, Modified, DistinguishedName, Description, Department, Title,
            @{ N = 'SID';           E = { "$($_.SID)" } },
            @{ N = 'IsStale';       E = { (-not $_.LastLogonDate) -or $_.LastLogonDate -lt $staleDate } },
            @{ N = 'MemberOfCount'; E = { @($_.MemberOf).Count } },
            @{ N = 'MemberOf';      E = { @($_.MemberOf) } },
            @{ N = 'SPNs';          E = { @($_.ServicePrincipalName) } }
    Write-FMPJson -InputObject @($users) -Path (Join-Path $objPath 'UserInventory.json')

    # Recursive membership of each privileged group.
    $privileged = @{}
    $privRows = foreach ($groupName in $script:FMPPrivilegedGroups) {
        try {
            Get-ADGroupMember -Identity $groupName -Recursive -Server $Domain -ErrorAction Stop |
                Where-Object objectClass -eq 'user' | ForEach-Object {
                    $privileged["$($_.SID)"] = $true
                    $u = Get-ADUser -Identity $_.SID -Server $Domain -Properties LastLogonDate, PasswordLastSet, Enabled, AdminCount
                    [pscustomobject]@{
                        PrivilegedGroup = $groupName
                        SamAccountName  = $u.SamAccountName
                        Enabled         = $u.Enabled
                        LastLogonDate   = $u.LastLogonDate
                        PasswordLastSet = $u.PasswordLastSet
                        AdminCount      = $u.AdminCount
                    }
                }
        } catch {
            Write-Warning "Unable to enumerate ${groupName}: $($_.Exception.Message)"
        }
    }
    $privRows | Export-Csv -Path (Join-Path $objPath 'PrivilegedUsers.csv') -NoTypeInformation -Encoding UTF8

    # adminCount=1 but no longer in any protected group (recursively) = orphaned.
    $users | Where-Object { $_.AdminCount -eq 1 } | Select-Object SamAccountName, Enabled, LastLogonDate,
            @{ N = 'InPrivilegedGroup';  E = { $privileged.ContainsKey($_.SID) } },
            @{ N = 'OrphanedAdminCount'; E = { -not $privileged.ContainsKey($_.SID) } } |
        Export-Csv -Path (Join-Path $objPath 'AdminCountReport.csv') -NoTypeInformation -Encoding UTF8

    $managed = @(Get-ADServiceAccount -Filter * -Server $Domain -Properties Enabled, Created, PasswordLastSet, ServicePrincipalName |
        Select-Object SamAccountName, Enabled, Created, PasswordLastSet, DistinguishedName,
            @{ N = 'ObjectClass'; E = { $_.ObjectClass } },
            @{ N = 'SPNs';        E = { @($_.ServicePrincipalName) } })
    Write-FMPJson -InputObject @($managed | Where-Object ObjectClass -eq 'msDS-ManagedServiceAccount')      -Path (Join-Path $saPath 'MSAInventory.json')
    Write-FMPJson -InputObject @($managed | Where-Object ObjectClass -eq 'msDS-GroupManagedServiceAccount') -Path (Join-Path $saPath 'gMSAInventory.json')

    $service = @()
    $service += $users | Where-Object { @($_.SPNs).Count -gt 0 } |
        Select-Object SamAccountName, Enabled, PasswordNeverExpires, LastLogonDate,
            @{ N = 'Type'; E = { 'User with SPN' } }, @{ N = 'SPNs'; E = { $_.SPNs -join '; ' } }
    $service += $managed | Select-Object SamAccountName, Enabled,
            @{ N = 'PasswordNeverExpires'; E = { $null } }, @{ N = 'LastLogonDate'; E = { $null } },
            @{ N = 'Type'; E = { $_.ObjectClass } }, @{ N = 'SPNs'; E = { $_.SPNs -join '; ' } }
    $service | Export-Csv -Path (Join-Path $objPath 'ServiceAccounts.csv') -NoTypeInformation -Encoding UTF8

    Write-Verbose "User inventory: $(@($users).Count) users, $(@($privRows).Count) privileged memberships."
}

function Get-FMPGroupInventory {
    <#
    .SYNOPSIS
        Groups with category, scope, member counts, empty flag and circular nesting.
    .OUTPUTS
        GroupInventory.json, CircularGroups.json
    #>
    [CmdletBinding()]
    param(
        [string]$Domain = (Get-ADDomain).DNSRoot,
        [string]$OutputPath = 'D:\FMP\Assessment'
    )
    $objPath = Get-FMPDomainPath -OutputPath $OutputPath -Domain $Domain -Area 'Objects'
    $groups = Get-ADGroup -Filter * -Server $Domain -Properties DisplayName, Description, Members, MemberOf,
        ManagedBy, Created, Modified, AdminCount |
        Select-Object SamAccountName, DisplayName, Description,
            @{ N = 'Category'; E = { "$($_.GroupCategory)" } },
            @{ N = 'Scope';    E = { "$($_.GroupScope)" } },
            ManagedBy, Created, Modified, DistinguishedName, AdminCount,
            @{ N = 'SID';               E = { "$($_.SID)" } },
            @{ N = 'DirectMemberCount'; E = { @($_.Members).Count } },
            @{ N = 'IsEmpty';           E = { @($_.Members).Count -eq 0 } },
            @{ N = 'CountMayBeCapped';  E = { @($_.Members).Count -ge 5000 } }
    Write-FMPJson -InputObject @($groups) -Path (Join-Path $objPath 'GroupInventory.json')
    Write-FMPJson -InputObject @(Find-CircularGroupNesting -Server $Domain) -Path (Join-Path $objPath 'CircularGroups.json')
    Write-Verbose "Group inventory: $(@($groups).Count) groups."
}

The privileged group list is Microsoft’s list of on-premises groups whose members are privileged. SDProp doesn’t clear adminCount when an account leaves a protected group, which is what the orphan report finds. CountMayBeCapped marks groups at the 5,000-value LDAP response limit, whose direct count should be checked another way. The ObjectClass filters for the MSA and gMSA files use the schema class names, such as msDS-GroupManagedServiceAccount for a gMSA; a dMSA on a Windows Server 2025 domain appears in ServiceAccounts.csv with its own class name.

### Trusts

$script:FMPTrustBits = [ordered]@{
    0x1  = 'NonTransitive'
    0x2  = 'UplevelOnly'
    0x4  = 'QuarantinedDomain'
    0x8  = 'ForestTransitive'
    0x10 = 'CrossOrganization'
    0x20 = 'WithinForest'
    0x40 = 'TreatAsExternal'
    0x80 = 'UsesRC4Encryption'
    0x100 = 'UsesAESKeys'
    0x200 = 'CrossOrganizationNoTGTDelegation'
    0x400 = 'PIMTrust'
    0x800 = 'CrossOrganizationEnableTGTDelegation'
}

function Get-FMPTrustMap {
    <#
    .SYNOPSIS
        Trusts with decoded attributes, access direction and posture. Enumeration only.
    .OUTPUTS
        TrustMap.json
    #>
    [CmdletBinding()]
    param(
        [string]$Domain = (Get-ADDomain).DNSRoot,
        [string]$OutputPath = 'D:\FMP\Assessment'
    )
    $trustPath = Get-FMPDomainPath -OutputPath $OutputPath -Domain $Domain -Area 'Trusts'
    $trusts = foreach ($t in Get-ADTrust -Filter * -Server $Domain -Properties *) {
        $attr = [int]$t.TrustAttributes
        $decoded = @($script:FMPTrustBits.Keys | Where-Object { $attr -band $_ } | ForEach-Object { $script:FMPTrustBits[$_] })
        $direction = "$($t.Direction)"
        [pscustomobject]@{
            Name                    = $t.Name
            Source                  = $t.Source
            Target                  = $t.Target
            Direction               = $direction
            TrustType               = "$($t.TrustType)"
            TrustAttributesRaw      = $attr
            TrustAttributes         = $decoded
            IntraForest             = $t.IntraForest
            ForestTransitive        = $t.ForestTransitive
            SelectiveAuthentication = $t.SelectiveAuthentication
            SIDFilteringQuarantined = $t.SIDFilteringQuarantined
            SIDFilteringForestAware = $t.SIDFilteringForestAware
            # Members of the trusted domain reach resources in the trusting domain.
            Access = switch ($direction) {
                'Inbound'       { "Users in $Domain can reach resources in $($t.Name)" }
                'Outbound'      { "Users in $($t.Name) can reach resources in $Domain" }
                'BiDirectional' { 'Users in each domain can reach resources in the other' }
                default         { 'Disabled' }
            }
            Posture = if ($t.IntraForest) { 'Intra-forest' }
                      elseif ($t.SelectiveAuthentication) { 'Hardened' }
                      elseif ($t.SIDFilteringQuarantined -or ($attr -band 0x8)) { 'Standard' }
                      else { 'Review required' }
            Created  = $t.Created
            Modified = $t.Modified
        }
    }
    $map = [pscustomobject]@{
        AssessmentTimestamp = (Get-Date -Format 'o')
        Domain              = $Domain
        TrustCount          = @($trusts).Count
        Trusts              = @($trusts)
    }
    Write-FMPJson -InputObject $map -Path (Join-Path $trustPath 'TrustMap.json') -Depth 6
    $map
}

function Test-FMPTrust {
    <#
    .SYNOPSIS
        Verifies each outbound trust's secure channel with netdom. Run separately, elevated.
    #>
    [CmdletBinding()]
    param([string]$Domain = (Get-ADDomain).DNSRoot)
    foreach ($t in Get-ADTrust -Filter * -Server $Domain) {
        $out = & netdom.exe trust $Domain "/domain:$($t.Name)" /verify 2>&1 | Out-String
        [pscustomobject]@{
            TrustPartner = $t.Name
            Direction    = "$($t.Direction)"
            Status       = if ($LASTEXITCODE -eq 0) { 'Verified' } else { 'Failed' }
            Output       = $out.Trim()
        }
    }
}

The bit values are from the Active Directory technical specification. netdom trust <trusting> /domain:<trusted> /verify verifies the secure channel secrets for one trust; Microsoft notes that accurate verification needs domain administrator credentials.

### Orchestrator and manifest

function Invoke-FMPADAssessment {
    <#
    .SYNOPSIS
        Runs every collector and writes AssessmentManifest.json with a SHA-256 hash per file.
    .EXAMPLE
        Invoke-FMPADAssessment -Domain 'contoso.com' -OutputPath 'D:\FMP\Assessment' -StaleThresholdDays 90
    #>
    [CmdletBinding()]
    param(
        [string]$Domain = (Get-ADDomain).DNSRoot,
        [string]$OutputPath = 'D:\FMP\Assessment',
        [int]$StaleThresholdDays = 90,
        [switch]$SkipGpoBackup
    )
    $start = Get-Date
    Write-Host "FMP Active Directory assessment: $Domain, started $($start.ToString('o'))"

    $steps = @(
        @{ Name = 'Forest topology';      Run = { Get-FMPForestTopology   -Domain $Domain -OutputPath $OutputPath | Out-Null } }
        @{ Name = 'OU hierarchy';         Run = { Get-FMPOUHierarchy      -Domain $Domain -OutputPath $OutputPath } }
        @{ Name = 'Group Policy';         Run = { Get-FMPGPOInventory     -Domain $Domain -OutputPath $OutputPath -SkipBackup:$SkipGpoBackup } }
        @{ Name = 'DNS';                  Run = { Get-FMPDNSAssessment    -Domain $Domain -OutputPath $OutputPath -StaleThresholdDays $StaleThresholdDays } }
        @{ Name = 'Certificate Services'; Run = { Get-FMPPKIAssessment    -Domain $Domain -OutputPath $OutputPath } }
        @{ Name = 'Computers';            Run = { Get-FMPComputerInventory -Domain $Domain -OutputPath $OutputPath -StaleThresholdDays $StaleThresholdDays } }
        @{ Name = 'Users and groups';     Run = { Get-FMPUserInventory    -Domain $Domain -OutputPath $OutputPath -StaleThresholdDays $StaleThresholdDays
                                                  Get-FMPGroupInventory   -Domain $Domain -OutputPath $OutputPath } }
        @{ Name = 'Trusts';               Run = { Get-FMPTrustMap         -Domain $Domain -OutputPath $OutputPath | Out-Null } }
    )
    $stepResults = @()
    $i = 0
    foreach ($s in $steps) {
        $i++
        Write-Host ("[{0}/{1}] {2}" -f $i, $steps.Count, $s.Name)
        try {
            & $s.Run
            $stepResults += [pscustomobject]@{ Step = $s.Name; Status = 'Completed'; Error = $null }
        } catch {
            Write-Warning "$($s.Name) failed: $($_.Exception.Message)"
            $stepResults += [pscustomobject]@{ Step = $s.Name; Status = 'Failed'; Error = $_.Exception.Message }
        }
    }

    $end      = Get-Date
    $basePath = Join-Path $OutputPath $Domain
    $files = Get-ChildItem -Path $basePath -Recurse -File |
        Where-Object { $_.Name -ne 'AssessmentManifest.json' } | ForEach-Object {
            [pscustomobject]@{
                RelativePath = $_.FullName.Substring($basePath.Length).TrimStart('\')
                SizeBytes    = $_.Length
                LastModified = $_.LastWriteTime.ToString('o')
                SHA256       = (Get-FileHash -Path $_.FullName -Algorithm SHA256).Hash
            }
        }

    $manifest = [pscustomobject]@{
        AssessmentId       = [guid]::NewGuid().ToString()
        Domain             = $Domain
        StartTime          = $start.ToString('o')
        EndTime            = $end.ToString('o')
        DurationMinutes    = [math]::Round(($end - $start).TotalMinutes, 2)
        ExecutedBy         = "$env:USERDOMAIN\$env:USERNAME"
        ComputerName       = $env:COMPUTERNAME
        StaleThresholdDays = $StaleThresholdDays
        Steps              = $stepResults
        FileCount          = @($files).Count
        Files              = @($files)
    }
    Write-FMPJson -InputObject $manifest -Path (Join-Path $basePath 'AssessmentManifest.json') -Depth 5
    Write-Host ("Assessment complete: {0} files in {1} minutes. Output: {2}" -f $manifest.FileCount, $manifest.DurationMinutes, $basePath)
    $manifest
}

A failed step is recorded in the manifest rather than stopping the run, so a partial run is visible as partial.

### Drift comparison

function Compare-FMPAssessments {
    <#
    .SYNOPSIS
        Compares two assessment runs: file hashes, then added and removed objects by stable key.
    .EXAMPLE
        Compare-FMPAssessments -BaselinePath 'E:\Repo\assessments\contoso.com\20261013-020000' `
                               -CurrentPath  'E:\Repo\assessments\contoso.com\20261020-020000'
    #>
    [CmdletBinding()]
    param(
        [Parameter(Mandatory)][string]$BaselinePath,
        [Parameter(Mandatory)][string]$CurrentPath
    )
    $keyed = [ordered]@{
        'Objects\ComputerInventory.json' = 'SID'
        'Objects\UserInventory.json'     = 'SID'
        'Objects\GroupInventory.json'    = 'SID'
        'GPOs\GPOInventory.json'         = 'Id'
    }
    $hashOnly = 'Forest\ForestTopology.json', 'Trusts\TrustMap.json', 'PKI\PKISecurityReport.json'

    $drift = @()
    foreach ($file in @($keyed.Keys) + $hashOnly) {
        $b = Join-Path $BaselinePath $file
        $c = Join-Path $CurrentPath $file
        if (-not (Test-Path $b) -or -not (Test-Path $c)) {
            $drift += [pscustomobject]@{ File = $file; Status = 'Missing in one run'; Added = $null; Removed = $null }
            continue
        }
        if ((Get-FileHash $b -Algorithm SHA256).Hash -eq (Get-FileHash $c -Algorithm SHA256).Hash) { continue }

        if ($keyed.Contains($file)) {
            $key = $keyed[$file]
            $bKeys = @((Get-Content $b -Raw | ConvertFrom-Json) | ForEach-Object { $_.$key })
            $cKeys = @((Get-Content $c -Raw | ConvertFrom-Json) | ForEach-Object { $_.$key })
            $drift += [pscustomobject]@{
                File    = $file
                Status  = 'Changed'
                Added   = @($cKeys | Where-Object { $_ -notin $bKeys })
                Removed = @($bKeys | Where-Object { $_ -notin $cKeys })
            }
        } else {
            # Files with an embedded timestamp always differ by hash; review their content.
            $drift += [pscustomobject]@{ File = $file; Status = 'Changed (review content)'; Added = $null; Removed = $null }
        }
    }
    $drift
}

For large inventories, replace the -notin comparisons with hash sets; the version above favors readability.

### Gitea integration

function Get-FMPGiteaHeaders {
    # The token comes from the Windows credential store or a vault; never from a text file.
    param([Parameter(Mandatory)][securestring]$Token)
    $plain = [Runtime.InteropServices.Marshal]::PtrToStringBSTR(
        [Runtime.InteropServices.Marshal]::SecureStringToBSTR($Token))
    @{ Authorization = "token $plain"; 'Content-Type' = 'application/json' }
}

function Push-FMPAssessmentToGitea {
    <#
    .SYNOPSIS
        Commits a whole run, manifest included, as one commit on a new branch.
    .EXAMPLE
        Push-FMPAssessmentToGitea -BaseUrl 'https://gitea.example.internal/api/v1' -Owner 'fmp' -Repo 'fmp' `
            -Token $token -RunPath 'D:\FMP\Assessment\contoso.com' -Domain 'contoso.com'
    #>
    [CmdletBinding()]
    param(
        [Parameter(Mandatory)][string]$BaseUrl,
        [Parameter(Mandatory)][string]$Owner,
        [Parameter(Mandatory)][string]$Repo,
        [Parameter(Mandatory)][securestring]$Token,
        [Parameter(Mandatory)][string]$RunPath,
        [Parameter(Mandatory)][string]$Domain,
        [string]$BaseBranch = 'main'
    )
    $headers   = Get-FMPGiteaHeaders -Token $Token
    $timestamp = Get-Date -Format 'yyyyMMdd-HHmmss'
    $prefix    = "assessments/$Domain/$timestamp"
    $branch    = "assessment/$Domain/$timestamp"

    # Every path is new under a timestamped folder, so each operation is a create.
    $files = Get-ChildItem -Path $RunPath -Recurse -File | ForEach-Object {
        @{
            operation = 'create'
            path      = "$prefix/" + ($_.FullName.Substring($RunPath.Length).TrimStart('\') -replace '\\', '/')
            content   = [Convert]::ToBase64String([IO.File]::ReadAllBytes($_.FullName))
        }
    }
    $body = @{
        branch     = $BaseBranch
        new_branch = $branch
        message    = "Assessment: $Domain @ $timestamp"
        files      = @($files)
    } | ConvertTo-Json -Depth 5

    Invoke-RestMethod -Uri "$BaseUrl/repos/$Owner/$Repo/contents" -Method Post -Headers $headers -Body $body
}

function New-FMPSecurityIssue {
    <#
    .SYNOPSIS
        Creates an issue for a critical finding. Label names are resolved to IDs first.
    #>
    [CmdletBinding()]
    param(
        [Parameter(Mandatory)][string]$BaseUrl,
        [Parameter(Mandatory)][string]$Owner,
        [Parameter(Mandatory)][string]$Repo,
        [Parameter(Mandatory)][securestring]$Token,
        [Parameter(Mandatory)][string]$Title,
        [Parameter(Mandatory)][string]$Body,
        [string[]]$Labels = @('security')
    )
    $headers = Get-FMPGiteaHeaders -Token $Token
    $all = Invoke-RestMethod -Uri "$BaseUrl/repos/$Owner/$Repo/labels" -Method Get -Headers $headers
    $ids = @($all | Where-Object { $_.name -in $Labels } | ForEach-Object { [int64]$_.id })
    $missing = @($Labels | Where-Object { $_ -notin $all.name })
    if ($missing) { Write-Warning "Labels not found in ${Repo}: $($missing -join ', ')" }

    $payload = @{ title = $Title; body = $Body; labels = $ids } | ConvertTo-Json -Depth 3
    $resp = Invoke-RestMethod -Uri "$BaseUrl/repos/$Owner/$Repo/issues" -Method Post -Headers $headers -Body $payload
    Write-Host "Issue created: $($resp.html_url)"
    $resp
}

function Invoke-FMPFindingIssues {
    <#
    .SYNOPSIS
        Raises issues for critical PKI findings and non-DC unconstrained delegation.
    #>
    [CmdletBinding()]
    param(
        [Parameter(Mandatory)][string]$BaseUrl,
        [Parameter(Mandatory)][string]$Owner,
        [Parameter(Mandatory)][string]$Repo,
        [Parameter(Mandatory)][securestring]$Token,
        [Parameter(Mandatory)][string]$RunPath
    )
    $common = @{ BaseUrl = $BaseUrl; Owner = $Owner; Repo = $Repo; Token = $Token }

    $pkiReport = Join-Path $RunPath 'PKI\PKISecurityReport.json'
    if (Test-Path $pkiReport) {
        foreach ($f in @(Get-Content $pkiReport -Raw | ConvertFrom-Json) | Where-Object Severity -eq 'Critical') {
            New-FMPSecurityIssue @common -Title "$($f.Finding): $($f.Template)" `
                -Body ("**Severity:** {0}`n`n{1}`n`n**Remediation:** {2}" -f $f.Severity, $f.Description, $f.Remediation) `
                -Labels @('security', 'critical', 'pki') | Out-Null
        }
    }

    $delegation = Join-Path $RunPath 'Objects\DelegationReport.csv'
    if (Test-Path $delegation) {
        $hits = @(Import-Csv $delegation | Where-Object { $_.DelegationType -eq 'Unconstrained' -and $_.IsDomainController -ne 'True' })
        if ($hits.Count -gt 0) {
            $lines = $hits | ForEach-Object { "- ``$($_.Name)`` ($($_.OperatingSystem))" }
            New-FMPSecurityIssue @common -Title "Unconstrained delegation: $($hits.Count) non-DC computer(s)" `
                -Body ("The following computers are trusted for unconstrained delegation:`n`n" + ($lines -join "`n")) `
                -Labels @('security', 'critical', 'delegation') | Out-Null
        }
    }
}

Export-ModuleMember -Function @(
    'Test-FMPPrerequisites', 'Get-FMPForestTopology', 'Get-FMPOUHierarchy', 'Get-FMPGPOInventory',
    'Export-FMPGPOSettings', 'Get-FMPDNSAssessment', 'Get-FMPPKIAssessment', 'Get-FMPComputerInventory',
    'Get-FMPUserInventory', 'Get-FMPGroupInventory', 'Get-FMPTrustMap', 'Test-FMPTrust',
    'Invoke-FMPADAssessment', 'Compare-FMPAssessments', 'Push-FMPAssessmentToGitea',
    'New-FMPSecurityIssue', 'Invoke-FMPFindingIssues'
)

The endpoints and fields are from Gitea’s API specification: the multi-file POST /repos/{owner}/{repo}/contents with branch, new_branch, message and a files list whose content is base64; label IDs from GET /repos/{owner}/{repo}/labels; and labels on a new issue as a list of IDs. The Authorization: token header form is Gitea’s documented API token format. A very large run may exceed your instance’s request size limit; if it does, commit in batches to the same branch.

### Optional: webhook and schedule

Create the webhook once, not per run. The webhook type for a generic JSON receiver is gitea; config needs url and content_type.

$hook = @{
    type          = 'gitea'
    active        = $true
    events        = @('push')
    branch_filter = 'assessment/*'
    config        = @{
        url          = 'https://automation.example.internal/api/webhook/assessment'
        content_type = 'json'
        secret       = '<shared secret held by the receiver>'
    }
} | ConvertTo-Json -Depth 4
Invoke-RestMethod -Uri "$BaseUrl/repos/fmp/fmp/hooks" -Method Post -Headers (Get-FMPGiteaHeaders -Token $token) -Body $hook

Schedule the run under the gMSA. Install and test the account on the host first; Install-ADServiceAccount caches it and proves the host can retrieve the password. Password is a documented value of -LogonType, and Task Scheduler is one of the services that can run under a gMSA. Pairing the two with the account name ending in $ is the program’s configuration; confirm in a test task that it runs without any stored password before relying on it.

Install-ADServiceAccount -Identity 'svc-fmp-assess$'
Test-ADServiceAccount   -Identity 'svc-fmp-assess$'

$action    = New-ScheduledTaskAction -Execute 'powershell.exe' `
    -Argument '-NoProfile -Command "Import-Module FMPADAssessment; Invoke-FMPADAssessment"'
$trigger   = New-ScheduledTaskTrigger -Weekly -DaysOfWeek Monday -At '02:00'
$principal = New-ScheduledTaskPrincipal -UserId 'CONTOSO\svc-fmp-assess$' -LogonType Password
Register-ScheduledTask -TaskName 'FMP-AD-Assessment' -Action $action -Trigger $trigger -Principal $principal `
    -Description 'Weekly Federal Modernization Program Active Directory assessment'

The source passed -ExecutionPolicy Bypass. Sign the module and rely on the host’s AllSigned or RemoteSigned policy instead.

## C.3 Installation

# Copy the module to a program-owned path.
$modulePath = 'D:\FMP\Modules\FMPADAssessment'
New-Item -Path $modulePath -ItemType Directory -Force | Out-Null
Copy-Item -Path '.\FMPADAssessment.psm1', '.\FMPADAssessment.psd1' -Destination $modulePath

# Add the parent folder to the machine module path once.
$current = [Environment]::GetEnvironmentVariable('PSModulePath', 'Machine')
if ($current -notmatch [regex]::Escape('D:\FMP\Modules')) {
    [Environment]::SetEnvironmentVariable('PSModulePath', "$current;D:\FMP\Modules", 'Machine')
}

# In a new session:
Import-Module FMPADAssessment -Verbose
Get-Command -Module FMPADAssessment
Test-FMPPrerequisites

## C.4 Output schema reference

Every file is UTF-8 JSON (or CSV, XML, HTML or text where noted). Timestamps are ISO 8601 with offset. Enumerations are written as strings.

### ForestTopology.json

| Field | Type | Description |
| --- | --- | --- |
| AssessmentTimestamp | string (ISO 8601) | When the collector ran |
| Forest | object | Name, RootDomain, ForestMode, SchemaMaster, DomainNamingMaster, Domains[], Sites[], GlobalCatalogs[], UPNSuffixes[], SPNSuffixes[] |
| Domains | array | DNSRoot, NetBIOSName, DomainMode, DomainSID, PDCEmulator, RIDMaster, InfrastructureMaster, DistinguishedName, ParentDomain, ChildDomains[] |
| DomainControllers | array | HostName, Domain, Site, IPv4Address, OperatingSystem, OperatingSystemVersion, IsGlobalCatalog, IsReadOnly, Enabled, OperationMasterRoles[] |
| Sites | array | Name, Description, Location, Subnets[] |
| SiteLinks | array | Name, Cost, ReplicationFrequencyInMinutes, Options, Description, Sites[] |
| Subnets | array | Name, Site, Location, Description |
| FSMORoles | array | Role, Scope (Forest or Domain), Domain, Holder |

{
  "AssessmentTimestamp": "2026-10-19T02:00:12.0000000-04:00",
  "Forest": {
    "Name": "contoso.com",
    "RootDomain": "contoso.com",
    "ForestMode": "Windows2016Forest",
    "SchemaMaster": "DC01.contoso.com",
    "DomainNamingMaster": "DC01.contoso.com",
    "Domains": ["contoso.com", "child.contoso.com"],
    "Sites": ["Default-First-Site-Name", "BranchOffice"],
    "GlobalCatalogs": ["DC01.contoso.com", "DC02.contoso.com"],
    "UPNSuffixes": ["contoso.gov"],
    "SPNSuffixes": []
  },
  "FSMORoles": [
    { "Role": "SchemaMaster", "Scope": "Forest", "Domain": "contoso.com", "Holder": "DC01.contoso.com" },
    { "Role": "PDCEmulator", "Scope": "Domain", "Domain": "child.contoso.com", "Holder": "CDC01.child.contoso.com" }
  ]
}

ForestMode and DomainMode take the ActiveDirectory module’s enumeration names, which now include Windows2025Forest and Windows2025Domain.

### GPOInventory.json and related GPO files

| Field | Type | Description |
| --- | --- | --- |
| DisplayName | string | GPO display name |
| Id | string (GUID) | GPO identifier; also the file name of its XML and HTML reports |
| GpoStatus | string | AllSettingsEnabled, UserSettingsDisabled, ComputerSettingsDisabled or AllSettingsDisabled |
| CreationTime, ModificationTime | datetime | Created and last modified |
| Owner | string | Owner, typically DOMAIN\group |
| WmiFilterName | string or null | WMI filter, if any |
| ComputerEnabled, UserEnabled | boolean | Whether each half is enabled |

GPOLinks.json holds GPOName, GPOGUID, LinkedTo[] (domain, OU and site DNs), SiteLinked, TotalLinks and IsUnlinked. GPOEmpty.json, GPOConflicts.json, GPOPermissions.json and GPOSettingsDecomposed.json follow the shapes in the functions above. GPOSettings\<GUID>.xml is the input to Intune Group Policy analytics.

[
  {
    "DisplayName": "Workstation Baseline",
    "Id": "31b2f340-016d-11d2-945f-00c04fb984f9",
    "GpoStatus": "UserSettingsDisabled",
    "CreationTime": "2019-03-04T10:15:00",
    "ModificationTime": "2026-08-30T16:41:22",
    "Owner": "CONTOSO\\Domain Admins",
    "Description": "",
    "WmiFilterName": null,
    "ComputerEnabled": true,
    "UserEnabled": false
  }
]

### PKISecurityReport.json

| Field | Type | Description |
| --- | --- | --- |
| Finding | string | ESC1, ESC2, ESC4, ESC6 or CA-UNREADABLE |
| Severity | string | Critical, High or Info |
| Template | string | Template display name, or N/A (<CA config string>) for CA-level findings |
| Description | string | What was found |
| Remediation | string | The documented fix, for the PKI owner to apply |

[
  {
    "Finding": "ESC1",
    "Severity": "Critical",
    "Template": "Web Server Legacy",
    "Description": "Published template lets broad groups enroll, supply the subject, and obtain an authentication certificate without approval.",
    "Remediation": "Turn off Supply in the request, remove authentication EKUs, restrict enrollment, require manager approval, or unpublish."
  }
]

### TrustMap.json

{
  "AssessmentTimestamp": "2026-10-19T02:41:03.0000000-04:00",
  "Domain": "contoso.com",
  "TrustCount": 1,
  "Trusts": [
    {
      "Name": "partner.example",
      "Direction": "Outbound",
      "TrustType": "Uplevel",
      "TrustAttributesRaw": 8,
      "TrustAttributes": ["ForestTransitive"],
      "IntraForest": false,
      "SelectiveAuthentication": false,
      "SIDFilteringQuarantined": false,
      "Access": "Users in partner.example can reach resources in contoso.com",
      "Posture": "Standard"
    }
  ]
}

### AssessmentManifest.json

| Field | Type | Description |
| --- | --- | --- |
| AssessmentId | string (GUID) | Unique identifier for the run |
| Domain | string | DNS name of the assessed domain |
| StartTime, EndTime | string (ISO 8601) | Execution window |
| DurationMinutes | number | Total duration |
| ExecutedBy, ComputerName | string | Account and host |
| StaleThresholdDays | integer | Threshold used by the run |
| Steps | array | Step, Status (Completed or Failed), Error |
| FileCount | integer | Number of files hashed |
| Files | array | RelativePath, SizeBytes, LastModified, SHA256 |

{
  "AssessmentId": "6f0c5a1e-9b8d-4e33-a2f1-0d7c3b9e4a12",
  "Domain": "contoso.com",
  "StartTime": "2026-10-19T02:00:00.0000000-04:00",
  "EndTime": "2026-10-19T02:47:31.0000000-04:00",
  "DurationMinutes": 47.52,
  "ExecutedBy": "CONTOSO\\svc-fmp-assess$",
  "ComputerName": "FMP-ASSESS01",
  "StaleThresholdDays": 90,
  "Steps": [
    { "Step": "Forest topology", "Status": "Completed", "Error": null },
    { "Step": "Certificate Services", "Status": "Failed", "Error": "The RPC server is unavailable." }
  ],
  "FileCount": 412,
  "Files": [
    {
      "RelativePath": "Forest\\ForestTopology.json",
      "SizeBytes": 48211,
      "LastModified": "2026-10-19T02:01:09.0000000-04:00",
      "SHA256": "<64 hexadecimal characters>"
    }
  ]
}

### Other files

| File | Root | Primary contents |
| --- | --- | --- |
| OUHierarchy.json | Array of nodes | Name, DistinguishedName, Description, ManagedBy, LinkedGPOs[], Depth, ObjectCounts, Children[] |
| OUDelegations.json | Array | OU, DN, Delegations[] (non-inherited ACEs) |
| DNSInventory.json | Object | AssessmentTimestamp, DnsServer, Zones[], ConditionalForwarders[], StubZones[], Forwarders, Scavenging, DNSSEC[] |
| DNSHealthReport.json | Object | ZonesByServer[], SRVChecks[], StaleThresholdDays |
| PKIInventory.json | Object | CertificationAuthorities[], CertificateTemplates[], CDPObjects[], AIAObjects[] |
| ComputerInventory.json | Array | Name, DNSHostName, OperatingSystem, Enabled, LastLogonDate, SPNs[], delegation fields, IsDomainController |
| UserInventory.json | Array | SamAccountName, UserPrincipalName, Enabled, LastLogonDate, AdminCount, IsStale, MemberOf[], SPNs[] |
| GroupInventory.json | Array | SamAccountName, Category, Scope, DirectMemberCount, IsEmpty, CountMayBeCapped |
| *.csv | CSV | Flat views for review: OUFlatList, ComputersByOS, StaleComputers, DelegationReport, PrivilegedUsers, AdminCountReport, ServiceAccounts |

## Continue the book

← Previous: Appendix A — Federal Requirements Crosswalk · Book index · Next: Appendix C — Identity Assessment Module →

# Appendix C — Identity Assessment Module

The reference material behind the identity chapters: what each attribute becomes, what each policy looks like on the wire, and the code that measures the gap.

## In this appendix

The full mapping of commonly used Active Directory user attributes to Microsoft Graph properties, including the program’s assignments for the fifteen extension attributes. Conditional Access policy templates in Microsoft Graph JSON for the policy set in Chapter 09. The FMPIdentityAssessment PowerShell module that Chapter 10 schedules for drift detection, written against Microsoft Graph PowerShell.

## Attribute mapping reference

The table maps commonly used Active Directory user attributes to Microsoft Graph user properties. Whether an attribute actually flows depends on the sync engine’s attribute mappings; Microsoft publishes the list of attributes Connect Sync synchronizes, grouped by workload. Property names are from the Microsoft Graph v1.0 user resource.

| AD attribute | Microsoft Graph property | Notes |
| --- | --- | --- |
| sAMAccountName | onPremisesSamAccountName | Read-only in Entra ID for synced users |
| userPrincipalName | userPrincipalName | Suffix must be a verified domain |
| mS-DS-ConsistencyGuid | onPremisesImmutableId (Base64) | The default source anchor; the hard-match key |
| objectGUID | onPremisesImmutableId (Base64), only where objectGUID is the configured source anchor | Older installations; can’t be changed on the AD object |
| objectSid | onPremisesSecurityIdentifier | Must be unique in the tenant |
| distinguishedName | onPremisesDistinguishedName | Read-only; useful for tracing OU placement during the transition |
| cn | No separate property | Synced, but not exposed as its own Graph user property |
| displayName, givenName, sn | displayName, givenName, surname | Direct |
| mail, mailNickname, proxyAddresses | mail, mailNickname, proxyAddresses | The primary SMTP address in proxyAddresses is a soft-match key |
| userAccountControl | accountEnabled | The disabled bit becomes a Boolean |
| pwdLastSet | lastPasswordChangeDateTime | Also used to invalidate issued tokens after a password change |
| whenCreated | createdDateTime | The date the object reached Entra ID, not the AD creation date |
| whenChanged | No equivalent |  |
| lastLogonTimestamp | No mapping; use signInActivity/lastSignInDateTime | A separate signal from Entra ID sign-ins; needs P1 and AuditLog.Read.All |
| department, title, company | department, jobTitle, companyName | Direct |
| manager, directReports | manager, directReports (relationships) | Resolved as relationships |
| telephoneNumber, mobile, facsimileTelephoneNumber | businessPhones, mobilePhone, faxNumber | Direct |
| streetAddress, l, st, postalCode | streetAddress, city, state, postalCode | Direct |
| c, co, countryCode | country | All three are synced; confirm which one your mapping writes to country |
| physicalDeliveryOfficeName | officeLocation | Direct |
| employeeID, employeeType | employeeId, employeeType | Direct; both usable in Lifecycle Workflows scope rules |
| memberOf, member | memberOf, members (relationships) | Resolved by the sync engine |
| description, info | No user property | Not carried on the user object |
| servicePrincipalName | No user property | Service principal objects have servicePrincipalNames, a different concept |
| thumbnailPhoto | Profile photo | Synced to the Microsoft 365 profile photo periodically |
| userCertificate | No user property in Graph v1.0 | Synced for Exchange; certificate-based authentication uses its own username bindings instead |
| msDS-UserPasswordExpiryTimeComputed | No equivalent | Cloud password policy is separate |
| adminCount | No equivalent | PIM replaces AdminSDHolder protection |
| accountExpires | No equivalent | The program copies the HR end date to extensionAttribute8 |
| extensionAttribute1–15 | onPremisesExtensionAttributes/extensionAttribute1–15 | Program assignments below |

### Extension attribute assignments

The program assigns the fifteen extension attributes as follows. These are design choices; any agency can reassign them, but the dynamic groups, Conditional Access personas, and workflows in Chapters 09 and 10 assume this layout.

| Attribute | Program meaning | Used by |
| --- | --- | --- |
| extensionAttribute1 | Region | Dynamic groups |
| extensionAttribute2 | Department code | Dynamic groups (alongside department) |
| extensionAttribute3 | Division | Mover trigger; dynamic administrative units |
| extensionAttribute4 | Role | Mover trigger; access package auto-assignment |
| extensionAttribute5 | Cost center | License assignment groups |
| extensionAttribute6 | Classification (worker type: Employee, Contractor) | Conditional Access Internals persona |
| extensionAttribute7 | Hire date from HR | Mapped to employeeHireDate by a sync rule |
| extensionAttribute8 | End date from HR | Mapped to employeeLeaveDateTime by a sync rule |
| extensionAttribute9 | Clearance level | Restricted access packages |
| extensionAttribute10 | Account type (Standard, Service, Privileged) | Conditional Access Admins persona; service account scoping |
| extensionAttribute11–15 | Reserved | extensionAttribute15 = DoNotSync excludes an object from sync |

Lifecycle Workflows read the native employeeHireDate and employeeLeaveDateTime properties, not the extension attributes. For synced users, map the HR dates from AD into those properties during sync, as Microsoft documents for Lifecycle Workflows. Extension attributes 7 and 8 are the AD-side carriers for that mapping.

## Conditional Access policy templates

These templates express policies from Chapter 09 as Microsoft Graph conditionalAccessPolicy JSON. Import them with New-MgIdentityConditionalAccessPolicy -BodyParameter, or export your own configured policies with the snippet at the end of this section.

## Placeholders and endpoints

The templates use placeholders such as <GUID-BreakGlassExclusionGroup> for group, named location, and authentication strength IDs. Replace every placeholder with your tenant’s values before import. List the built-in authentication strengths and their IDs with GET /policies/authenticationStrengthPolicies?$filter=policyType eq 'builtIn' (beta). A GCC tenant uses the worldwide Microsoft Graph endpoint, https://graph.microsoft.com; https://graph.microsoft.us is for GCC High. Every template is created in report-only state (enabledForReportingButNotEnforced).

### CA001: block legacy authentication

{
  "displayName": "CA001-AllUsers-BlockLegacyAuth",
  "state": "enabledForReportingButNotEnforced",
  "conditions": {
    "users": {
      "includeUsers": ["All"],
      "excludeGroups": ["<GUID-BreakGlassExclusionGroup>"]
    },
    "applications": { "includeApplications": ["All"] },
    "clientAppTypes": ["exchangeActiveSync", "other"]
  },
  "grantControls": {
    "operator": "OR",
    "builtInControls": ["block"]
  }
}

### CA003: admins require phishing-resistant MFA

{
  "displayName": "CA003-Admins-RequirePhishResistantMFA",
  "state": "enabledForReportingButNotEnforced",
  "conditions": {
    "users": {
      "includeGroups": ["<GUID-AdminsGroup>"],
      "excludeGroups": ["<GUID-BreakGlassExclusionGroup>"]
    },
    "applications": { "includeApplications": ["All"] },
    "clientAppTypes": ["browser", "mobileAppsAndDesktopClients"]
  },
  "grantControls": {
    "operator": "OR",
    "authenticationStrength": { "id": "<GUID-PhishingResistantMFA>" }
  },
  "sessionControls": {
    "signInFrequency": { "value": 4, "type": "hours", "isEnabled": true }
  }
}

### CA006: internals require MFA

{
  "displayName": "CA006-Internals-RequireMFA",
  "state": "enabledForReportingButNotEnforced",
  "conditions": {
    "users": {
      "includeGroups": ["<GUID-InternalsGroup>"],
      "excludeGroups": ["<GUID-BreakGlassExclusionGroup>", "<GUID-AdminsGroup>"]
    },
    "applications": { "includeApplications": ["All"] },
    "clientAppTypes": ["browser", "mobileAppsAndDesktopClients"]
  },
  "grantControls": {
    "operator": "OR",
    "authenticationStrength": { "id": "<GUID-MFA>" }
  },
  "sessionControls": {
    "signInFrequency": { "value": 12, "type": "hours", "isEnabled": true }
  }
}

### CA008: block sign-ins from outside the United States for internals

{
  "displayName": "CA008-Internals-BlockNonUSLocations",
  "state": "enabledForReportingButNotEnforced",
  "conditions": {
    "users": {
      "includeGroups": ["<GUID-InternalsGroup>"],
      "excludeGroups": ["<GUID-BreakGlassExclusionGroup>", "<GUID-ApprovedTravelExceptions>"]
    },
    "applications": { "includeApplications": ["All"] },
    "locations": {
      "includeLocations": ["All"],
      "excludeLocations": ["<GUID-TrustedCountriesUS>"]
    },
    "clientAppTypes": ["browser", "mobileAppsAndDesktopClients"]
  },
  "grantControls": {
    "operator": "OR",
    "builtInControls": ["block"]
  }
}

### CA013: high user risk requires risk remediation

This template replaces the earlier “require password change and MFA” version. riskRemediation is a newer member of the grant control enumeration; Microsoft Graph returns it only when the request carries the header Prefer: include-unknown-enum-members. When you select it in the admin center, the authentication strength and an every-time sign-in frequency are applied automatically and are mandatory, so the safest way to get the exact shape for your tenant is to create the policy in the admin center and export it.

{
  "displayName": "CA013-AllUsers-HighUserRisk-RequireRemediation",
  "state": "enabledForReportingButNotEnforced",
  "conditions": {
    "users": {
      "includeUsers": ["All"],
      "excludeGroups": ["<GUID-BreakGlassExclusionGroup>"]
    },
    "applications": { "includeApplications": ["All"] },
    "userRiskLevels": ["high"],
    "clientAppTypes": ["all"]
  },
  "grantControls": {
    "operator": "AND",
    "builtInControls": ["riskRemediation"],
    "authenticationStrength": { "id": "<GUID-MFA>" }
  },
  "sessionControls": {
    "signInFrequency": {
      "isEnabled": true,
      "frequencyInterval": "everyTime",
      "authenticationType": "primaryAndSecondaryAuthentication"
    }
  }
}

### CA015: service accounts restricted to trusted networks

Conditional Access for workload identities needs Workload Identities Premium licensing and applies only to single-tenant service principals. Microsoft’s sample uses the Graph beta endpoint.

{
  "displayName": "CA015-ServiceAccounts-LocationRestriction",
  "state": "enabledForReportingButNotEnforced",
  "conditions": {
    "clientApplications": {
      "includeServicePrincipals": ["ServicePrincipalsInMyTenant"]
    },
    "applications": { "includeApplications": ["All"] },
    "locations": {
      "includeLocations": ["All"],
      "excludeLocations": ["<GUID-TrustedNetworks>"]
    }
  },
  "grantControls": {
    "operator": "AND",
    "builtInControls": ["block"]
  }
}

The other policies in the set (CA004, CA005, CA007, CA009 through CA012, CA014, CA016, and CA017) follow the same structure. CA002 is retired; the break-glass exemption is the exclusion on every policy. Export your configured policies as JSON for the Git baseline:

## Illustrative code

The PowerShell in this appendix is illustrative. It hasn’t been tested against a production forest or tenant. Review it, and run it first against a lab forest and a test tenant with read-only permissions. The write operations (creating groups and issues) run only when you call them explicitly.

#Requires -Modules Microsoft.Graph.Identity.SignIns
Connect-MgGraph -Scopes 'Policy.Read.All'

$exportPath = "C:\FMP\Exports\CA_Policies_$(Get-Date -Format 'yyyyMMdd').json"
$policies = Get-MgIdentityConditionalAccessPolicy -All
$policies | ConvertTo-Json -Depth 10 | Out-File -FilePath $exportPath -Encoding UTF8
Write-Host "Exported $($policies.Count) Conditional Access policies to $exportPath" -ForegroundColor Green

Disconnect-MgGraph

## The FMPIdentityAssessment module

The FMPIdentityAssessment module packages the identity assessment and drift functions used in Chapters 09 and 10. It’s a script module (.psm1) with a manifest (.psd1).

### Tooling: Microsoft Graph PowerShell only

The module uses the ActiveDirectory module for the forest and the Microsoft Graph PowerShell SDK for the tenant. It doesn’t use the MSOnline or AzureAD modules, and nothing in this book should. Microsoft deprecated both on March 30, 2024. MSOnline was retired, and stopped working, between early April and late May 2025; AzureAD lost support after March 30, 2025 and was retired in early July 2025. Microsoft’s migration guide and cmdlet map cover the replacements, and the ones that matter for this book are:

| Retired cmdlet | Microsoft Graph PowerShell replacement |
| --- | --- |
| Connect-MsolService, Connect-AzureAD | Connect-MgGraph |
| Get-MsolUser, Get-AzureADUser | Get-MgUser |
| Convert-MsolDomainToStandard | Update-MgDomain -AuthenticationType "Managed" after staged rollout; Remove-MgDomainFederationConfiguration to remove the federation settings |
| Convert-MsolDomainToFederated | New-MgDomainFederationConfiguration |
| Get-AzureADDirectoryRoleMember | Get-MgRoleManagementDirectoryRoleAssignment and the PIM schedule cmdlets |

Role reporting uses the PIM schedule APIs. Active assignments, including activated ones, come from role assignment schedules, whose assignmentType is Assigned for a standing assignment or Activated for one made through PIM; eligible assignments come from Get-MgRoleManagementDirectoryRoleEligibilitySchedule in the Microsoft.Graph.Identity.Governance module. An earlier version of this module tried to tell eligible from active assignments by looking for a ScheduleInfo property on Get-MgRoleManagementDirectoryRoleAssignment output; that property doesn’t exist there, so every assignment was reported as active. The version below fixes it.

### Module manifest

Generate a fresh GUID for your copy with New-Guid; the one shown is a placeholder.

# FMPIdentityAssessment.psd1
@{
    RootModule        = 'FMPIdentityAssessment.psm1'
    ModuleVersion     = '1.1.0'
    GUID              = '00000000-0000-0000-0000-000000000000'   # replace with New-Guid
    Author            = 'Federal Modernization Program Identity Team'
    Description       = 'Federal Modernization Program identity assessment: Active Directory to Microsoft Entra ID'
    PowerShellVersion = '7.4'
    RequiredModules   = @(
        'ActiveDirectory',
        @{ ModuleName = 'Microsoft.Graph.Authentication';        ModuleVersion = '2.0.0' },
        @{ ModuleName = 'Microsoft.Graph.Identity.Governance';   ModuleVersion = '2.0.0' },
        @{ ModuleName = 'Microsoft.Graph.Identity.DirectoryManagement'; ModuleVersion = '2.0.0' },
        @{ ModuleName = 'Microsoft.Graph.Reports';               ModuleVersion = '2.0.0' }
    )
    FunctionsToExport = @(
        'Get-FMPUserInventory',
        'Get-FMPGroupInventory',
        'Get-FMPServiceAccountInventory',
        'Get-FMPPrivilegedAccessReport',
        'Get-FMPLegacyAuthReport',
        'Export-FMPIdentityBaseline',
        'Invoke-FMPIdentityAssessment',
        'Get-FMPGiteaLabelId',
        'New-FMPGiteaDriftIssue'
    )
    CmdletsToExport   = @()
    VariablesToExport = @()
    AliasesToExport   = @()
}

### Module implementation

The module is shown in sections; together they form FMPIdentityAssessment.psm1.

#### Module settings and user inventory

Get-FMPUserInventory exports AD users with the attributes that matter for migration and flags the problems Chapter 09 cares about. Pass -VerifiedDomain with the tenant’s verified domains to test UPN suffixes exactly; without it, the function falls back to a pattern for common non-routable suffixes.

# FMPIdentityAssessment.psm1
# Federal Modernization Program identity assessment module, version 1.1.0
#Requires -Version 7.4

$script:ExportBasePath   = 'C:\FMP\Exports'
$script:GraphEnvironment = 'Global'   # GCC uses the worldwide endpoints

function Get-FMPUserInventory {
    [CmdletBinding()]
    param(
        [string]$SearchBase = (Get-ADDomain).DistinguishedName,
        [string]$ExportPath = "$script:ExportBasePath\Users_$(Get-Date -Format 'yyyyMMdd_HHmmss').json",
        [string[]]$VerifiedDomain,
        [switch]$IncludeDisabled
    )

    $filter = if ($IncludeDisabled) { '*' } else { 'Enabled -eq $true' }
    $properties = @(
        'UserPrincipalName', 'DisplayName', 'GivenName', 'Surname', 'Mail', 'Department',
        'Title', 'Company', 'Manager', 'DistinguishedName', 'Enabled', 'PasswordNeverExpires',
        'PasswordLastSet', 'LastLogonDate', 'WhenCreated', 'WhenChanged', 'MemberOf',
        'ServicePrincipalName', 'AdminCount', 'AccountExpirationDate',
        'extensionAttribute1', 'extensionAttribute2', 'extensionAttribute3', 'extensionAttribute4',
        'extensionAttribute5', 'extensionAttribute6', 'extensionAttribute7', 'extensionAttribute8',
        'extensionAttribute9', 'extensionAttribute10'
    )
    $nonRoutablePattern = '\.(local|internal|corp|lan|ad)$'
    $staleCutoff = (Get-Date).AddDays(-90)

    Write-Host "Collecting AD user inventory from: $SearchBase" -ForegroundColor Cyan
    $adUsers = Get-ADUser -Filter $filter -SearchBase $SearchBase -Properties $properties

    $users = foreach ($u in $adUsers) {
        $suffix = if ($u.UserPrincipalName) { ($u.UserPrincipalName -split '@')[1] } else { $null }
        $isRoutable = if (-not $suffix) { $false }
                      elseif ($VerifiedDomain) { $suffix -in $VerifiedDomain }
                      else { $suffix -notmatch $nonRoutablePattern }
        $spnCount = ($u.ServicePrincipalName | Measure-Object).Count

        $flags = [System.Collections.Generic.List[string]]::new()
        if (-not $isRoutable)                { $flags.Add('UPN_REMEDIATION_REQUIRED') }
        if ($u.PasswordNeverExpires)         { $flags.Add('PASSWORD_NEVER_EXPIRES') }
        if ($u.AdminCount -eq 1)             { $flags.Add('ADMINCOUNT_SET') }
        if ($spnCount -gt 0)                 { $flags.Add('HAS_SPN') }
        if (-not $u.LastLogonDate -or $u.LastLogonDate -lt $staleCutoff) { $flags.Add('STALE_ACCOUNT') }

        [PSCustomObject]@{
            SamAccountName       = $u.SamAccountName
            UPN                  = $u.UserPrincipalName
            UPNSuffix            = $suffix
            IsRoutableUPN        = $isRoutable
            DisplayName          = $u.DisplayName
            Mail                 = $u.Mail
            Department           = $u.Department
            Title                = $u.Title
            Enabled              = $u.Enabled
            PasswordNeverExpires = $u.PasswordNeverExpires
            PasswordLastSet      = $u.PasswordLastSet
            LastLogon            = $u.LastLogonDate
            Created              = $u.WhenCreated
            GroupCount           = ($u.MemberOf | Measure-Object).Count
            HasSPN               = ($spnCount -gt 0)
            AdminCount           = $u.AdminCount
            OU                   = ($u.DistinguishedName -split ',', 2)[1]
            ExtensionAttributes  = [PSCustomObject]@{
                Region         = $u.extensionAttribute1
                Department     = $u.extensionAttribute2
                Division       = $u.extensionAttribute3
                Role           = $u.extensionAttribute4
                CostCenter     = $u.extensionAttribute5
                Classification = $u.extensionAttribute6
                HireDate       = $u.extensionAttribute7
                EndDate        = $u.extensionAttribute8
                ClearanceLevel = $u.extensionAttribute9
                AccountType    = $u.extensionAttribute10
            }
            MigrationFlags       = ($flags -join ',')
        }
    }

    $parent = Split-Path $ExportPath -Parent
    if (-not (Test-Path $parent)) { New-Item -ItemType Directory -Path $parent -Force | Out-Null }
    $users | ConvertTo-Json -Depth 5 | Out-File -FilePath $ExportPath -Encoding UTF8

    Write-Host "Exported $(@($users).Count) users to $ExportPath" -ForegroundColor Green
    Write-Host "  UPN remediation required: $(@($users | Where-Object { $_.MigrationFlags -match 'UPN_REMEDIATION' }).Count)" -ForegroundColor Yellow
    Write-Host "  adminCount set:           $(@($users | Where-Object { $_.AdminCount -eq 1 }).Count)" -ForegroundColor Yellow
    Write-Host "  Stale (over 90 days):     $(@($users | Where-Object { $_.MigrationFlags -match 'STALE' }).Count)" -ForegroundColor Yellow

    return $users
}

Two fixes from the earlier version: the UPN check was inverted inside MigrationFlags (it flagged routable suffixes and passed non-routable ones), and the flag for adminCount was named “AdminSDHolder protected.” adminCount stays at 1 after an account leaves a protected group, so the flag now says what it measures.

#### Group inventory

function Get-FMPGroupInventory {
    [CmdletBinding()]
    param(
        [string]$SearchBase = (Get-ADDomain).DistinguishedName,
        [string]$ExportPath = "$script:ExportBasePath\Groups_$(Get-Date -Format 'yyyyMMdd_HHmmss').json"
    )

    Write-Host "Collecting AD group inventory from: $SearchBase" -ForegroundColor Cyan
    $groups = Get-ADGroup -Filter * -SearchBase $SearchBase -Properties Description, GroupScope,
            GroupCategory, ManagedBy, Members, MemberOf, Mail, WhenCreated, WhenChanged |
        Select-Object @{N = 'Name';          E = { $_.Name } },
                      @{N = 'Description';   E = { $_.Description } },
                      @{N = 'Scope';         E = { $_.GroupScope.ToString() } },
                      @{N = 'Category';      E = { $_.GroupCategory.ToString() } },
                      @{N = 'ManagedBy';     E = {
                            if ($_.ManagedBy) { (Get-ADObject $_.ManagedBy -Properties DisplayName).DisplayName }
                            else { 'UNMANAGED' } } },
                      @{N = 'MemberCount';   E = { ($_.Members | Measure-Object).Count } },
                      @{N = 'NestedInCount'; E = { ($_.MemberOf | Measure-Object).Count } },
                      @{N = 'HasMail';       E = { [bool]$_.Mail } },
                      @{N = 'OU';            E = { ($_.DistinguishedName -split ',', 2)[1] } },
                      @{N = 'Created';       E = { $_.WhenCreated } },
                      @{N = 'Modified';      E = { $_.WhenChanged } },
                      @{N = 'MigrationDecision'; E = {
                            $mc = ($_.Members | Measure-Object).Count
                            if ($mc -eq 0) { 'DECOMMISSION' }
                            elseif ($_.GroupCategory -eq 'Distribution') { 'EVALUATE_M365_GROUP' }
                            elseif ($_.Mail) { 'SYNC_MAIL_ENABLED_SECURITY' }
                            else { 'EVALUATE_SYNC_OR_DYNAMIC' } } }

    $groups | ConvertTo-Json -Depth 5 | Out-File -FilePath $ExportPath -Encoding UTF8
    Write-Host "Exported $(@($groups).Count) groups to $ExportPath" -ForegroundColor Green
    return $groups
}

#### Service account inventory

The earlier module had only a stub here that pointed elsewhere for the body. The module now carries the full function; it’s the same code as Chapter 09, with the export path tied to the module’s base path.

function Get-FMPServiceAccountInventory {
    [CmdletBinding()]
    param(
        [string]$SearchBase = (Get-ADDomain).DistinguishedName,
        [string]$ExportPath = "$script:ExportBasePath\ServiceAccounts_$(Get-Date -Format 'yyyyMMdd_HHmmss').json"
    )

    $results = [System.Collections.Generic.List[object]]::new()
    $staleCutoff = (Get-Date).AddDays(-90)

    $svcUsers = Get-ADUser -SearchBase $SearchBase -Filter {
            (ServicePrincipalName -like '*') -or (SamAccountName -like 'svc-*') -or
            (SamAccountName -like 'svc_*') -or (SamAccountName -like 'sa-*') -or
            (Description -like '*service*account*')
        } -Properties UserPrincipalName, DisplayName, Description, ServicePrincipalName,
                      Enabled, PasswordNeverExpires, PasswordLastSet, LastLogonDate,
                      WhenCreated, MemberOf, DistinguishedName

    foreach ($svc in $svcUsers) {
        $spnCount = ($svc.ServicePrincipalName | Measure-Object).Count
        $daysSincePasswordChange = if ($svc.PasswordLastSet) {
            (New-TimeSpan -Start $svc.PasswordLastSet -End (Get-Date)).Days
        } else { -1 }

        $recommendation = switch ($true) {
            (-not $svc.Enabled)                   { 'Disabled: verify and retire'; break }
            ($svc.LastLogonDate -lt $staleCutoff) { 'Stale: verify use and retire if unused'; break }
            ($svc.PasswordNeverExpires)           { 'HIGH RISK: move to a workload identity (federated credential, managed identity, or certificate)'; break }
            ($spnCount -gt 0)                     { 'Kerberos service: convert to gMSA, then evaluate workload identity federation'; break }
            default                               { 'Evaluate the workload; target a managed identity or application registration' }
        }

        $riskLevel = if ($svc.Enabled -and $svc.PasswordNeverExpires) { 'HIGH' }
                     elseif ($daysSincePasswordChange -gt 365)          { 'HIGH' }
                     elseif ($svc.Enabled)                              { 'MEDIUM' }
                     else                                               { 'LOW' }

        $results.Add([PSCustomObject]@{
            Type                    = 'TraditionalServiceAccount'
            SamAccountName          = $svc.SamAccountName
            DisplayName             = $svc.DisplayName
            Description             = $svc.Description
            Enabled                 = $svc.Enabled
            PasswordNeverExpires    = $svc.PasswordNeverExpires
            DaysSincePasswordChange = $daysSincePasswordChange
            SPNCount                = $spnCount
            SPNs                    = ($svc.ServicePrincipalName -join '; ')
            LastLogon               = $svc.LastLogonDate
            GroupMembershipCount    = ($svc.MemberOf | Measure-Object).Count
            OU                      = ($svc.DistinguishedName -split ',', 2)[1]
            RiskLevel               = $riskLevel
            Recommendation          = $recommendation
        })
    }

    $msaAccounts = Get-ADServiceAccount -Filter * -SearchBase $SearchBase -Properties Enabled,
        DistinguishedName, ObjectClass, 'msDS-ManagedPasswordInterval', WhenCreated

    foreach ($msa in $msaAccounts) {
        $isGmsa = ($msa.ObjectClass -eq 'msDS-GroupManagedServiceAccount')
        $results.Add([PSCustomObject]@{
            Type                    = if ($isGmsa) { 'gMSA' } else { 'MSA' }
            SamAccountName          = $msa.SamAccountName
            DisplayName             = $msa.SamAccountName
            Description             = ''
            Enabled                 = $msa.Enabled
            PasswordNeverExpires    = $false
            DaysSincePasswordChange = 0
            SPNCount                = 0
            SPNs                    = ''
            LastLogon               = $null
            GroupMembershipCount    = 0
            OU                      = ($msa.DistinguishedName -split ',', 2)[1]
            RiskLevel               = 'LOW'
            Recommendation          = if ($isGmsa) {
                'Keep for on-premises workloads; plan workload identity federation when the workload moves'
            } else {
                'Upgrade to gMSA first, then evaluate for cloud migration'
            }
        })
    }

    $results | ConvertTo-Json -Depth 5 | Out-File -FilePath $ExportPath -Encoding UTF8
    Write-Host "Service account inventory: $($results.Count) accounts exported to $ExportPath" -ForegroundColor Green
    return $results
}

#### Privileged access report

function Get-FMPPrivilegedAccessReport {
    [CmdletBinding()]
    param(
        [switch]$Last24Hours,
        [string]$ExportPath = "$script:ExportBasePath\PrivilegedAccess_$(Get-Date -Format 'yyyyMMdd_HHmmss').json"
    )

    Connect-MgGraph -Scopes 'RoleManagement.Read.Directory', 'AuditLog.Read.All' -Environment $script:GraphEnvironment -NoWelcome

    # Role definitions, for display names
    $roleNames = @{}
    Get-MgRoleManagementDirectoryRoleDefinition -All |
        ForEach-Object { $roleNames[$_.Id] = $_.DisplayName }

    function ConvertTo-FMPRoleRow {
        param($Item, [string]$Kind)
        [PSCustomObject]@{
            RoleName      = $roleNames[$Item.RoleDefinitionId]
            PrincipalName = if ($Item.Principal.AdditionalProperties.displayName) {
                                $Item.Principal.AdditionalProperties.displayName } else { $Item.PrincipalId }
            PrincipalType = ($Item.Principal.AdditionalProperties.'@odata.type' -replace '#microsoft.graph.', '')
            Kind          = $Kind
            Expiration    = $Item.ScheduleInfo.Expiration.Type   # noExpiration means permanent
            EndDateTime   = $Item.ScheduleInfo.Expiration.EndDateTime
            DirectoryScope = $Item.DirectoryScopeId
        }
    }

    # Active assignments: AssignmentType is 'Assigned' (standing) or 'Activated' (via PIM)
    $active = Get-MgRoleManagementDirectoryRoleAssignmentSchedule -All -ExpandProperty Principal |
        ForEach-Object { ConvertTo-FMPRoleRow -Item $_ -Kind "Active-$($_.AssignmentType)" }

    # Eligible assignments
    $eligible = Get-MgRoleManagementDirectoryRoleEligibilitySchedule -All -ExpandProperty Principal |
        ForEach-Object { ConvertTo-FMPRoleRow -Item $_ -Kind 'Eligible' }

    $activations = @()
    if ($Last24Hours) {
        $since = (Get-Date).ToUniversalTime().AddHours(-24).ToString('yyyy-MM-ddTHH:mm:ssZ')
        $auditFilter = "activityDateTime ge $since and activityDisplayName eq 'Add member to role completed (PIM activation)'"
        $activations = Get-MgAuditLogDirectoryAudit -Filter $auditFilter -All |
            Select-Object ActivityDateTime,
                          @{N = 'InitiatedBy'; E = { $_.InitiatedBy.User.UserPrincipalName } },
                          @{N = 'Role';        E = { ($_.TargetResources | Where-Object Type -eq 'Role').DisplayName } }
    }

    $report = [PSCustomObject]@{
        GeneratedAt          = (Get-Date).ToUniversalTime().ToString('o')
        ActiveAssignments    = @($active)
        EligibleAssignments  = @($eligible)
        RecentActivations    = @($activations)
    }
    $report | ConvertTo-Json -Depth 6 | Out-File -FilePath $ExportPath -Encoding UTF8

    $standing = @($active | Where-Object { $_.Kind -eq 'Active-Assigned' -and $_.Expiration -eq 'noExpiration' })
    Write-Host "Privileged access report exported to $ExportPath" -ForegroundColor Green
    Write-Host "  Eligible assignments:          $(@($eligible).Count)"
    Write-Host "  Permanent active assignments:  $($standing.Count) (target: the emergency accounts only)" -ForegroundColor Yellow
    if ($Last24Hours) { Write-Host "  PIM activations, last 24 hours: $(@($activations).Count)" }

    Disconnect-MgGraph | Out-Null
    return $report
}

The activation filter uses the activity name from Microsoft’s audit activity reference. Off-hours analysis (Chapter 10’s detection) runs on the exported RecentActivations, after converting ActivityDateTime from UTC to local time.

#### Legacy authentication report

function Get-FMPLegacyAuthReport {
    [CmdletBinding()]
    param(
        [int]$DaysBack = 30,
        [string]$ExportPath = "$script:ExportBasePath\LegacyAuth_$(Get-Date -Format 'yyyyMMdd_HHmmss').json"
    )

    Connect-MgGraph -Scopes 'AuditLog.Read.All' -Environment $script:GraphEnvironment -NoWelcome

    $legacyClients = @('Exchange ActiveSync', 'Authenticated SMTP', 'POP3', 'IMAP4',
                       'Other clients', 'Outlook Anywhere (RPC over HTTP)')
    $startDate = (Get-Date).ToUniversalTime().AddDays(-$DaysBack).ToString('yyyy-MM-ddTHH:mm:ssZ')
    $filter = "createdDateTime ge $startDate and status/errorCode eq 0"

    Write-Host "Scanning sign-in logs for legacy authentication (last $DaysBack days)..." -ForegroundColor Cyan
    $signIns = Get-MgAuditLogSignIn -Filter $filter -All |
        Where-Object { $_.ClientAppUsed -in $legacyClients }

    $report = $signIns |
        Group-Object -Property UserPrincipalName, ClientAppUsed |
        Select-Object @{N = 'UserPrincipalName'; E = { ($_.Name -split ', ')[0] } },
                      @{N = 'ClientApp';         E = { ($_.Name -split ', ')[1] } },
                      @{N = 'SignInCount';       E = { $_.Count } },
                      @{N = 'LastSignIn';        E = { ($_.Group | Sort-Object CreatedDateTime -Descending |
                                                        Select-Object -First 1).CreatedDateTime } },
                      @{N = 'RemediationAction'; E = {
                            switch (($_.Name -split ', ')[1]) {
                                'Authenticated SMTP'  { 'Move to OAuth SMTP, the Microsoft Graph sendMail API, or a supported relay' }
                                'POP3'                { 'Move to the Microsoft Graph mail API or POP with OAuth' }
                                'IMAP4'               { 'Move to the Microsoft Graph mail API or IMAP with OAuth' }
                                'Exchange ActiveSync' { 'Move to Outlook mobile with an Intune app protection policy' }
                                default               { 'Identify the application and move it to modern authentication' }
                            } } }

    $report | ConvertTo-Json -Depth 5 | Out-File -FilePath $ExportPath -Encoding UTF8
    Write-Host "Legacy authentication report exported to $ExportPath" -ForegroundColor Green
    Write-Host "  Users with legacy sign-ins: $(@($report | Select-Object -Unique UserPrincipalName).Count)" -ForegroundColor Yellow
    Write-Host "  Total legacy sign-ins:      $(($report | Measure-Object -Property SignInCount -Sum).Sum)" -ForegroundColor Yellow

    Disconnect-MgGraph | Out-Null
    return $report
}

#### Baseline export

function Export-FMPIdentityBaseline {
    [CmdletBinding()]
    param(
        [string]$SearchBase = (Get-ADDomain).DistinguishedName,
        [string]$BaselinePath = "$script:ExportBasePath\Baseline_$(Get-Date -Format 'yyyyMMdd_HHmmss')",
        [string[]]$VerifiedDomain
    )

    if (-not (Test-Path $BaselinePath)) { New-Item -ItemType Directory -Path $BaselinePath -Force | Out-Null }
    Write-Host "=== Federal Modernization Program identity baseline export ===" -ForegroundColor Cyan
    Write-Host "Output directory: $BaselinePath" -ForegroundColor Cyan

    $users  = Get-FMPUserInventory -SearchBase $SearchBase -ExportPath "$BaselinePath\users.json" -VerifiedDomain $VerifiedDomain
    $groups = Get-FMPGroupInventory -SearchBase $SearchBase -ExportPath "$BaselinePath\groups.json"
    $svc    = Get-FMPServiceAccountInventory -SearchBase $SearchBase -ExportPath "$BaselinePath\service_accounts.json"

    [PSCustomObject]@{
        GeneratedAt         = (Get-Date).ToUniversalTime().ToString('o')
        SearchBase          = $SearchBase
        Domain              = (Get-ADDomain).DNSRoot
        Forest              = (Get-ADForest).Name
        UserCount           = @($users).Count
        GroupCount          = @($groups).Count
        ServiceAccountCount = @($svc).Count
        ModuleVersion       = '1.1.0'
    } | ConvertTo-Json | Out-File -FilePath "$BaselinePath\metadata.json" -Encoding UTF8

    Write-Host "`n=== Baseline export complete: $BaselinePath ===" -ForegroundColor Green
}

#### Drift issues in the Git host

These two functions open a drift issue through the Gitea REST API: a token in an Authorization: token <value> header, endpoints under /api/v1/, and label IDs as integers on the new issue. The Markdown code fence inside the issue body is built from a variable so that the body doesn’t depend on PowerShell’s backtick escaping.

function Get-FMPGiteaLabelId {
    [CmdletBinding()]
    param(
        [Parameter(Mandatory)][string]$Name,
        [string]$GiteaBaseUrl = $env:FMP_GITEA_URL,
        [string]$RepoOwner    = $env:FMP_GITEA_OWNER,
        [string]$RepoName     = 'fmp-identity-baseline',
        [string]$ApiToken     = $env:FMP_GITEA_TOKEN
    )
    $headers = @{ Authorization = "token $ApiToken" }
    $labels = Invoke-RestMethod -Uri "$GiteaBaseUrl/api/v1/repos/$RepoOwner/$RepoName/labels" -Headers $headers -Method Get
    ($labels | Where-Object name -eq $Name | Select-Object -First 1).id
}

function New-FMPGiteaDriftIssue {
    [CmdletBinding(SupportsShouldProcess)]
    param(
        [Parameter(Mandatory)][string]$DriftSummary,
        [Parameter(Mandatory)][ValidateSet('Low', 'Medium', 'High', 'Critical')][string]$Severity,
        [Parameter(Mandatory)][string]$DiffContent,
        [string]$GiteaBaseUrl = $env:FMP_GITEA_URL,
        [string]$RepoOwner    = $env:FMP_GITEA_OWNER,
        [string]$RepoName     = 'fmp-identity-baseline',
        [string]$ApiToken     = $env:FMP_GITEA_TOKEN
    )

    $severityLabel = "priority/$($Severity.ToLower())"
    $labelIds = @(
        Get-FMPGiteaLabelId -Name $severityLabel  -GiteaBaseUrl $GiteaBaseUrl -RepoOwner $RepoOwner -RepoName $RepoName -ApiToken $ApiToken
        Get-FMPGiteaLabelId -Name 'identity-drift' -GiteaBaseUrl $GiteaBaseUrl -RepoOwner $RepoOwner -RepoName $RepoName -ApiToken $ApiToken
    ) | Where-Object { $_ }

    $fence = '```'
    $detected = (Get-Date).ToUniversalTime().ToString('yyyy-MM-dd HH:mm:ss') + ' UTC'
    $issueBody = @"
## Identity drift detection report

**Detected:** $detected
**Severity:** $Severity
**Summary:** $DriftSummary

### Diff

${fence}json
$DiffContent
${fence}

### Recommended actions

- Review the diff for unauthorized changes.
- Cross-check against change management records.
- Fix the source record or rule for unauthorized drift; update the baseline only for approved changes.
- Commit the updated baseline to Git.

*Generated by Invoke-FMPIdentityAssessment*
"@

    $body = @{
        title  = "[Identity Drift] $DriftSummary - $(Get-Date -Format 'yyyy-MM-dd')"
        body   = $issueBody
        labels = @($labelIds)
    } | ConvertTo-Json -Depth 5

    $headers = @{ Authorization = "token $ApiToken"; 'Content-Type' = 'application/json' }
    $uri = "$GiteaBaseUrl/api/v1/repos/$RepoOwner/$RepoName/issues"

    if ($PSCmdlet.ShouldProcess($uri, 'Create drift issue')) {
        try {
            $response = Invoke-RestMethod -Uri $uri -Method Post -Headers $headers -Body $body
            Write-Host "Created issue #$($response.number): $($response.title)" -ForegroundColor Green
            return $response
        }
        catch {
            Write-Error "Failed to create the drift issue: $_"
        }
    }
}

#### The orchestrator

Invoke-FMPIdentityAssessment runs the inventories, the Entra ID reports, and, with -Compare, a user-level drift comparison against a previous baseline. -CommitToGitea opens an issue when drift is found; committing the new baseline to the repository is a separate git step in the scheduled job. The earlier version printed an ASCII-art banner of a former program name; it’s been replaced with a plain header.

function Invoke-FMPIdentityAssessment {
    [CmdletBinding()]
    param(
        [string]$SearchBase = (Get-ADDomain).DistinguishedName,
        [string[]]$VerifiedDomain,
        [switch]$Compare,
        [string]$PreviousBaselinePath,
        [switch]$CommitToGitea
    )

    Write-Host "Federal Modernization Program: identity modernization assessment v1.1.0" -ForegroundColor Cyan
    $assessmentPath = "$script:ExportBasePath\Assessment_$(Get-Date -Format 'yyyyMMdd_HHmmss')"

    Write-Host "`n[1/4] Active Directory inventory" -ForegroundColor Yellow
    Export-FMPIdentityBaseline -SearchBase $SearchBase -BaselinePath $assessmentPath -VerifiedDomain $VerifiedDomain

    Write-Host "`n[2/4] Entra ID privileged access" -ForegroundColor Yellow
    Get-FMPPrivilegedAccessReport -ExportPath "$assessmentPath\privileged_access.json" | Out-Null

    Write-Host "`n[3/4] Legacy authentication" -ForegroundColor Yellow
    Get-FMPLegacyAuthReport -ExportPath "$assessmentPath\legacy_auth.json" | Out-Null

    if ($Compare -and $PreviousBaselinePath) {
        Write-Host "`n[4/4] Drift comparison" -ForegroundColor Yellow
        $currentUsers  = Get-Content "$assessmentPath\users.json" -Raw | ConvertFrom-Json
        $previousUsers = Get-Content "$PreviousBaselinePath\users.json" -Raw | ConvertFrom-Json

        $newUsers     = $currentUsers  | Where-Object { $_.SamAccountName -notin $previousUsers.SamAccountName }
        $removedUsers = $previousUsers | Where-Object { $_.SamAccountName -notin $currentUsers.SamAccountName }

        $drift = [PSCustomObject]@{
            NewUsers      = @($newUsers).Count
            RemovedUsers  = @($removedUsers).Count
            TotalCurrent  = @($currentUsers).Count
            TotalPrevious = @($previousUsers).Count
            NewUserNames     = @($newUsers.SamAccountName)
            RemovedUserNames = @($removedUsers.SamAccountName)
            DriftDetected = (@($newUsers).Count + @($removedUsers).Count) -gt 0
        }
        $drift | ConvertTo-Json -Depth 4 | Out-File -FilePath "$assessmentPath\drift_report.json" -Encoding UTF8
        Write-Host "Drift: $($drift.NewUsers) new, $($drift.RemovedUsers) removed" -ForegroundColor $(if ($drift.DriftDetected) { 'Yellow' } else { 'Green' })

        if ($CommitToGitea -and $drift.DriftDetected) {
            $total = $drift.NewUsers + $drift.RemovedUsers
            $severity = if ($total -gt 50) { 'High' } elseif ($total -gt 10) { 'Medium' } else { 'Low' }
            New-FMPGiteaDriftIssue -DriftSummary "$($drift.NewUsers) new users, $($drift.RemovedUsers) removed users" `
                -Severity $severity -DiffContent (Get-Content "$assessmentPath\drift_report.json" -Raw)
        }
    }
    else {
        Write-Host "`n[4/4] Skipped: no comparison baseline given" -ForegroundColor DarkGray
    }

    Write-Host "`n=== Assessment complete: $assessmentPath ===" -ForegroundColor Green
    Write-Host "Next: review the output and commit it to the identity-baseline branch." -ForegroundColor Cyan
}

The comparison covers user additions and removals only. Attribute-level drift, group membership drift, and the Conditional Access policy diff are listed as planned scheduled tasks in Chapter 10; until they’re built, compare those exports in Git directly.

## Continue the book

← Previous: Appendix B — Forest Assessment Module · Book index

Office of Management and Budget, M-22-09, Moving the U.S. Government Toward Zero Trust Cybersecurity Principles, January 26, 2022, https://www.whitehouse.gov/wp-content/uploads/2022/01/M-22-09.pdf (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-207, Zero Trust Architecture, August 2020, https://csrc.nist.gov/pubs/sp/800/207/final (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, Zero Trust Maturity Model, Version 2.0, April 2023, section 5.1 (Identity), https://www.cisa.gov/sites/default/files/2023-04/CISA_Zero_Trust_Maturity_Model_Version_2_508c.pdf (accessed Oct 20, 2026).

Office of Management and Budget, M-22-09, Moving the U.S. Government Toward Zero Trust Cybersecurity Principles, January 26, 2022, https://www.whitehouse.gov/wp-content/uploads/2022/01/M-22-09.pdf (accessed Oct 20, 2026).

Microsoft Learn, “Users in Active Directory Domain Services,” https://learn.microsoft.com/en-us/windows/win32/ad/users-in-active-directory-domain-services (accessed Oct 20, 2026).

Microsoft Learn, “Cloud transformation posture” (road to the cloud), https://learn.microsoft.com/en-us/entra/architecture/road-to-the-cloud-posture (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, “ASD’s ACSC, CISA, and US and International Partners Release Guidance on Detecting and Mitigating Active Directory Compromises,” September 2024, https://www.cisa.gov/news-events/alerts/2024/09/25/asds-acsc-cisa-and-us-and-international-partners-release-guidance-detecting-and-mitigating-active (accessed Oct 20, 2026).

Microsoft Learn, “New name for Azure Active Directory” (FAQ: “Does Microsoft still support on-premises identity management?”), https://learn.microsoft.com/en-us/entra/fundamentals/new-name (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect Sync: Understand and customize synchronization,” https://learn.microsoft.com/en-us/entra/identity/hybrid/connect/how-to-connect-sync-whatis (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra releases and announcements” (April 2026: “Upcoming Change - Migrate from Microsoft Entra Connect Sync to Microsoft Entra Cloud Sync”; January 2026: “General Availability - Ability to convert Source of Authority of synced on-premises AD users to cloud users”), https://learn.microsoft.com/en-us/entra/fundamentals/whats-new (accessed Oct 20, 2026).

Microsoft Learn, “Migrate from federation to cloud authentication,” https://learn.microsoft.com/en-us/entra/identity/hybrid/connect/migrate-from-federation-to-cloud-authentication (accessed Oct 20, 2026).

Microsoft Learn, “Protect Microsoft 365 from on-premises attacks,” https://learn.microsoft.com/en-us/entra/architecture/protect-m365-from-on-premises-attacks (accessed Oct 20, 2026).

Microsoft Learn, “Deprecated features for Windows client” (NTLM, deprecation announced June 2024), https://learn.microsoft.com/en-us/windows/whats-new/deprecated-features (accessed Oct 20, 2026).

Microsoft Learn, “Cloud transformation posture” (road to the cloud), https://learn.microsoft.com/en-us/entra/architecture/road-to-the-cloud-posture (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra releases and announcements” (April 2026: “Upcoming Change - Migrate from Microsoft Entra Connect Sync to Microsoft Entra Cloud Sync”; January 2026: “General Availability - Ability to convert Source of Authority of synced on-premises AD users to cloud users”), https://learn.microsoft.com/en-us/entra/fundamentals/whats-new (accessed Oct 20, 2026).

Microsoft Learn, “Embrace cloud-first posture: Convert Group Source of Authority to the cloud,” https://learn.microsoft.com/en-us/entra/identity/hybrid/concept-source-of-authority-overview (accessed Oct 20, 2026).

Microsoft Learn, “Cloud transformation posture” (road to the cloud), https://learn.microsoft.com/en-us/entra/architecture/road-to-the-cloud-posture (accessed Oct 20, 2026).

Microsoft Learn, “Skype for Business Online retirement,” https://learn.microsoft.com/en-us/microsoftteams/skype-for-business-online-retirement (accessed Oct 20, 2026).

Microsoft Learn, “Exchange Server 2019 and 2016 end of support roadmap,” https://learn.microsoft.com/en-us/troubleshoot/exchange/administration/exchange-2019-2016-end-of-support (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra for Zero Trust: Protect identities and secrets” (privileged accounts are cloud-native identities), https://learn.microsoft.com/en-us/entra/fundamentals/zero-trust-protect-identities (accessed Oct 20, 2026).

Microsoft Learn, “Protect Microsoft 365 from on-premises attacks,” https://learn.microsoft.com/en-us/entra/architecture/protect-m365-from-on-premises-attacks (accessed Oct 20, 2026).

Microsoft Learn, “Protect Microsoft 365 from on-premises attacks,” https://learn.microsoft.com/en-us/entra/architecture/protect-m365-from-on-premises-attacks (accessed Oct 20, 2026).

Microsoft Learn, “Protect Microsoft 365 from on-premises attacks,” https://learn.microsoft.com/en-us/entra/architecture/protect-m365-from-on-premises-attacks (accessed Oct 20, 2026).

Microsoft Learn, “Users in Active Directory Domain Services,” https://learn.microsoft.com/en-us/windows/win32/ad/users-in-active-directory-domain-services (accessed Oct 20, 2026).

Microsoft Learn, “Kerberos Policy,” https://learn.microsoft.com/en-us/windows/win32/secauthn/kerberos-policy (accessed Oct 20, 2026).

Microsoft Learn, “Group Policy processing,” https://learn.microsoft.com/en-us/windows-server/identity/ad-ds/manage/group-policy/group-policy-processing (accessed Oct 20, 2026).

Microsoft Learn, “Cloud transformation posture” (road to the cloud), https://learn.microsoft.com/en-us/entra/architecture/road-to-the-cloud-posture (accessed Oct 20, 2026).

Microsoft Learn, “Administrative units in Microsoft Entra ID” (Constraints; Groups), https://learn.microsoft.com/en-us/entra/identity/role-based-access-control/administrative-units (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra service limits and restrictions” (Administrative units), https://learn.microsoft.com/en-us/entra/identity/users/directory-service-limits-restrictions (accessed Oct 20, 2026).

Microsoft Learn, “Manage users or devices for an administrative unit with rules for dynamic membership groups,” https://learn.microsoft.com/en-us/entra/identity/role-based-access-control/admin-units-members-dynamic (accessed Oct 20, 2026).

Microsoft Learn, “Administrative units in Microsoft Entra ID” (Constraints; Groups), https://learn.microsoft.com/en-us/entra/identity/role-based-access-control/administrative-units (accessed Oct 20, 2026).

Microsoft Learn, “Manage users or devices for an administrative unit with rules for dynamic membership groups,” https://learn.microsoft.com/en-us/entra/identity/role-based-access-control/admin-units-members-dynamic (accessed Oct 20, 2026).

Microsoft Learn, “onPremisesExtensionAttributes resource type,” Microsoft Graph v1.0, https://learn.microsoft.com/en-us/graph/api/resources/onpremisesextensionattributes?view=graph-rest-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra releases and announcements” (January 2026: “General Availability - Ability to convert Source of Authority of synced on-premises AD users to cloud users”), https://learn.microsoft.com/en-us/entra/fundamentals/whats-new (accessed Oct 20, 2026).

Microsoft Learn, “Administrative units in Microsoft Entra ID” (Constraints; Groups), https://learn.microsoft.com/en-us/entra/identity/role-based-access-control/administrative-units (accessed Oct 20, 2026).

Microsoft Learn, “Assign Microsoft Entra roles” (Roles that can be assigned with administrative unit scope), https://learn.microsoft.com/en-us/entra/identity/role-based-access-control/manage-roles-portal (accessed Oct 20, 2026).

Microsoft Learn, “Assign Microsoft Entra roles” (Roles that can be assigned with administrative unit scope), https://learn.microsoft.com/en-us/entra/identity/role-based-access-control/manage-roles-portal (accessed Oct 20, 2026).

Microsoft Learn, “Assign Microsoft Entra roles” (Roles that can be assigned with administrative unit scope), https://learn.microsoft.com/en-us/entra/identity/role-based-access-control/manage-roles-portal (accessed Oct 20, 2026).

Microsoft Learn, “Protect Microsoft 365 from on-premises attacks” (Isolate privileged identities), https://learn.microsoft.com/en-us/entra/architecture/protect-m365-from-on-premises-attacks (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra built-in roles” (Application Administrator; Cloud Application Administrator), https://learn.microsoft.com/en-us/entra/identity/role-based-access-control/permissions-reference (accessed Oct 20, 2026).

Microsoft Learn, “Max-Ticket-Age attribute,” Active Directory schema, https://learn.microsoft.com/en-us/windows/win32/adschema/a-maxticketage (accessed Oct 20, 2026).

Microsoft Learn, “Max-Renew-Age attribute,” Active Directory schema, https://learn.microsoft.com/en-us/windows/win32/adschema/a-maxrenewage (accessed Oct 20, 2026).

Microsoft Learn, “Group Policy processing,” https://learn.microsoft.com/en-us/windows-server/identity/ad-ds/manage/group-policy/group-policy-processing (accessed Oct 20, 2026).

Microsoft Learn, “Windows 7 Clients intermittently fail to apply group policy at startup,” https://learn.microsoft.com/en-us/troubleshoot/windows-client/group-policy/fail-to-apply-group-policy-at-startup (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-207, Zero Trust Architecture, August 2020, section 2.1 (tenet 6), https://csrc.nist.gov/pubs/sp/800/207/final (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, Zero Trust Maturity Model, Version 2.0, April 2023, Table 2 (Identity pillar, Authentication), https://www.cisa.gov/sites/default/files/2023-04/CISA_Zero_Trust_Maturity_Model_Version_2_508c.pdf (accessed Oct 20, 2026).

Microsoft Learn, “Continuous access evaluation,” https://learn.microsoft.com/en-us/entra/identity/conditional-access/concept-continuous-access-evaluation (accessed Oct 20, 2026).

FedRAMP, “FedRAMP 20x,” https://www.fedramp.gov/20x/ (accessed Oct 20, 2026).

Foundations for Evidence-Based Policymaking Act of 2018, Pub. L. No. 115-435, approved January 14, 2019, Title II (OPEN Government Data Act), https://www.govinfo.gov/content/pkg/PLAW-115publ435/html/PLAW-115publ435.htm (accessed Oct 20, 2026).

Microsoft Learn, “What is Conditional Access?,” https://learn.microsoft.com/entra/identity/conditional-access/overview (accessed Oct 20, 2026).

Microsoft Learn, “Cloud-native endpoints and on-premises resources,” https://learn.microsoft.com/intune/solutions/cloud-native-endpoints/on-premises-resources (accessed Oct 20, 2026).

Microsoft Learn, “Implement password hash synchronization with Microsoft Entra Connect Sync,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-password-hash-synchronization (accessed Oct 20, 2026).

IETF, RFC 4120, The Kerberos Network Authentication Service (V5), July 2005, https://www.rfc-editor.org/rfc/rfc4120 (accessed Oct 20, 2026).

IETF, RFC 4178, The Simple and Protected Generic Security Service Application Program Interface (GSS-API) Negotiation Mechanism, October 2005, https://www.rfc-editor.org/rfc/rfc4178 (accessed Oct 20, 2026).

IETF, RFC 6749, The OAuth 2.0 Authorization Framework, October 2012, https://www.rfc-editor.org/rfc/rfc6749 (accessed Oct 20, 2026).

OpenID Foundation, OpenID Connect Core 1.0 incorporating errata set 2, https://openid.net/specs/openid-connect-core-1_0.html (accessed Oct 20, 2026).

IETF, RFC 7643, System for Cross-domain Identity Management: Core Schema, September 2015, https://www.rfc-editor.org/rfc/rfc7643 (accessed Oct 20, 2026).

IETF, RFC 7644, System for Cross-domain Identity Management: Protocol, September 2015, https://www.rfc-editor.org/rfc/rfc7644 (accessed Oct 20, 2026).

Microsoft Learn, “SCIM support in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/app-provisioning/scim-support-in-entra-id (accessed Oct 20, 2026).

Microsoft Learn, “Proof-of-Possession (PoP) tokens,” MSAL.NET documentation, https://learn.microsoft.com/entra/msal/dotnet/advanced/proof-of-possession-tokens (accessed Oct 20, 2026).

IETF, RFC 8705, OAuth 2.0 Mutual-TLS Client Authentication and Certificate-Bound Access Tokens, February 2020, https://www.rfc-editor.org/rfc/rfc8705 (accessed Oct 20, 2026).

IETF, RFC 9449, OAuth 2.0 Demonstrating Proof of Possession (DPoP), September 2023, https://www.rfc-editor.org/rfc/rfc9449 (accessed Oct 20, 2026).

Microsoft Learn, “Token Protection in Microsoft Entra Conditional Access,” https://learn.microsoft.com/entra/identity/conditional-access/concept-token-protection (accessed Oct 20, 2026).

Microsoft Learn, “Meet multifactor authentication requirements of memorandum 22-09,” https://learn.microsoft.com/entra/standards/memo-22-09-multi-factor-authentication (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra certificate-based authentication?,” https://learn.microsoft.com/entra/identity/authentication/concept-certificate-based-authentication (accessed Oct 20, 2026).

Microsoft Learn, “Windows authentication - Kerberos constrained delegation with Microsoft Entra ID,” https://learn.microsoft.com/entra/architecture/auth-kcd (accessed Oct 20, 2026).

Microsoft Learn, “What is Conditional Access?,” https://learn.microsoft.com/entra/identity/conditional-access/overview (accessed Oct 20, 2026).

Microsoft Learn, “Conditional Access: Conditions,” https://learn.microsoft.com/entra/identity/conditional-access/concept-conditional-access-conditions (accessed Oct 20, 2026).

Microsoft Learn, “Cloud-native endpoints and on-premises resources,” https://learn.microsoft.com/intune/solutions/cloud-native-endpoints/on-premises-resources (accessed Oct 20, 2026).

Microsoft Learn, “Deprecated features for Windows client,” https://learn.microsoft.com/windows/whats-new/deprecated-features (accessed Oct 20, 2026).

Microsoft Learn, “Deprecated features for Windows client,” https://learn.microsoft.com/windows/whats-new/deprecated-features (accessed Oct 20, 2026).

Microsoft Learn, “Windows message center,” entry “Take action: NTLMv1 hardening changes might affect network connections on devices without Credential Guard,” October 14, 2026, https://learn.microsoft.com/windows/release-health/windows-message-center (accessed Oct 20, 2026).

Microsoft Learn, “Features removed or no longer developed in Windows Server,” https://learn.microsoft.com/windows-server/get-started/removed-deprecated-features-windows-server (accessed Oct 20, 2026).

Microsoft Windows IT Pro Blog, “Advancing Windows security: Disabling NTLM by default,” January 29, 2026, https://techcommunity.microsoft.com/blog/windows-itpro-blog/advancing-windows-security-disabling-ntlm-by-default/4489526 (accessed Oct 20, 2026).

Microsoft Learn, “Features removed or no longer developed in Windows Server,” https://learn.microsoft.com/windows-server/get-started/removed-deprecated-features-windows-server (accessed Oct 20, 2026).

Microsoft Learn, “Features removed or no longer developed in Windows Server,” https://learn.microsoft.com/windows-server/get-started/removed-deprecated-features-windows-server (accessed Oct 20, 2026).

Microsoft Learn, “LDAP signing overview for Active Directory Domain Services,” https://learn.microsoft.com/windows-server/identity/ad-ds/ldap-signing (accessed Oct 20, 2026).

Microsoft Learn, “LDAP channel binding overview for Active Directory Domain Services,” https://learn.microsoft.com/windows-server/identity/ad-ds/ldap-channel-binding (accessed Oct 20, 2026).

Microsoft Windows IT Pro Blog, “Advancing Windows security: Disabling NTLM by default,” January 29, 2026, https://techcommunity.microsoft.com/blog/windows-itpro-blog/advancing-windows-security-disabling-ntlm-by-default/4489526 (accessed Oct 20, 2026).

Microsoft Learn, “Implement password hash synchronization with Microsoft Entra Connect Sync,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-password-hash-synchronization (accessed Oct 20, 2026).

Microsoft Learn, “Implement password hash synchronization with Microsoft Entra Connect Sync,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-password-hash-synchronization (accessed Oct 20, 2026).

Microsoft Learn, “Features removed or no longer developed in Windows Server,” https://learn.microsoft.com/windows-server/get-started/removed-deprecated-features-windows-server (accessed Oct 20, 2026).

Microsoft Learn, “Access tokens in the Microsoft identity platform,” https://learn.microsoft.com/entra/identity-platform/access-tokens (accessed Oct 20, 2026).

Microsoft Learn, “How Application Provisioning works in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/app-provisioning/how-provisioning-works (accessed Oct 20, 2026).

Microsoft Learn, “Meet multifactor authentication requirements of memorandum 22-09,” https://learn.microsoft.com/entra/standards/memo-22-09-multi-factor-authentication (accessed Oct 20, 2026).

Microsoft Learn, “Access tokens in the Microsoft identity platform,” https://learn.microsoft.com/entra/identity-platform/access-tokens (accessed Oct 20, 2026).

Microsoft Learn, “Configure the Active Directory Web Services (ADWS) to start automatically on all the servers,” Microsoft Engage Center, https://learn.microsoft.com/services-hub/microsoft-engage-center/health/remediation-steps-ad/configure-the-active-directory-web-services-adws-to-start-automatically-on-all-servers (accessed Oct 20, 2026).

Microsoft Learn, “Upgrade from Azure AD PowerShell to Microsoft Graph PowerShell,” https://learn.microsoft.com/powershell/microsoftgraph/migration-steps (accessed Oct 20, 2026).

Microsoft Learn, “Overview of the Microsoft Authentication Library (MSAL),” https://learn.microsoft.com/entra/msal/overview (accessed Oct 20, 2026).

Microsoft Learn, “Overview of the Microsoft Authentication Library (MSAL),” https://learn.microsoft.com/entra/msal/overview (accessed Oct 20, 2026).

Microsoft Learn, “Overview of the Microsoft Authentication Library (MSAL),” https://learn.microsoft.com/entra/msal/overview (accessed Oct 20, 2026).

Microsoft Learn, “Overview of the Microsoft Authentication Library (MSAL),” https://learn.microsoft.com/entra/msal/overview (accessed Oct 20, 2026).

Microsoft Learn, “Features removed or no longer developed in Windows Server,” https://learn.microsoft.com/windows-server/get-started/removed-deprecated-features-windows-server (accessed Oct 20, 2026).

Microsoft Learn, “Upgrade from Azure AD PowerShell to Microsoft Graph PowerShell,” https://learn.microsoft.com/powershell/microsoftgraph/migration-steps (accessed Oct 20, 2026).

Microsoft Learn, “Archive for Microsoft Entra releases and announcements,” January 2025 entry “Take action to avoid impact when legacy MSOnline and AzureAD PowerShell modules retire,” https://learn.microsoft.com/entra/fundamentals/whats-new-archive (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra for increased security (Preview),” https://learn.microsoft.com/entra/fundamentals/configure-security (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra PowerShell?,” https://learn.microsoft.com/powershell/entra-powershell/overview (accessed Oct 20, 2026).

Microsoft Learn, “Bicep templates for Microsoft Graph resources,” https://learn.microsoft.com/graph/templates/bicep/overview-bicep-templates-for-graph (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Graph Bicep feature limitations and restrictions,” https://learn.microsoft.com/graph/templates/bicep/limitations (accessed Oct 20, 2026).

National Institute of Standards and Technology, “OSCAL: Layers and Models,” https://pages.nist.gov/OSCAL/learn/concepts/layer/ (accessed Oct 20, 2026).

Microsoft Learn, “Kerberos protocol registry entries and KDC configuration keys in Windows,” https://learn.microsoft.com/troubleshoot/windows-server/windows-security/kerberos-protocol-registry-kdc-configuration-keys (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect Sync: Scheduler,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-sync-feature-scheduler (accessed Oct 20, 2026).

Microsoft Learn, “What is cross-tenant synchronization?,” https://learn.microsoft.com/entra/identity/multi-tenant-organizations/cross-tenant-synchronization-overview (accessed Oct 20, 2026).

Microsoft Learn, “Locating domain controllers in Windows and Windows Server,” https://learn.microsoft.com/windows-server/identity/ad-ds/manage/dc-locator (accessed Oct 20, 2026).

FedRAMP, Marketplace product data (entry FR2017257053, Infoblox Government Cloud: FedRAMP Certified, Moderate), https://www.fedramp.gov/marketplace/products.json (accessed Oct 20, 2026).

Microsoft Learn, “Use certificates for authentication in Microsoft Intune,” https://learn.microsoft.com/intune/fundamentals/certificates/overview (accessed Oct 20, 2026).

Microsoft Learn, “Overview of Microsoft Cloud PKI for Microsoft Intune,” https://learn.microsoft.com/intune/cloud-pki/ (accessed Oct 20, 2026).

Microsoft Learn, “How to configure certificate authorities for Microsoft Entra certificate-based authentication,” https://learn.microsoft.com/entra/identity/authentication/how-to-configure-certificate-authorities (accessed Oct 20, 2026).

Microsoft Learn, “Set up Microsoft Entra certificate-based authentication,” https://learn.microsoft.com/entra/identity/authentication/how-to-certificate-based-authentication (accessed Oct 20, 2026).

Microsoft Learn, “Plan a Windows Hello for Business deployment,” https://learn.microsoft.com/windows/security/identity-protection/hello-for-business/deploy/ (accessed Oct 20, 2026).

Microsoft Learn, “RADIUS authentication with Microsoft Entra ID,” https://learn.microsoft.com/entra/architecture/auth-radius (accessed Oct 20, 2026).

Microsoft Learn, “Integrate your existing Network Policy Server (NPS) infrastructure with Microsoft Entra multifactor authentication,” https://learn.microsoft.com/entra/identity/authentication/howto-mfa-nps-extension (accessed Oct 20, 2026).

Microsoft Learn, “RADIUS authentication with Microsoft Entra ID,” https://learn.microsoft.com/entra/architecture/auth-radius (accessed Oct 20, 2026).

Microsoft Learn, “LDAP signing overview for Active Directory Domain Services,” https://learn.microsoft.com/windows-server/identity/ad-ds/ldap-signing (accessed Oct 20, 2026).

Microsoft Learn, “Configure LDAP signing by using Group Policy for Active Directory Domain Services,” https://learn.microsoft.com/windows-server/identity/manage-ldap-signing-group-policy (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra Domain Services?,” https://learn.microsoft.com/entra/identity/domain-services/overview (accessed Oct 20, 2026).

Microsoft Learn, “Tutorial: Create and configure a Microsoft Entra Domain Services managed domain,” https://learn.microsoft.com/entra/identity/domain-services/tutorial-create-instance (accessed Oct 20, 2026).

Microsoft Learn, “Kerberos Constrained Delegation for single sign-on (SSO) to your apps with application proxy,” https://learn.microsoft.com/entra/identity/app-proxy/how-to-configure-sso-with-kcd (accessed Oct 20, 2026).

Microsoft Learn, “Introduction to Microsoft Entra Connect V2,” https://learn.microsoft.com/entra/identity/hybrid/connect/whatis-azure-ad-connect-v2 (accessed Oct 20, 2026).

Microsoft Learn, “Migrate from Microsoft Entra Connect to Cloud Sync: Decision Guide,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/connect-to-cloud-sync-decision-guide (accessed Oct 20, 2026).

Microsoft Learn, “Migrate from Microsoft Entra Connect Sync to Cloud Sync FAQ,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/cloud-sync-migration-faq (accessed Oct 20, 2026).

Microsoft Learn, “Embrace cloud-first posture: Convert Group Source of Authority to the cloud,” https://learn.microsoft.com/entra/identity/hybrid/concept-source-of-authority-overview (accessed Oct 20, 2026).

Microsoft Learn, “Configure user Source of Authority (SOA),” https://learn.microsoft.com/entra/identity/hybrid/how-to-user-source-of-authority-configure (accessed Oct 20, 2026).

Microsoft Learn, “Migrate from Microsoft Entra Connect to Cloud Sync: Decision Guide,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/connect-to-cloud-sync-decision-guide (accessed Oct 20, 2026).

Microsoft Learn, “Co-management workloads,” https://learn.microsoft.com/intune/configmgr/comanage/workloads (accessed Oct 20, 2026).

Microsoft Learn, “Import and analyze your on-premises GPOs using Group Policy analytics in Microsoft Intune,” https://learn.microsoft.com/intune/device-configuration/import-group-policy-analytics (accessed Oct 20, 2026).

Microsoft Learn, “Kerberos protocol registry entries and KDC configuration keys in Windows,” https://learn.microsoft.com/troubleshoot/windows-server/windows-security/kerberos-protocol-registry-kdc-configuration-keys (accessed Oct 20, 2026).

Microsoft Learn, “How the Windows Time Service works,” https://learn.microsoft.com/windows-server/networking/windows-time-service/how-the-windows-time-service-works (accessed Oct 20, 2026).

Microsoft Learn, “How the Windows Time Service works,” https://learn.microsoft.com/windows-server/networking/windows-time-service/how-the-windows-time-service-works (accessed Oct 20, 2026).

Microsoft Learn, “Policy CSP - ADMX_W32Time,” https://learn.microsoft.com/windows/client-management/mdm/policy-csp-admx-w32time (accessed Oct 20, 2026).

Microsoft Learn, “How the Windows Time Service works,” https://learn.microsoft.com/windows-server/networking/windows-time-service/how-the-windows-time-service-works (accessed Oct 20, 2026).

Microsoft Learn, “Choose a namespace type,” https://learn.microsoft.com/windows-server/storage/dfs-namespaces/choose-a-namespace-type (accessed Oct 20, 2026).

Microsoft Learn, “Enable Microsoft Entra Kerberos authentication for hybrid and cloud-only identities on Azure Files,” https://learn.microsoft.com/azure/storage/files/storage-files-identity-auth-hybrid-identities-enable (accessed Oct 20, 2026).

Microsoft Learn, “How to use DFS Namespaces with Azure Files,” https://learn.microsoft.com/azure/storage/files/files-manage-namespaces (accessed Oct 20, 2026).

Microsoft Learn, “Introduction to Microsoft Entra Kerberos,” https://learn.microsoft.com/entra/identity/authentication/kerberos (accessed Oct 20, 2026).

Microsoft Learn, “Administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/administrative-units (accessed Oct 20, 2026).

Microsoft Learn, “Administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/administrative-units (accessed Oct 20, 2026).

Microsoft Learn, “Administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/administrative-units (accessed Oct 20, 2026).

Microsoft Learn, “Administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/administrative-units (accessed Oct 20, 2026).

Microsoft Learn, “Assign Microsoft Entra roles,” section “Assign roles with administrative unit scope,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-assign-roles (accessed Oct 20, 2026).

Microsoft Learn, “Administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/administrative-units (accessed Oct 20, 2026).

Microsoft Learn, “Manage users or devices for an administrative unit with rules for dynamic membership groups,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-members-dynamic (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra administrative units: Troubleshooting and FAQ,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-faq-troubleshoot (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra administrative units: Troubleshooting and FAQ,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-faq-troubleshoot (accessed Oct 20, 2026).

Microsoft Learn, “Restricted management administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-restricted-management (accessed Oct 20, 2026).

Microsoft Learn, “Restricted management administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-restricted-management (accessed Oct 20, 2026).

Microsoft Learn, “Restricted management administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-restricted-management (accessed Oct 20, 2026).

Microsoft Learn, “Assign Microsoft Entra roles,” section “Assign roles with administrative unit scope,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-assign-roles (accessed Oct 20, 2026).

Microsoft Learn, “Administrative units in Microsoft Purview,” https://learn.microsoft.com/purview/purview-admin-units (accessed Oct 20, 2026).

Microsoft Learn, “Use Microsoft Entra groups to manage role assignments,” https://learn.microsoft.com/entra/identity/role-based-access-control/groups-concept (accessed Oct 20, 2026).

Microsoft Learn, “Assign Microsoft Entra roles in Privileged Identity Management,” section “Assign a role with restricted scope,” https://learn.microsoft.com/entra/id-governance/privileged-identity-management/pim-how-to-add-role-to-user (accessed Oct 20, 2026).

Microsoft Learn, “Assign Microsoft Entra roles,” section “Assign roles with administrative unit scope,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-assign-roles (accessed Oct 20, 2026).

Microsoft Learn, “Restricted management administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-restricted-management (accessed Oct 20, 2026).

Microsoft Learn, “Restricted management administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-restricted-management (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-53 Rev. 5, Security and Privacy Controls for Information Systems and Organizations, September 2020 (updated December 10, 2020), https://csrc.nist.gov/pubs/sp/800/53/r5/upd1/final (accessed Oct 20, 2026).

Microsoft Learn, “Restricted management administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-restricted-management (accessed Oct 20, 2026).

Microsoft Learn, “Update-MgDirectoryAdministrativeUnit,” https://learn.microsoft.com/powershell/module/microsoft.graph.identity.directorymanagement/update-mgdirectoryadministrativeunit?view=graph-powershell-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Restricted management administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-restricted-management (accessed Oct 20, 2026).

Office of Management and Budget, M-19-17, Enabling Mission Delivery through Improved Identity, Credential, and Access Management, May 21, 2019, https://www.whitehouse.gov/wp-content/uploads/2019/05/M-19-17.pdf (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-37 Rev. 2, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy, Appendix D, December 2018, https://nvlpubs.nist.gov/nistpubs/SpecialPublications/NIST.SP.800-37r2.pdf (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-37 Rev. 2, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy, Appendix D, December 2018, https://nvlpubs.nist.gov/nistpubs/SpecialPublications/NIST.SP.800-37r2.pdf (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-37 Rev. 2, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy, Appendix D, December 2018, https://nvlpubs.nist.gov/nistpubs/SpecialPublications/NIST.SP.800-37r2.pdf (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-37 Rev. 2, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy, Appendix D, December 2018, https://nvlpubs.nist.gov/nistpubs/SpecialPublications/NIST.SP.800-37r2.pdf (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-37 Rev. 2, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy, Appendix D, December 2018, https://nvlpubs.nist.gov/nistpubs/SpecialPublications/NIST.SP.800-37r2.pdf (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-37 Rev. 2, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy, Appendix D, December 2018, https://nvlpubs.nist.gov/nistpubs/SpecialPublications/NIST.SP.800-37r2.pdf (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, BOD 25-01, Implementing Secure Practices for Cloud Services, December 17, 2024, https://www.cisa.gov/news-events/directives/bod-25-01-implementing-secure-practices-cloud-services (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-37 Rev. 2, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy, Appendix D, December 2018, https://nvlpubs.nist.gov/nistpubs/SpecialPublications/NIST.SP.800-37r2.pdf (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-37 Rev. 2, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy, Appendix D, December 2018, https://nvlpubs.nist.gov/nistpubs/SpecialPublications/NIST.SP.800-37r2.pdf (accessed Oct 20, 2026).

Microsoft Learn, “Prerequisites for Microsoft Entra Cloud Sync,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/how-to-prerequisites (accessed Oct 20, 2026).

Microsoft Learn, “Configure Temporary Access Pass to register passwordless authentication methods,” https://learn.microsoft.com/entra/identity/authentication/howto-authentication-temporary-access-pass (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-37 Rev. 2, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy, Appendix D, December 2018, https://nvlpubs.nist.gov/nistpubs/SpecialPublications/NIST.SP.800-37r2.pdf (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra built-in roles,” https://learn.microsoft.com/entra/identity/role-based-access-control/permissions-reference (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra built-in roles,” https://learn.microsoft.com/entra/identity/role-based-access-control/permissions-reference (accessed Oct 20, 2026).

Microsoft Learn, “Configure Temporary Access Pass to register passwordless authentication methods,” https://learn.microsoft.com/entra/identity/authentication/howto-authentication-temporary-access-pass (accessed Oct 20, 2026).

Microsoft Learn, “Least privileged roles by task in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/delegate-by-task (accessed Oct 20, 2026).

Microsoft Learn, “Restricted management administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/admin-units-restricted-management (accessed Oct 20, 2026).

Microsoft Learn, “Migrate from Microsoft Entra Connect to Cloud Sync: Decision Guide,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/connect-to-cloud-sync-decision-guide (accessed Oct 20, 2026).

Microsoft Learn, “Migrate from Microsoft Entra Connect to Cloud Sync: Decision Guide,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/connect-to-cloud-sync-decision-guide (accessed Oct 20, 2026).

Microsoft Learn, “Prerequisites for Microsoft Entra Cloud Sync,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/how-to-prerequisites (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect Sync: Understand and customize synchronization,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-sync-whatis (accessed Oct 20, 2026).

Microsoft Learn, “Prerequisites for Microsoft Entra Connect,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-install-prerequisites (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra Connect?,” https://learn.microsoft.com/entra/identity/hybrid/connect/whatis-azure-ad-connect (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra Connect?,” https://learn.microsoft.com/entra/identity/hybrid/connect/whatis-azure-ad-connect (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect Health frequently asked questions,” https://learn.microsoft.com/entra/identity/hybrid/connect/reference-connect-health-faq (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra ID Governance licensing fundamentals,” https://learn.microsoft.com/entra/id-governance/licensing-fundamentals (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra feature availability,” https://learn.microsoft.com/entra/identity/authentication/feature-availability (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra ID Governance licensing fundamentals,” https://learn.microsoft.com/entra/id-governance/licensing-fundamentals (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra ID Protection?,” https://learn.microsoft.com/entra/id-protection/overview-identity-protection (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra ID Protection?,” https://learn.microsoft.com/entra/id-protection/overview-identity-protection (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Defender for Identity’s security posture assessments,” https://learn.microsoft.com/defender-for-identity/security-assessment (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Defender for Identity in the Microsoft Defender portal,” https://learn.microsoft.com/defender-for-identity/microsoft-365-security-center-mdi (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Defender for Identity’s security posture assessments,” https://learn.microsoft.com/defender-for-identity/security-assessment (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Defender for Identity in the Microsoft Defender portal,” https://learn.microsoft.com/defender-for-identity/microsoft-365-security-center-mdi (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Defender for Identity for US Government offerings,” https://learn.microsoft.com/defender-for-identity/us-govt-gcc-high; and “Microsoft Defender for Identity sensor v2.x prerequisites,” https://learn.microsoft.com/defender-for-identity/deploy/prerequisites-sensor-version-2 (both accessed Oct 20, 2026).

Microsoft Learn, “Overview of Microsoft Graph,” https://learn.microsoft.com/graph/overview (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Intune licensing,” https://learn.microsoft.com/intune/fundamentals/licensing (accessed Oct 20, 2026).

Microsoft Learn, “Import and analyze your on-premises GPOs using Group Policy analytics in Microsoft Intune,” https://learn.microsoft.com/intune/device-configuration/import-group-policy-analytics (accessed Oct 20, 2026).

Microsoft Learn, “Create a Settings Catalog policy using your imported GPOs in Microsoft Intune,” https://learn.microsoft.com/intune/device-configuration/migrate-group-policy (accessed Oct 20, 2026).

Microsoft Learn, “Import and analyze your on-premises GPOs using Group Policy analytics in Microsoft Intune,” https://learn.microsoft.com/intune/device-configuration/import-group-policy-analytics (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Intune licensing,” https://learn.microsoft.com/intune/fundamentals/licensing (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Security Compliance Toolkit - How to use,” https://learn.microsoft.com/windows/security/operating-system-security/device-management/windows-security-configuration-framework/security-compliance-toolkit-10 (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Security Compliance Toolkit - How to use,” https://learn.microsoft.com/windows/security/operating-system-security/device-management/windows-security-configuration-framework/security-compliance-toolkit-10 (accessed Oct 20, 2026).

Microsoft Learn, “Modernize server management from Configuration Manager to Azure Arc,” https://learn.microsoft.com/azure/azure-arc/servers/modernize-server-management; and “Windows Server Management enabled by Azure Arc,” https://learn.microsoft.com/azure/azure-arc/servers/windows-server-management-overview (both accessed Oct 20, 2026).

Microsoft Learn, “Modernize server management from Configuration Manager to Azure Arc,” https://learn.microsoft.com/azure/azure-arc/servers/modernize-server-management; and “Windows Server Management enabled by Azure Arc,” https://learn.microsoft.com/azure/azure-arc/servers/windows-server-management-overview (both accessed Oct 20, 2026).

Microsoft Learn, “Learn about auditing solutions in Microsoft Purview,” https://learn.microsoft.com/purview/audit-solutions-overview (accessed Oct 20, 2026).

Microsoft Learn, “Learn about auditing solutions in Microsoft Purview,” https://learn.microsoft.com/purview/audit-solutions-overview (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Sentinel security information and event management (SIEM)?,” https://learn.microsoft.com/azure/sentinel/overview#microsoft-sentinel-in-the-azure-portal-retirement-timeline (accessed Oct 20, 2026).

Microsoft Learn, “Reduce costs for Microsoft Sentinel,” https://learn.microsoft.com/azure/sentinel/billing-reduce-costs (accessed Oct 20, 2026).

Microsoft Learn, “Assess your security posture with Microsoft Secure Score,” https://learn.microsoft.com/defender-xdr/microsoft-secure-score-improvement-actions (accessed Oct 20, 2026).

Microsoft Learn, “What is the Zero Trust Assessment?,” https://learn.microsoft.com/security/zero-trust/assessment/overview; and “Get started with the Zero Trust Assessment,” https://learn.microsoft.com/security/zero-trust/assessment/get-started (both accessed Oct 20, 2026).

Microsoft Learn, “What is the Zero Trust Assessment?,” https://learn.microsoft.com/security/zero-trust/assessment/overview; and “Get started with the Zero Trust Assessment,” https://learn.microsoft.com/security/zero-trust/assessment/get-started (both accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Defender for Identity’s security posture assessments,” https://learn.microsoft.com/defender-for-identity/security-assessment (accessed Oct 20, 2026).

Microsoft Learn, “What is the Zero Trust Assessment?,” https://learn.microsoft.com/security/zero-trust/assessment/overview; and “Get started with the Zero Trust Assessment,” https://learn.microsoft.com/security/zero-trust/assessment/get-started (both accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, “ScubaGear,” GitHub repository, https://github.com/cisagov/ScubaGear (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, BOD 25-01, Implementing Secure Practices for Cloud Services, December 17, 2024, https://www.cisa.gov/news-events/directives/bod-25-01-implementing-secure-practices-cloud-services (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, “ScubaGear,” GitHub repository, https://github.com/cisagov/ScubaGear (accessed Oct 20, 2026).

Microsoft Learn, “Azure Migrate: Common questions,” https://learn.microsoft.com/azure/migrate/resources-faq (accessed Oct 20, 2026).

Microsoft Learn, “Azure Migrate: Common questions,” https://learn.microsoft.com/azure/migrate/resources-faq (accessed Oct 20, 2026).

Microsoft Learn, “Azure Migrate: Common questions,” https://learn.microsoft.com/azure/migrate/resources-faq (accessed Oct 20, 2026).

Microsoft Learn, “Support policy and known issues for Active Directory Migration Tool,” https://learn.microsoft.com/troubleshoot/windows-server/active-directory/support-policy-and-known-issues-for-admt (accessed Oct 20, 2026).

Microsoft Learn, “Support policy and known issues for Active Directory Migration Tool,” https://learn.microsoft.com/troubleshoot/windows-server/active-directory/support-policy-and-known-issues-for-admt (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra Health monitoring?,” https://learn.microsoft.com/entra/identity/monitoring-health/concept-microsoft-entra-health (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra Health monitoring?,” https://learn.microsoft.com/entra/identity/monitoring-health/concept-microsoft-entra-health (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra licensing,” https://learn.microsoft.com/entra/fundamentals/licensing (accessed Oct 20, 2026).

Microsoft Learn, “Eligibility” (FastTrack for Microsoft 365), https://learn.microsoft.com/microsoft-365/fasttrack/eligibility; and “Microsoft Entra” (FastTrack), https://learn.microsoft.com/microsoft-365/fasttrack/microsoft-entra-id (both accessed Oct 20, 2026).

Microsoft Learn, “Eligibility” (FastTrack for Microsoft 365), https://learn.microsoft.com/microsoft-365/fasttrack/eligibility; and “Microsoft Entra” (FastTrack), https://learn.microsoft.com/microsoft-365/fasttrack/microsoft-entra-id (both accessed Oct 20, 2026).

Microsoft Learn, “Security assessment: Certificates,” https://learn.microsoft.com/defender-for-identity/security-posture-assessments/certificates (accessed Oct 20, 2026).

ADRecon, GitHub repository, https://github.com/adrecon/ADRecon (accessed Oct 20, 2026).

PingCastle, https://www.pingcastle.com/ (accessed Oct 20, 2026).

SpecterOps, “BloodHound,” GitHub repository, https://github.com/SpecterOps/BloodHound (accessed Oct 20, 2026).

Semperis, “Purple Knight,” https://www.semperis.com/purple-knight/ (accessed Oct 20, 2026).

NIST, SP 800-53 Rev. 5, Security and Privacy Controls for Information Systems and Organizations, September 2020 (updates as of December 10, 2020; Release 5.2.0 August 27, 2025), Access Control family, https://csrc.nist.gov/pubs/sp/800/53/r5/upd1/final (accessed Oct 20, 2026).

Microsoft Learn, “Troubleshoot password writeback access rights and permissions” (default permissions for Authenticated Users and Pre-Windows 2000 Compatible Access on the domain root and user objects), https://learn.microsoft.com/troubleshoot/entra/entra-id/user-prov-sync/password-writeback-access-rights-permissions (accessed Oct 20, 2026).

Microsoft Learn, “Troubleshoot password writeback access rights and permissions” (default permissions for Authenticated Users and Pre-Windows 2000 Compatible Access on the domain root and user objects), https://learn.microsoft.com/troubleshoot/entra/entra-id/user-prov-sync/password-writeback-access-rights-permissions (accessed Oct 20, 2026).

Microsoft Learn, “Active Directory security groups” (Pre–Windows 2000 Compatible Access), https://learn.microsoft.com/windows-server/identity/ad-ds/manage/understand-security-groups (accessed Oct 20, 2026).

Microsoft Learn, “Appendix C: Protected Accounts and Groups in Active Directory,” https://learn.microsoft.com/windows-server/identity/ad-ds/plan/security-best-practices/appendix-c--protected-accounts-and-groups-in-active-directory (accessed Oct 20, 2026).

Microsoft Learn, “Reducing the Active Directory Attack Surface” (AdminSDHolder and SDProp; formerly protected objects), https://learn.microsoft.com/windows-server/identity/ad-ds/plan/security-best-practices/reducing-the-active-directory-attack-surface (accessed Oct 20, 2026).

Microsoft Learn, “Mark an attribute as confidential in Windows Server 2003 Service Pack 1” (KB 922836), https://learn.microsoft.com/troubleshoot/windows-server/windows-security/mark-attribute-as-confidential (accessed Oct 20, 2026).

Microsoft Learn, “Search-Flags attribute,” https://learn.microsoft.com/windows/win32/adschema/a-searchflags (accessed Oct 20, 2026).

Microsoft Learn, “Accounts security posture assessments” (Microsoft LAPS usage), https://learn.microsoft.com/defender-for-identity/security-posture-assessments/accounts (accessed Oct 20, 2026).

Microsoft Learn, “Windows LAPS schema extensions reference,” https://learn.microsoft.com/windows-server/identity/laps/laps-technical-reference (accessed Oct 20, 2026).

Microsoft Learn, “What is Windows LAPS?” (deprecation of the legacy Microsoft LAPS product), https://learn.microsoft.com/windows-server/identity/laps/laps-overview (accessed Oct 20, 2026).

Microsoft Learn, “DS-Replication-Get-Changes-All extended right,” https://learn.microsoft.com/windows/win32/adschema/r-ds-replication-get-changes-all (accessed Oct 20, 2026).

Microsoft Learn, “Implement password hash synchronization with Microsoft Entra Connect Sync,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-password-hash-synchronization (accessed Oct 20, 2026).

Microsoft Learn, “Let nonadministrators view the contents of the Active Directory deleted objects container” (KB 892806), https://learn.microsoft.com/troubleshoot/windows-server/active-directory/non-administrators-view-deleted-object-container (accessed Oct 20, 2026).

Microsoft Learn, “Restoring Deleted Objects” (permissions required), https://learn.microsoft.com/windows/win32/ad/restoring-deleted-objects (accessed Oct 20, 2026).

Microsoft Learn, “Advanced AD DS Management using Active Directory Administrative Center (Level 200)” (Active Directory Recycle Bin; tombstoneLifetime), https://learn.microsoft.com/windows-server/identity/ad-ds/get-started/adac/advanced-ad-ds-management-using-active-directory-administrative-center--level-200- (accessed Oct 20, 2026).

Microsoft Learn, “Configure fine grained password policies for Active Directory Domain Services,” https://learn.microsoft.com/windows-server/identity/ad-ds/get-started/adac/fine-grained-password-policies (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Defender for Identity alerts in Microsoft Defender format” (discovery alerts, including Active Directory enumeration and LDAP queries targeting sensitive attributes), https://learn.microsoft.com/defender-for-identity/alerts-xdr (accessed Oct 20, 2026).

Microsoft Learn, “Windows Server release information” and “Windows 11 release information,” https://learn.microsoft.com/windows/release-health/windows-server-release-info and https://learn.microsoft.com/windows/release-health/windows11-release-information (accessed Oct 20, 2026).

Microsoft Learn, “Install and manage Remote Server Administration Tools in Windows,” https://learn.microsoft.com/windows-server/administration/install-remote-server-administration-tools (accessed Oct 20, 2026).

Microsoft Learn, “Available Features on Demand,” section “Remote server administration tools (RSAT),” https://learn.microsoft.com/windows-hardware/manufacture/desktop/features-on-demand-non-language-fod (accessed Oct 20, 2026).

Microsoft Learn, “Install and manage Remote Server Administration Tools in Windows,” https://learn.microsoft.com/windows-server/administration/install-remote-server-administration-tools (accessed Oct 20, 2026).

Microsoft Learn, “Making the second hop in PowerShell Remoting,” https://learn.microsoft.com/powershell/scripting/security/remoting/ps-remoting-second-hop (accessed Oct 20, 2026).

PKI Solutions, “PowerShell PKI (PSPKI) Module,” https://www.pkisolutions.com/tools/pspki/ (accessed Oct 20, 2026).

PowerShell Gallery, “PSPKI 4.4.1,” https://www.powershellgallery.com/packages/PSPKI (accessed Oct 20, 2026).

Microsoft Learn, “Security assessment: Unsafe permissions on the DnsAdmins group,” https://learn.microsoft.com/defender-for-identity/unsafe-permissions-dns-admins-group (accessed Oct 20, 2026).

Microsoft Learn, “netdom trust” and “netdom query,” https://learn.microsoft.com/windows-server/administration/windows-commands/netdom-trust and https://learn.microsoft.com/windows-server/administration/windows-commands/netdom-query (accessed Oct 20, 2026).

Microsoft Learn, “Flexible Single Master Operations roles in Active Directory Domain Services,” https://learn.microsoft.com/windows-server/identity/ad-ds/manage/understand-fsmo-roles (accessed Oct 20, 2026).

Microsoft Learn, “Flexible Single Master Operations roles in Active Directory Domain Services,” https://learn.microsoft.com/windows-server/identity/ad-ds/manage/understand-fsmo-roles (accessed Oct 20, 2026).

Microsoft Learn, “Transfer Flexible Single Master Operations roles,” section “Find the current role holders,” https://learn.microsoft.com/windows-server/identity/ad-ds/manage/manage-fsmo-roles (accessed Oct 20, 2026).

Microsoft Learn, “Set-ADForestMode,” parameter -ForestMode, https://learn.microsoft.com/powershell/module/activedirectory/set-adforestmode?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “What’s new in Windows Server 2025,” section “Forest and domain functional levels,” https://learn.microsoft.com/windows-server/get-started/whats-new-windows-server-2025 (accessed Oct 20, 2026).

Microsoft Learn, “Active Directory Domain Services functional levels,” https://learn.microsoft.com/windows-server/identity/ad-ds/active-directory-functional-levels (accessed Oct 20, 2026).

Microsoft Learn, “Identifying your functional level upgrade,” https://learn.microsoft.com/windows-server/identity/ad-ds/plan/identifying-your-functional-level-upgrade (accessed Oct 20, 2026).

Microsoft Learn, “Raise domain and forest functional levels in Active Directory Domain Services,” https://learn.microsoft.com/windows-server/identity/ad-ds/plan/raise-domain-forest-functional-levels (accessed Oct 20, 2026).

Microsoft Learn, “ActiveDirectory Module,” cmdlet index, https://learn.microsoft.com/powershell/module/activedirectory/?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “Get-GPInheritance,” https://learn.microsoft.com/powershell/module/grouppolicy/get-gpinheritance?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “Group Policy scope,” section “GPO scope types,” https://learn.microsoft.com/windows-server/identity/ad-ds/manage/group-policy/group-policy-scope (accessed Oct 20, 2026).

Microsoft Learn, “Group Policy processing,” sections “Enforced GPOs” and “Block Inheritance,” https://learn.microsoft.com/windows-server/identity/ad-ds/manage/group-policy/group-policy-processing (accessed Oct 20, 2026).

Microsoft Learn, “GroupPolicy Module,” https://learn.microsoft.com/powershell/module/grouppolicy/?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “Get-GPOReport,” https://learn.microsoft.com/powershell/module/grouppolicy/get-gporeport?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “Get-GPPermission,” https://learn.microsoft.com/powershell/module/grouppolicy/get-gppermission?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “Create a Settings Catalog policy using your imported GPOs in Microsoft Intune,” section “Conflicting settings are detected early,” https://learn.microsoft.com/intune/device-configuration/migrate-group-policy (accessed Oct 20, 2026).

Microsoft Learn, “Use Microsoft Intune to import and analyze group policies,” https://learn.microsoft.com/intune/device-configuration/import-group-policy-analytics (accessed Oct 20, 2026).

Microsoft Learn, “Get-DnsServerDnsSecZoneSetting,” https://learn.microsoft.com/powershell/module/dnsserver/get-dnsserverdnsseczonesetting?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “Configure DNS aging and scavenging,” https://learn.microsoft.com/windows-server/networking/dns/configure-aging-scavenging (accessed Oct 20, 2026).

Microsoft Learn, “Configure DNS aging and scavenging,” https://learn.microsoft.com/windows-server/networking/dns/configure-aging-scavenging (accessed Oct 20, 2026).

Microsoft Learn, “Monitor AD CS publication health with Enterprise PKI,” section “Understand Public Key Services data,” https://learn.microsoft.com/windows-server/identity/ad-cs/monitor-ad-cs-health-enterprise-pki (accessed Oct 20, 2026).

Microsoft Learn, “certutil,” https://learn.microsoft.com/windows-server/administration/windows-commands/certutil (accessed Oct 20, 2026).

PowerShell Gallery, “PSPKI 4.4.1,” https://www.powershellgallery.com/packages/PSPKI (accessed Oct 20, 2026).

SpecterOps, “Certify: command overview,” https://docs.specterops.io/ghostpack-docs/Certify.wik-mdx/overview (accessed Oct 20, 2026). The underlying research is Will Schroeder and Lee Christensen, Certified Pre-Owned: Abusing Active Directory Certificate Services, SpecterOps, June 2021.

Microsoft Learn, “Security assessment: Certificates,” Microsoft Defender for Identity, https://learn.microsoft.com/defender-for-identity/security-posture-assessments/certificates (accessed Oct 20, 2026).

Microsoft Learn, “Security assessment: Certificates,” Microsoft Defender for Identity, https://learn.microsoft.com/defender-for-identity/security-posture-assessments/certificates (accessed Oct 20, 2026).

Microsoft Learn, “Security assessment: Certificates,” Microsoft Defender for Identity, https://learn.microsoft.com/defender-for-identity/security-posture-assessments/certificates (accessed Oct 20, 2026).

Microsoft Learn, “Security assessment: Certificates,” Microsoft Defender for Identity, https://learn.microsoft.com/defender-for-identity/security-posture-assessments/certificates (accessed Oct 20, 2026).

Microsoft Learn, “X509CertificateTemplateSubjectNameFlag enumeration (certenroll.h),” https://learn.microsoft.com/windows/win32/api/certenroll/ne-certenroll-x509certificatetemplatesubjectnameflag (accessed Oct 20, 2026).

Microsoft Learn, “X509CertificateTemplateEnrollmentFlag enumeration (certenroll.h),” https://learn.microsoft.com/windows/win32/api/certenroll/ne-certenroll-x509certificatetemplateenrollmentflag (accessed Oct 20, 2026).

Microsoft Learn, “Guidelines for enabling smart card logon with third-party certification authorities,” https://learn.microsoft.com/troubleshoot/windows-server/certificates-and-public-key-infrastructure-pki/enabling-smart-card-logon-third-party-certification-authorities (accessed Oct 20, 2026).

Internet Engineering Task Force, RFC 4556, Public Key Cryptography for Initial Authentication in Kerberos (PKINIT), June 2006, https://www.rfc-editor.org/rfc/rfc4556 (accessed Oct 20, 2026).

Internet Engineering Task Force, RFC 5280, Internet X.509 Public Key Infrastructure Certificate and Certificate Revocation List (CRL) Profile, section 4.2.1.12, May 2008, https://www.rfc-editor.org/rfc/rfc5280 (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra certificate-based authentication?,” https://learn.microsoft.com/entra/identity/authentication/concept-certificate-based-authentication (accessed Oct 20, 2026).

Microsoft Learn, “Last-Logon-Timestamp attribute,” https://learn.microsoft.com/windows/win32/adschema/a-lastlogontimestamp, and “The lastLogonTimestamp attribute in System Center 2012 Configuration Manager may not be accurate,” https://learn.microsoft.com/troubleshoot/mem/configmgr/discovery/lastlogontimestamp-not-accurate (accessed Oct 20, 2026).

Microsoft Learn, “Accounts security posture assessments,” Microsoft Defender for Identity, https://learn.microsoft.com/defender-for-identity/security-posture-assessments/accounts (accessed Oct 20, 2026).

Microsoft Learn, “Kerberos Constrained Delegation Overview,” section “Resource-based constrained delegation across domains,” https://learn.microsoft.com/windows-server/security/kerberos/kerberos-constrained-delegation-overview (accessed Oct 20, 2026).

Microsoft Learn, “Making the second hop in PowerShell Remoting,” https://learn.microsoft.com/powershell/scripting/security/remoting/ps-remoting-second-hop (accessed Oct 20, 2026).

Microsoft Learn, “Making the second hop in PowerShell Remoting,” https://learn.microsoft.com/powershell/scripting/security/remoting/ps-remoting-second-hop (accessed Oct 20, 2026).

Microsoft Learn, “Accounts security posture assessments,” Microsoft Defender for Identity, https://learn.microsoft.com/defender-for-identity/security-posture-assessments/accounts (accessed Oct 20, 2026).

Microsoft Learn, “Privileged access security levels,” https://learn.microsoft.com/security/privileged-access-workstations/privileged-access-security-levels (accessed Oct 20, 2026).

Microsoft Learn, “Appendix C: Protected Accounts and Groups in Active Directory,” https://learn.microsoft.com/windows-server/identity/ad-ds/plan/security-best-practices/appendix-c--protected-accounts-and-groups-in-active-directory (accessed Oct 20, 2026).

Microsoft Learn, “Reducing the Active Directory Attack Surface,” section “Privileged Accounts and Groups in Active Directory,” https://learn.microsoft.com/windows-server/identity/ad-ds/plan/security-best-practices/reducing-the-active-directory-attack-surface (accessed Oct 20, 2026).

Microsoft Learn, “Delegated Managed Service Accounts overview,” https://learn.microsoft.com/windows-server/identity/ad-ds/manage/delegated-managed-service-accounts/delegated-managed-service-accounts-overview (accessed Oct 20, 2026).

Microsoft Learn, “Manage group Managed Service Accounts,” https://learn.microsoft.com/windows-server/identity/ad-ds/manage/group-managed-service-accounts/group-managed-service-accounts/manage-group-managed-service-accounts (accessed Oct 20, 2026).

Microsoft Learn, “Windows Server 2008 and newer domain controller returns only 5000 values in an LDAP response,” https://learn.microsoft.com/troubleshoot/windows-server/active-directory/domain-controller-returns-500-values-ldap-response (accessed Oct 20, 2026).

Microsoft Learn, “Active Directory Domain Services maximum limits and scalability,” section “Group Memberships for security principals,” https://learn.microsoft.com/windows-server/identity/ad-ds/plan/active-directory-domain-services-maximum-limits (accessed Oct 20, 2026).

Microsoft Learn, “How trust relationships work for forests in Active Directory,” section “Trusted domain object,” https://learn.microsoft.com/entra/identity/domain-services/concepts-forest-trust (accessed Oct 20, 2026).

Microsoft Learn, “Get-ADTrust,” https://learn.microsoft.com/powershell/module/activedirectory/get-adtrust?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft, [MS-ADTS] Active Directory Technical Specification, “trustAttributes,” https://learn.microsoft.com/openspecs/windows_protocols/ms-adts/e9a2d23c-c31e-4a6f-88a0-6646fdb51a3c (accessed Oct 20, 2026).

Microsoft Learn, “Management concepts for user accounts, passwords, and administration in Microsoft Entra Domain Services,” section “Forests and trusts,” https://learn.microsoft.com/entra/identity/domain-services/administration-concepts, and “How trust relationships work for forests in Active Directory,” section “Forest trusts,” https://learn.microsoft.com/entra/identity/domain-services/concepts-forest-trust (accessed Oct 20, 2026).

Microsoft Learn, “ActiveDirectory Module,” cmdlet index, https://learn.microsoft.com/powershell/module/activedirectory/?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “netdom trust” and “netdom query,” https://learn.microsoft.com/windows-server/administration/windows-commands/netdom-trust and https://learn.microsoft.com/windows-server/administration/windows-commands/netdom-query (accessed Oct 20, 2026).

Microsoft Learn, “Overview: Cross-tenant access with Microsoft Entra External ID,” https://learn.microsoft.com/entra/external-id/cross-tenant-access-overview (accessed Oct 20, 2026).

Microsoft Learn, “Manage group Managed Service Accounts,” https://learn.microsoft.com/windows-server/identity/ad-ds/manage/group-managed-service-accounts/group-managed-service-accounts/manage-group-managed-service-accounts (accessed Oct 20, 2026).

Microsoft Learn, “Run assessments with Managed Service Accounts,” Microsoft Engage Center, https://learn.microsoft.com/services-hub/microsoft-engage-center/health/kb/kb-running-assessments-with-msas (accessed Oct 20, 2026).

Gitea, “API Usage,” https://docs.gitea.com/development/api-usage (accessed Oct 20, 2026).

Gitea, API specification (OpenAPI 2.0), https://gitea.com/swagger.v1.json (accessed Oct 20, 2026). Endpoint names, request fields and the deprecation of query-parameter tokens are as published there; confirm them against /api/swagger on your own instance, because fields vary by Gitea version.

Gitea, API specification (OpenAPI 2.0), https://gitea.com/swagger.v1.json (accessed Oct 20, 2026). Endpoint names, request fields and the deprecation of query-parameter tokens are as published there; confirm them against /api/swagger on your own instance, because fields vary by Gitea version.

Microsoft Learn, “Security assessment: Unsafe permissions on the DnsAdmins group,” https://learn.microsoft.com/defender-for-identity/unsafe-permissions-dns-admins-group (accessed Oct 20, 2026).

Microsoft Learn, “Run assessments with Managed Service Accounts,” Microsoft Engage Center, https://learn.microsoft.com/services-hub/microsoft-engage-center/health/kb/kb-running-assessments-with-msas (accessed Oct 20, 2026).

Microsoft Learn, “Specify a server name and port number for an Active Directory cmdlet,” https://learn.microsoft.com/troubleshoot/windows-server/active-directory/specify-server-port-active-directory-powershell-cmdlet (accessed Oct 20, 2026).

Microsoft Learn, “Service overview and network port requirements for Windows,” https://learn.microsoft.com/troubleshoot/windows-server/networking/service-overview-and-network-port-requirements (accessed Oct 20, 2026).

Microsoft Learn, “Security Considerations for PowerShell Remoting using WinRM,” https://learn.microsoft.com/powershell/scripting/security/remoting/winrm-security (accessed Oct 20, 2026).

Microsoft Learn, “Specify a server name and port number for an Active Directory cmdlet,” https://learn.microsoft.com/troubleshoot/windows-server/active-directory/specify-server-port-active-directory-powershell-cmdlet (accessed Oct 20, 2026).

Microsoft Learn, “Installation and configuration for Windows Remote Management,” section “TrustedHosts,” https://learn.microsoft.com/windows/win32/winrm/installation-and-configuration-for-windows-remote-management (accessed Oct 20, 2026).

Microsoft Learn, “‘Size Limit Exceeded - Error Code 0x4’ error message during delta import in Microsoft Entra Connect,” https://learn.microsoft.com/troubleshoot/entra/entra-id/user-prov-sync/size-limit-exceeded (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Graph national cloud deployments,” https://learn.microsoft.com/graph/deployments (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra UserPrincipalName population,” https://learn.microsoft.com/entra/identity/hybrid/connect/plan-connect-userprincipalname (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra Connect for an existing tenant,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-install-existing-tenant (accessed Oct 20, 2026).

Microsoft Learn, “Administrative units in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/administrative-units (accessed Oct 20, 2026).

Microsoft Learn, “Appendix C: Protected Accounts and Groups in Active Directory,” https://learn.microsoft.com/windows-server/identity/ad-ds/plan/security-best-practices/appendix-c--protected-accounts-and-groups-in-active-directory (accessed Oct 20, 2026).

Microsoft Learn, “Appendix C: Protected Accounts and Groups in Active Directory,” https://learn.microsoft.com/windows-server/identity/ad-ds/plan/security-best-practices/appendix-c--protected-accounts-and-groups-in-active-directory (accessed Oct 20, 2026).

Microsoft Learn, “Reducing the Active Directory Attack Surface,” https://learn.microsoft.com/windows-server/identity/ad-ds/plan/security-best-practices/reducing-the-active-directory-attack-surface (accessed Oct 20, 2026).

Microsoft Learn, “What are protected actions in Microsoft Entra ID?,” https://learn.microsoft.com/entra/identity/role-based-access-control/protected-actions-overview (accessed Oct 20, 2026).

Microsoft Learn, “What is managed identities for Azure resources?,” https://learn.microsoft.com/entra/identity/managed-identities-azure-resources/overview (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Cloud Sync migration decision guide,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/connect-to-cloud-sync-decision-guide (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra ID Governance licensing fundamentals,” https://learn.microsoft.com/entra/id-governance/licensing-fundamentals (accessed Oct 20, 2026).

Microsoft Learn, “Manage rules for dynamic membership groups in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/users/groups-dynamic-membership (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra licensing,” https://learn.microsoft.com/entra/fundamentals/licensing (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra ID Governance licensing fundamentals,” https://learn.microsoft.com/entra/id-governance/licensing-fundamentals (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra ID Governance licensing fundamentals,” https://learn.microsoft.com/entra/id-governance/licensing-fundamentals (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra ID Governance licensing fundamentals,” https://learn.microsoft.com/entra/id-governance/licensing-fundamentals (accessed Oct 20, 2026).

Microsoft Learn, “Risk-based access policies,” https://learn.microsoft.com/entra/id-protection/concept-identity-protection-policies (accessed Oct 20, 2026).

Microsoft Learn, “Manage rules for dynamic membership groups in Microsoft Entra ID: rule syntax for a single expression,” https://learn.microsoft.com/entra/identity/users/groups-dynamic-membership#rule-syntax-for-a-single-expression (accessed Oct 20, 2026).

Microsoft Learn, “Troubleshoot dynamic groups,” https://learn.microsoft.com/troubleshoot/entra/entra-id/dir-dmns-obj/troubleshoot-dynamic-groups (accessed Oct 20, 2026).

Microsoft Learn, “Manage rules for dynamic membership groups in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/users/groups-dynamic-membership (accessed Oct 20, 2026).

Microsoft Learn, “Configure dynamic membership groups with the memberOf operator in the Entra Admin Center (preview),” https://learn.microsoft.com/entra/identity/users/groups-dynamic-rule-member-of (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Cloud Sync migration decision guide,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/connect-to-cloud-sync-decision-guide (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Cloud Sync migration decision guide,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/connect-to-cloud-sync-decision-guide (accessed Oct 20, 2026).

Microsoft Learn, “Disable group writeback,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-group-writeback-disable (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Cloud Sync migration decision guide,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/connect-to-cloud-sync-decision-guide (accessed Oct 20, 2026).

Microsoft Learn, “Hybrid scenarios,” https://learn.microsoft.com/entra/identity/hybrid/common-scenarios (accessed Oct 20, 2026).

Microsoft Learn, “Choose the right authentication method for your Microsoft Entra hybrid identity solution,” https://learn.microsoft.com/entra/identity/hybrid/connect/choose-ad-authn (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Cloud Sync migration decision guide,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/connect-to-cloud-sync-decision-guide (accessed Oct 20, 2026).

Microsoft Learn, “Choose the right authentication method for your Microsoft Entra hybrid identity solution,” https://learn.microsoft.com/entra/identity/hybrid/connect/choose-ad-authn (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra pass-through authentication: Quickstart,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-pta-quick-start (accessed Oct 20, 2026).

Microsoft Learn, “Choose the right authentication method for your Microsoft Entra hybrid identity solution,” https://learn.microsoft.com/entra/identity/hybrid/connect/choose-ad-authn (accessed Oct 20, 2026).

Microsoft Learn, “Choose the right authentication method for your Microsoft Entra hybrid identity solution,” https://learn.microsoft.com/entra/identity/hybrid/connect/choose-ad-authn (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra Connect for an existing tenant,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-install-existing-tenant (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra Connect for an existing tenant,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-install-existing-tenant (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra Connect for an existing tenant,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-install-existing-tenant (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect user sign-in options,” https://learn.microsoft.com/entra/identity/hybrid/connect/plan-connect-user-signin (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect user sign-in options,” https://learn.microsoft.com/entra/identity/hybrid/connect/plan-connect-user-signin (accessed Oct 20, 2026).

Microsoft Learn, “Sign-in to Microsoft Entra ID with email as an alternate login ID (Preview),” https://learn.microsoft.com/entra/identity/authentication/howto-authentication-use-email-signin (accessed Oct 20, 2026).

Microsoft Learn, “Group writeback with Microsoft Entra Cloud Sync,” https://learn.microsoft.com/entra/identity/hybrid/group-writeback-cloud-sync (accessed Oct 20, 2026).

Microsoft Learn, “Manage Microsoft Entra groups and group membership,” https://learn.microsoft.com/entra/fundamentals/how-to-manage-groups (accessed Oct 20, 2026).

Microsoft Learn, “Conditional Access: Users, groups, agents, and workload identities,” https://learn.microsoft.com/entra/identity/conditional-access/concept-conditional-access-users-groups (accessed Oct 20, 2026).

Microsoft Learn, “Manage Microsoft Entra groups and group membership,” https://learn.microsoft.com/entra/fundamentals/how-to-manage-groups (accessed Oct 20, 2026).

Microsoft Learn, “Manage Microsoft Entra groups and group membership,” https://learn.microsoft.com/entra/fundamentals/how-to-manage-groups (accessed Oct 20, 2026).

Microsoft Learn, “Manage rules for dynamic membership groups in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/users/groups-dynamic-membership (accessed Oct 20, 2026).

Microsoft Learn, “Manage Microsoft Entra groups and group membership,” https://learn.microsoft.com/entra/fundamentals/how-to-manage-groups (accessed Oct 20, 2026).

Microsoft Learn, “Configure the expiration policy for Microsoft 365 groups,” https://learn.microsoft.com/entra/identity/users/groups-lifecycle (accessed Oct 20, 2026).

Microsoft Learn, “Configure an app to trust an external identity provider,” https://learn.microsoft.com/entra/workload-id/workload-identity-federation-create-trust (accessed Oct 20, 2026).

Microsoft Learn, “Important considerations and restrictions for federated identity credentials,” https://learn.microsoft.com/entra/workload-id/workload-identity-federation-considerations (accessed Oct 20, 2026).

Microsoft Learn, “Important considerations and restrictions for federated identity credentials,” https://learn.microsoft.com/entra/workload-id/workload-identity-federation-considerations (accessed Oct 20, 2026).

Microsoft Learn, “Conditional Access for workload identities,” https://learn.microsoft.com/entra/identity/conditional-access/workload-identity (accessed Oct 20, 2026).

Microsoft Learn, “Conditional Access for workload identities,” https://learn.microsoft.com/entra/identity/conditional-access/workload-identity (accessed Oct 20, 2026).

Microsoft Learn, “Privileged roles and permissions in Microsoft Entra ID (preview),” https://learn.microsoft.com/entra/identity/role-based-access-control/privileged-roles-permissions (accessed Oct 20, 2026).

Microsoft Learn, “Conditional Access: Users, groups, agents, and workload identities,” https://learn.microsoft.com/entra/identity/conditional-access/concept-conditional-access-users-groups (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra role settings in Privileged Identity Management,” https://learn.microsoft.com/entra/id-governance/privileged-identity-management/pim-how-to-change-default-settings (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra role settings in Privileged Identity Management,” https://learn.microsoft.com/entra/id-governance/privileged-identity-management/pim-how-to-change-default-settings (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra role settings in Privileged Identity Management,” https://learn.microsoft.com/entra/id-governance/privileged-identity-management/pim-how-to-change-default-settings (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra role settings in Privileged Identity Management,” https://learn.microsoft.com/entra/id-governance/privileged-identity-management/pim-how-to-change-default-settings (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra role settings in Privileged Identity Management,” https://learn.microsoft.com/entra/id-governance/privileged-identity-management/pim-how-to-change-default-settings (accessed Oct 20, 2026).

Microsoft Learn, “Privileged Identity Management (PIM) for Groups,” https://learn.microsoft.com/entra/id-governance/privileged-identity-management/concept-pim-for-groups (accessed Oct 20, 2026).

Microsoft Learn, “Privileged Identity Management (PIM) for Groups,” https://learn.microsoft.com/entra/id-governance/privileged-identity-management/concept-pim-for-groups (accessed Oct 20, 2026).

Microsoft Learn, “Privileged Identity Management (PIM) for Groups,” https://learn.microsoft.com/entra/id-governance/privileged-identity-management/concept-pim-for-groups (accessed Oct 20, 2026).

Microsoft Learn, “Assign eligibility for a group in Privileged Identity Management,” https://learn.microsoft.com/entra/id-governance/privileged-identity-management/groups-assign-member-owner (accessed Oct 20, 2026).

Microsoft Learn, “Manage emergency access accounts in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/security-emergency-access (accessed Oct 20, 2026).

Microsoft Learn, “Manage emergency access accounts in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/security-emergency-access (accessed Oct 20, 2026).

Microsoft Learn, “Manage emergency access accounts in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/security-emergency-access (accessed Oct 20, 2026).

Microsoft Learn, “Manage emergency access accounts in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/security-emergency-access (accessed Oct 20, 2026).

Microsoft Learn, “Manage emergency access accounts in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/role-based-access-control/security-emergency-access (accessed Oct 20, 2026).

Microsoft Learn, “What are protected actions in Microsoft Entra ID?,” https://learn.microsoft.com/entra/identity/role-based-access-control/protected-actions-overview (accessed Oct 20, 2026).

Microsoft Learn, “What are protected actions in Microsoft Entra ID?,” https://learn.microsoft.com/entra/identity/role-based-access-control/protected-actions-overview (accessed Oct 20, 2026).

Microsoft Learn, “What are protected actions in Microsoft Entra ID?,” https://learn.microsoft.com/entra/identity/role-based-access-control/protected-actions-overview (accessed Oct 20, 2026).

Microsoft Learn, “Privileged roles and permissions in Microsoft Entra ID (preview),” https://learn.microsoft.com/entra/identity/role-based-access-control/privileged-roles-permissions (accessed Oct 20, 2026).

Microsoft Learn, “Conditional Access: Users, groups, agents, and workload identities,” https://learn.microsoft.com/entra/identity/conditional-access/concept-conditional-access-users-groups (accessed Oct 20, 2026).

Microsoft Learn, “Understand Microsoft U.S. government cloud environments for Microsoft 365 and Microsoft Copilot,” https://learn.microsoft.com/microsoft-365/copilot/gov-overview (accessed Oct 20, 2026).

Microsoft Learn, “Conditional Access authentication strengths,” https://learn.microsoft.com/entra/identity/authentication/concept-authentication-strengths (accessed Oct 20, 2026).

Microsoft Learn, “Meet multifactor authentication requirements of memorandum 22-09,” https://learn.microsoft.com/entra/standards/memo-22-09-multi-factor-authentication (accessed Oct 20, 2026).

Microsoft Learn, “Conditional Access authentication strengths,” https://learn.microsoft.com/entra/identity/authentication/concept-authentication-strengths (accessed Oct 20, 2026).

Microsoft Learn, “Configure and enable risk policies,” https://learn.microsoft.com/entra/id-protection/howto-identity-protection-configure-risk-policies (accessed Oct 20, 2026).

Microsoft Learn, “Risk-based access policies,” https://learn.microsoft.com/entra/id-protection/concept-identity-protection-policies (accessed Oct 20, 2026).

Microsoft Learn, “What are risk detections?,” https://learn.microsoft.com/entra/id-protection/concept-identity-protection-risks (accessed Oct 20, 2026).

Microsoft Learn, “Choose the right authentication method for your Microsoft Entra hybrid identity solution,” https://learn.microsoft.com/entra/identity/hybrid/connect/choose-ad-authn (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra ID Governance licensing fundamentals,” https://learn.microsoft.com/entra/id-governance/licensing-fundamentals (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra licensing,” https://learn.microsoft.com/entra/fundamentals/licensing (accessed Oct 20, 2026).

Microsoft Learn, “Configure dynamic membership groups with the memberOf operator in the Entra Admin Center (preview),” https://learn.microsoft.com/entra/identity/users/groups-dynamic-rule-member-of (accessed Oct 20, 2026).

Microsoft Learn, “Group writeback with Microsoft Entra Cloud Sync,” https://learn.microsoft.com/entra/identity/hybrid/group-writeback-cloud-sync (accessed Oct 20, 2026).

Microsoft Learn, “Lifecycle workflows execution conditions and scheduling,” https://learn.microsoft.com/entra/id-governance/lifecycle-workflow-execution-conditions (accessed Oct 20, 2026).

Microsoft Learn, “Lifecycle workflows execution conditions and scheduling,” https://learn.microsoft.com/entra/id-governance/lifecycle-workflow-execution-conditions (accessed Oct 20, 2026).

Microsoft Learn, “Managing users synchronized from Active Directory Domain Services to Microsoft Entra ID with Lifecycle workflows,” https://learn.microsoft.com/entra/id-governance/lifecycle-workflow-on-premises (accessed Oct 20, 2026).

Microsoft Learn, “ruleBasedSubjectSet resource type,” https://learn.microsoft.com/graph/api/resources/identitygovernance-rulebasedsubjectset?view=graph-rest-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra ID Governance licensing fundamentals,” https://learn.microsoft.com/entra/id-governance/licensing-fundamentals (accessed Oct 20, 2026).

Microsoft Learn, “Lifecycle Workflow built-in tasks,” https://learn.microsoft.com/entra/id-governance/lifecycle-workflow-tasks (accessed Oct 20, 2026).

Microsoft Learn, “Lifecycle Workflows templates and categories,” https://learn.microsoft.com/entra/id-governance/lifecycle-workflow-templates (accessed Oct 20, 2026).

Microsoft Learn, “Configure the arguments for built-in Lifecycle Workflows tasks,” https://learn.microsoft.com/graph/identitygovernance-lifecycleworkflows-task-arguments (accessed Oct 20, 2026).

Microsoft Learn, “Lifecycle Workflows templates and categories,” https://learn.microsoft.com/entra/id-governance/lifecycle-workflow-templates (accessed Oct 20, 2026).

Microsoft Learn, “Lifecycle Workflows templates and categories,” https://learn.microsoft.com/entra/id-governance/lifecycle-workflow-templates (accessed Oct 20, 2026).

Microsoft Learn, “Lifecycle Workflow built-in tasks,” https://learn.microsoft.com/entra/id-governance/lifecycle-workflow-tasks (accessed Oct 20, 2026).

Microsoft Learn, “Managing users synchronized from Active Directory Domain Services to Microsoft Entra ID with Lifecycle workflows,” https://learn.microsoft.com/entra/id-governance/lifecycle-workflow-on-premises (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra licensing,” https://learn.microsoft.com/entra/fundamentals/licensing (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra ID Governance?,” https://learn.microsoft.com/entra/id-governance/identity-governance-overview (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra B2B collaboration FAQs,” https://learn.microsoft.com/entra/external-id/faq (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra B2B collaboration FAQs,” https://learn.microsoft.com/entra/external-id/faq (accessed Oct 20, 2026).

Microsoft Learn, “Overview: Cross-tenant access with Microsoft Entra External ID,” https://learn.microsoft.com/entra/external-id/cross-tenant-access-overview (accessed Oct 20, 2026).

Microsoft Learn, “Overview: Cross-tenant access with Microsoft Entra External ID,” https://learn.microsoft.com/entra/external-id/cross-tenant-access-overview (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra licensing,” https://learn.microsoft.com/entra/fundamentals/licensing (accessed Oct 20, 2026).

Microsoft Learn, “B2B direct connect overview,” https://learn.microsoft.com/entra/external-id/b2b-direct-connect-overview (accessed Oct 20, 2026).

Microsoft Learn, “B2B direct connect overview,” https://learn.microsoft.com/entra/external-id/b2b-direct-connect-overview (accessed Oct 20, 2026).

Microsoft Learn, “B2B direct connect overview,” https://learn.microsoft.com/entra/external-id/b2b-direct-connect-overview (accessed Oct 20, 2026).

Microsoft Learn, “Identity providers for External ID in workforce tenants,” https://learn.microsoft.com/entra/external-id/identity-providers (accessed Oct 20, 2026).

Microsoft Learn, “Email one-time passcode authentication for B2B guest users,” https://learn.microsoft.com/entra/external-id/one-time-passcode (accessed Oct 20, 2026).

Microsoft Learn, “What are risk detections?,” https://learn.microsoft.com/entra/id-protection/concept-identity-protection-risks (accessed Oct 20, 2026).

Microsoft Learn, “Choose the right authentication method for your Microsoft Entra hybrid identity solution,” https://learn.microsoft.com/entra/identity/hybrid/connect/choose-ad-authn (accessed Oct 20, 2026).

Microsoft Learn, “Choose the right authentication method for your Microsoft Entra hybrid identity solution,” https://learn.microsoft.com/entra/identity/hybrid/connect/choose-ad-authn (accessed Oct 20, 2026).

Office of Management and Budget, M-22-09, Moving the U.S. Government Toward Zero Trust Cybersecurity Principles, January 26, 2022, https://bidenwhitehouse.archives.gov/wp-content/uploads/2022/01/M-22-09.pdf (accessed Oct 20, 2026).

Office of Management and Budget, M-22-09, Moving the U.S. Government Toward Zero Trust Cybersecurity Principles, January 26, 2022, https://bidenwhitehouse.archives.gov/wp-content/uploads/2022/01/M-22-09.pdf (accessed Oct 20, 2026).

Microsoft Learn, “Meet multifactor authentication requirements of memorandum 22-09,” https://learn.microsoft.com/entra/standards/memo-22-09-multi-factor-authentication (accessed Oct 20, 2026).

Microsoft Learn, “Enable passkeys in Authenticator,” https://learn.microsoft.com/entra/identity/authentication/how-to-enable-authenticator-passkey (accessed Oct 20, 2026).

Microsoft Learn, “Conditional Access authentication strengths,” https://learn.microsoft.com/entra/identity/authentication/concept-authentication-strengths (accessed Oct 20, 2026).

Microsoft Learn, “How to enable passkeys (FIDO2) in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/authentication/how-to-authentication-passkeys-fido2 (accessed Oct 20, 2026).

Microsoft Learn, “How to enable passkeys (FIDO2) in Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/authentication/how-to-authentication-passkeys-fido2 (accessed Oct 20, 2026).

Microsoft Learn, “How number matching works in MFA push notifications for Authenticator,” https://learn.microsoft.com/entra/identity/authentication/how-to-mfa-number-match (accessed Oct 20, 2026).

Microsoft Learn, “Meet multifactor authentication requirements of memorandum 22-09,” https://learn.microsoft.com/entra/standards/memo-22-09-multi-factor-authentication (accessed Oct 20, 2026).

Microsoft Learn, “Configure Temporary Access Pass to register passwordless authentication methods,” https://learn.microsoft.com/entra/identity/authentication/howto-authentication-temporary-access-pass (accessed Oct 20, 2026).

Office of Management and Budget, M-22-09, Moving the U.S. Government Toward Zero Trust Cybersecurity Principles, January 26, 2022, https://bidenwhitehouse.archives.gov/wp-content/uploads/2022/01/M-22-09.pdf (accessed Oct 20, 2026).

Microsoft Learn, “Deprecation of Basic authentication in Exchange Online,” https://learn.microsoft.com/exchange/clients-and-mobile-in-exchange-online/deprecation-of-basic-authentication-exchange-online (accessed Oct 20, 2026).

Microsoft Learn, “Deprecation of Basic authentication in Exchange Online,” https://learn.microsoft.com/exchange/clients-and-mobile-in-exchange-online/deprecation-of-basic-authentication-exchange-online (accessed Oct 20, 2026).

FedRAMP, “Identification and Authentication” (NIST SP 800-53 Rev. 5 controls, catalog release 5.2.0), https://fedramp.gov/2026/reference/controls/identification-and-authentication/ (accessed Oct 20, 2026).

FedRAMP, “Identification and Authentication” (NIST SP 800-53 Rev. 5 controls, catalog release 5.2.0), https://fedramp.gov/2026/reference/controls/identification-and-authentication/ (accessed Oct 20, 2026).

FedRAMP, “Identification and Authentication” (NIST SP 800-53 Rev. 5 controls, catalog release 5.2.0), https://fedramp.gov/2026/reference/controls/identification-and-authentication/ (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra certificate-based authentication on iOS and macOS,” https://learn.microsoft.com/entra/identity/authentication/concept-certificate-based-authentication-mobile-ios (accessed Oct 20, 2026).

FedRAMP, “Identity and Access Management” (FedRAMP 20x Key Security Indicators, Consolidated Rules for 2026), https://fedramp.gov/2026/providers/20x/key-security-indicators/identity-and-access-management/ (accessed Oct 20, 2026).

FedRAMP, “Access Control” (NIST SP 800-53 Rev. 5 controls, catalog release 5.2.0), https://fedramp.gov/2026/reference/controls/access-control/ (accessed Oct 20, 2026).

Microsoft Learn, “Phase 2: Configure and secure privileged workstations,” https://learn.microsoft.com/security/zero-trust/adopt/implement-privileged-access-devices (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra data retention,” https://learn.microsoft.com/entra/identity/monitoring-health/reference-reports-data-retention (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra data retention,” https://learn.microsoft.com/entra/identity/monitoring-health/reference-reports-data-retention (accessed Oct 20, 2026).

Microsoft Learn, “Integrate Microsoft Entra logs with Azure Monitor logs,” https://learn.microsoft.com/entra/identity/monitoring-health/howto-integrate-activity-logs-with-azure-monitor-logs (accessed Oct 20, 2026).

Microsoft Learn, “Integrate Microsoft Entra logs with Azure Monitor logs,” https://learn.microsoft.com/entra/identity/monitoring-health/howto-integrate-activity-logs-with-azure-monitor-logs (accessed Oct 20, 2026).

Microsoft Learn, “user resource type,” https://learn.microsoft.com/graph/api/resources/user?view=graph-rest-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra audit log categories and activities,” https://learn.microsoft.com/entra/identity/monitoring-health/reference-audit-activities (accessed Oct 20, 2026).

Microsoft Learn, “Security operations for privileged accounts in Microsoft Entra ID,” https://learn.microsoft.com/entra/architecture/security-operations-privileged-accounts (accessed Oct 20, 2026).

Microsoft Learn, “What are Microsoft Entra workbooks?,” https://learn.microsoft.com/entra/identity/monitoring-health/overview-workbooks (accessed Oct 20, 2026).

Microsoft Learn, “Compliance Manager regulations list,” https://learn.microsoft.com/purview/compliance-manager-regulations-list (accessed Oct 20, 2026).

FedRAMP, “Identity and Access Management” (FedRAMP 20x Key Security Indicators, Consolidated Rules for 2026), https://fedramp.gov/2026/providers/20x/key-security-indicators/identity-and-access-management/ (accessed Oct 20, 2026).

FedRAMP, “Identity and Access Management” (FedRAMP 20x Key Security Indicators, Consolidated Rules for 2026), https://fedramp.gov/2026/providers/20x/key-security-indicators/identity-and-access-management/ (accessed Oct 20, 2026).

FedRAMP, “Monitoring, Logging, and Auditing” (FedRAMP 20x Key Security Indicators), https://fedramp.gov/2026/providers/20x/key-security-indicators/monitoring-logging-and-auditing/ (accessed Oct 20, 2026).

Microsoft Learn, “Choose the right authentication method for your Microsoft Entra hybrid identity solution,” https://learn.microsoft.com/entra/identity/hybrid/connect/choose-ad-authn (accessed Oct 20, 2026).

Microsoft Learn, “Migrate to cloud authentication using Staged Rollout,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-staged-rollout (accessed Oct 20, 2026).

Microsoft Learn, “Migrate from federation to cloud authentication,” https://learn.microsoft.com/entra/identity/hybrid/connect/migrate-from-federation-to-cloud-authentication (accessed Oct 20, 2026).

Microsoft Learn, “Migrate from federation to cloud authentication,” https://learn.microsoft.com/entra/identity/hybrid/connect/migrate-from-federation-to-cloud-authentication (accessed Oct 20, 2026).

Gitea, “API Usage,” https://docs.gitea.com/development/api-usage (accessed Oct 20, 2026).

Gitea, API specification (CreateIssueOption), https://gitea.com/swagger.v1.json (accessed Oct 20, 2026).

Microsoft Learn, “Understanding errors during Microsoft Entra synchronization,” https://learn.microsoft.com/entra/identity/hybrid/connect/tshoot-connect-sync-errors (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra Connect for an existing tenant,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-install-existing-tenant (accessed Oct 20, 2026).

Microsoft Learn, “Understanding errors during Microsoft Entra synchronization,” https://learn.microsoft.com/entra/identity/hybrid/connect/tshoot-connect-sync-errors (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra Connect for an existing tenant,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-install-existing-tenant (accessed Oct 20, 2026).

Microsoft Learn, “Tutorial: Enable Microsoft Entra self-service password reset writeback to an on-premises environment,” https://learn.microsoft.com/entra/identity/authentication/tutorial-enable-sspr-writeback (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect: Configure AD DS Connector Account Permissions,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-configure-ad-ds-connector-account (accessed Oct 20, 2026).

Office of Management and Budget, M-22-09, Moving the U.S. Government Toward Zero Trust Cybersecurity Principles, January 26, 2022, https://www.whitehouse.gov/wp-content/uploads/2022/01/M-22-09.pdf (accessed Oct 20, 2026).

Office of Management and Budget, M-21-31, Improving the Federal Government’s Investigative and Remediation Capabilities Related to Cybersecurity Incidents, August 27, 2021, https://www.whitehouse.gov/wp-content/uploads/2021/08/M-21-31-Improving-the-Federal-Governments-Investigative-and-Remediation-Capabilities-Related-to-Cybersecurity-Incidents.pdf (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, “BOD 25-01: Implementation Guidance for Implementing Secure Practices for Cloud Services,” https://www.cisa.gov/news-events/directives/bod-25-01-implementation-guidance-implementing-secure-practices-cloud-services (accessed Oct 20, 2026).

FedRAMP, “FedRAMP 20x,” https://www.fedramp.gov/20x/ (accessed Oct 20, 2026).

Microsoft Learn, “Cloud feature availability for US Government customers,” https://learn.microsoft.com/azure/security/fundamentals/feature-availability#microsoft-365-integration (accessed Oct 20, 2026).

Microsoft Learn, “You can’t use Kerberos unconstrained delegation in certain versions of Windows,” https://learn.microsoft.com/troubleshoot/sql/database-engine/connect/windows-prevents-unconstrained-delegation (accessed Oct 20, 2026).

Microsoft Learn, “Register a Service Principal Name for Kerberos connections,” https://learn.microsoft.com/sql/database-engine/configure-windows/register-a-service-principal-name-for-kerberos-connections (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect Sync: Understand and customize synchronization,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-sync-whatis (accessed Oct 20, 2026).

Microsoft Learn, “Migrate from Microsoft Entra Connect to Cloud Sync: Decision Guide,” https://learn.microsoft.com/entra/identity/hybrid/cloud-sync/connect-to-cloud-sync-decision-guide (accessed Oct 20, 2026).

Microsoft Learn, “Configure infrastructure to support SCEP with Intune,” https://learn.microsoft.com/intune/fundamentals/certificates/scep-infrastructure (accessed Oct 20, 2026).

Microsoft Learn, “Overview of Microsoft Cloud PKI for Microsoft Intune,” https://learn.microsoft.com/intune/cloud-pki/ (accessed Oct 20, 2026).

Microsoft Learn, “SQL Server enabled by Azure Arc,” https://learn.microsoft.com/sql/sql-server/azure-arc/overview (accessed Oct 20, 2026).

Microsoft Learn, “Tutorial: Enable Microsoft Entra authentication for SQL Server on Windows without Azure Arc,” https://learn.microsoft.com/sql/relational-databases/security/authentication-access/microsoft-entra-authentication-sql-server-enable-without-arc (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra authentication for SQL Server,” https://learn.microsoft.com/sql/relational-databases/security/authentication-access/azure-ad-authentication-sql-server-overview (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-63-4, Digital Identity Guidelines, July 2025, https://csrc.nist.gov/pubs/sp/800/63/4/final (accessed Oct 20, 2026).

Microsoft Learn, “Troubleshoot SQL Server Kerberos and authentication failures with gMSAs,” https://learn.microsoft.com/troubleshoot/sql/database-engine/startup-shutdown/gmsa-kerberos-authentication-failures (accessed Oct 20, 2026).

Microsoft Learn, “Adaptive scopes,” https://learn.microsoft.com/purview/purview-adaptive-scopes (accessed Oct 20, 2026).

Microsoft Learn, “Connect to and manage Azure Arc-enabled SQL Server in Microsoft Purview,” https://learn.microsoft.com/purview/register-scan-azure-arc-enabled-sql-server (accessed Oct 20, 2026).

Microsoft Learn, “Fabric domains,” https://learn.microsoft.com/fabric/governance/domains (accessed Oct 20, 2026).

Microsoft Learn, “Mirroring SQL Server,” https://learn.microsoft.com/fabric/mirroring/sql-server (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Fabric for US Government GCC High customers,” https://learn.microsoft.com/fabric/enterprise/us-government-community-cloud-high (accessed Oct 20, 2026).

Microsoft Learn, “Power BI for US government customers,” https://learn.microsoft.com/fabric/enterprise/powerbi/service-government-us-overview (accessed Oct 20, 2026).

FedRAMP, “FedRAMP 20x,” https://www.fedramp.gov/20x/ (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-37 Rev. 2, Risk Management Framework for Information Systems and Organizations: A System Life Cycle Approach for Security and Privacy, December 2018, https://csrc.nist.gov/pubs/sp/800/37/r2/final (accessed Oct 20, 2026).

Microsoft Learn, “What is Microsoft Entra certificate-based authentication?,” https://learn.microsoft.com/entra/identity/authentication/concept-certificate-based-authentication (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra for increased security (Preview),” https://learn.microsoft.com/entra/fundamentals/configure-security (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra for increased security (Preview),” https://learn.microsoft.com/entra/fundamentals/configure-security (accessed Oct 20, 2026).

Microsoft Learn, “Known limitations for Global Secure Access,” section “Global Secure Access In Government Cloud limitations,” https://learn.microsoft.com/entra/global-secure-access/reference-current-known-limitations (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra for increased security (Preview),” https://learn.microsoft.com/entra/fundamentals/configure-security (accessed Oct 20, 2026).

Microsoft Learn, “Known limitations for Global Secure Access,” section “Global Secure Access In Government Cloud limitations,” https://learn.microsoft.com/entra/global-secure-access/reference-current-known-limitations (accessed Oct 20, 2026).

Microsoft Learn, “Dynamics 365 US Government,” https://learn.microsoft.com/power-platform/admin/microsoft-dynamics-365-government (accessed Oct 20, 2026). The page contrasts GCC High and DoD, which use Microsoft Entra Government, with GCC, which uses the public Microsoft Entra ID service.

Microsoft Learn, “Configure Microsoft Entra for increased security (Preview),” https://learn.microsoft.com/entra/fundamentals/configure-security (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra for increased security (Preview),” https://learn.microsoft.com/entra/fundamentals/configure-security (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, “BOD 25-01: Implementing Secure Practices for Cloud Services Required Configurations,” https://www.cisa.gov/resources-tools/services/bod-25-01-implementing-secure-practices-cloud-services-required-configurations (accessed Oct 20, 2026).

Microsoft Learn, “Implement password hash synchronization with Microsoft Entra Connect Sync,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-password-hash-synchronization (accessed Oct 20, 2026).

Microsoft Learn, “Configure Microsoft Entra for Zero Trust: Protect identities and secrets,” https://learn.microsoft.com/entra/fundamentals/zero-trust-protect-identities (accessed Oct 20, 2026).

Office of Management and Budget, M-22-09, Moving the U.S. Government Toward Zero Trust Cybersecurity Principles, January 26, 2022, https://bidenwhitehouse.archives.gov/wp-content/uploads/2022/01/M-22-09.pdf (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, “BOD 25-01: Implementing Secure Practices for Cloud Services Required Configurations,” https://www.cisa.gov/resources-tools/services/bod-25-01-implementing-secure-practices-cloud-services-required-configurations (accessed Oct 20, 2026).

Microsoft Learn, “Meet multifactor authentication requirements of memorandum 22-09,” https://learn.microsoft.com/entra/standards/memo-22-09-multi-factor-authentication (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, BOD 25-01, Implementing Secure Practices for Cloud Services, December 17, 2024, https://www.cisa.gov/news-events/directives/bod-25-01-implementing-secure-practices-cloud-services (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, BOD 25-01, Implementing Secure Practices for Cloud Services, December 17, 2024, https://www.cisa.gov/news-events/directives/bod-25-01-implementing-secure-practices-cloud-services (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, “BOD 25-01: Implementing Secure Practices for Cloud Services Required Configurations,” https://www.cisa.gov/resources-tools/services/bod-25-01-implementing-secure-practices-cloud-services-required-configurations (accessed Oct 20, 2026).

Cybersecurity and Infrastructure Security Agency, BOD 25-01, Implementing Secure Practices for Cloud Services, December 17, 2024, https://www.cisa.gov/news-events/directives/bod-25-01-implementing-secure-practices-cloud-services (accessed Oct 20, 2026).

Office of Management and Budget, M-22-09, Moving the U.S. Government Toward Zero Trust Cybersecurity Principles, January 26, 2022, https://bidenwhitehouse.archives.gov/wp-content/uploads/2022/01/M-22-09.pdf (accessed Oct 20, 2026).

Microsoft Learn, “Meet multifactor authentication requirements of memorandum 22-09,” https://learn.microsoft.com/entra/standards/memo-22-09-multi-factor-authentication (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect Sync: Scheduler,” https://learn.microsoft.com/entra/identity/hybrid/connect/how-to-connect-sync-feature-scheduler (accessed Oct 20, 2026).

National Institute of Standards and Technology, SP 800-53 Rev. 5, Security and Privacy Controls for Information Systems and Organizations, September 2020 (updated December 10, 2020; Release 5.2.0, August 27, 2025), https://csrc.nist.gov/pubs/sp/800/53/r5/upd1/final (accessed Oct 20, 2026).

National Institute of Standards and Technology, NIST SP 800-53 Rev. 5 catalog (OSCAL JSON, Release 5.2.0), usnistgov/oscal-content, https://raw.githubusercontent.com/usnistgov/oscal-content/main/nist.gov/SP800-53/rev5/json/NIST_SP-800-53_rev5_catalog.json (accessed Oct 20, 2026).

PKI Solutions, “PowerShell PKI (PSPKI) Module,” https://www.pkisolutions.com/tools/pspki/ (accessed Oct 20, 2026).

PowerShell Gallery, “PSPKI 4.4.1,” function list, https://www.powershellgallery.com/packages/PSPKI (accessed Oct 20, 2026).

Microsoft Learn, “ActiveDirectory Module,” cmdlet index, https://learn.microsoft.com/powershell/module/activedirectory/?view=windowsserver2025-ps (accessed Oct 20, 2026).

Gitea, API specification (OpenAPI 2.0), https://gitea.com/swagger.v1.json (accessed Oct 20, 2026). Confirm field names against /api/swagger on your own instance; they vary by Gitea version.

Microsoft Learn, “Get-GPPermission,” https://learn.microsoft.com/powershell/module/grouppolicy/get-gppermission?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “Get-DnsServerDnsSecZoneSetting,” https://learn.microsoft.com/powershell/module/dnsserver/get-dnsserverdnsseczonesetting?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “Configure DNS aging and scavenging,” https://learn.microsoft.com/windows-server/networking/dns/configure-aging-scavenging (accessed Oct 20, 2026).

Microsoft Learn, “Configure DNS aging and scavenging,” https://learn.microsoft.com/windows-server/networking/dns/configure-aging-scavenging (accessed Oct 20, 2026).

Microsoft Learn, “Security assessment: Certificates,” Microsoft Defender for Identity, https://learn.microsoft.com/defender-for-identity/security-posture-assessments/certificates (accessed Oct 20, 2026).

Microsoft Learn, “X509CertificateTemplateSubjectNameFlag enumeration (certenroll.h),” https://learn.microsoft.com/windows/win32/api/certenroll/ne-certenroll-x509certificatetemplatesubjectnameflag (accessed Oct 20, 2026).

Microsoft Learn, “X509CertificateTemplateEnrollmentFlag enumeration (certenroll.h),” https://learn.microsoft.com/windows/win32/api/certenroll/ne-certenroll-x509certificatetemplateenrollmentflag (accessed Oct 20, 2026).

Microsoft Learn, “Certificate-Enrollment extended right,” https://learn.microsoft.com/windows/win32/adschema/r-certificate-enrollment (accessed Oct 20, 2026).

Microsoft Learn, “Guidelines for enabling smart card logon with third-party certification authorities,” https://learn.microsoft.com/troubleshoot/windows-server/certificates-and-public-key-infrastructure-pki/enabling-smart-card-logon-third-party-certification-authorities (accessed Oct 20, 2026).

Internet Engineering Task Force, RFC 4556, Public Key Cryptography for Initial Authentication in Kerberos (PKINIT), June 2006, https://www.rfc-editor.org/rfc/rfc4556 (accessed Oct 20, 2026).

Internet Engineering Task Force, RFC 5280, Internet X.509 Public Key Infrastructure Certificate and Certificate Revocation List (CRL) Profile, section 4.2.1.12, May 2008, https://www.rfc-editor.org/rfc/rfc5280 (accessed Oct 20, 2026).

Microsoft Learn, “Monitor AD CS publication health with Enterprise PKI,” section “Understand Public Key Services data,” https://learn.microsoft.com/windows-server/identity/ad-cs/monitor-ad-cs-health-enterprise-pki (accessed Oct 20, 2026).

Microsoft Learn, “certutil,” https://learn.microsoft.com/windows-server/administration/windows-commands/certutil (accessed Oct 20, 2026).

Microsoft Learn, “Security assessment: Certificates,” Microsoft Defender for Identity, https://learn.microsoft.com/defender-for-identity/security-posture-assessments/certificates (accessed Oct 20, 2026).

Microsoft Learn, “Security assessment: Certificates,” Microsoft Defender for Identity, https://learn.microsoft.com/defender-for-identity/security-posture-assessments/certificates (accessed Oct 20, 2026).

Microsoft Learn, “Kerberos Constrained Delegation Overview,” https://learn.microsoft.com/windows-server/security/kerberos/kerberos-constrained-delegation-overview, and “Making the second hop in PowerShell Remoting,” https://learn.microsoft.com/powershell/scripting/security/remoting/ps-remoting-second-hop (accessed Oct 20, 2026).

Microsoft Learn, “Privileged access security levels,” https://learn.microsoft.com/security/privileged-access-workstations/privileged-access-security-levels (accessed Oct 20, 2026).

Microsoft Learn, “Reducing the Active Directory Attack Surface,” https://learn.microsoft.com/windows-server/identity/ad-ds/plan/security-best-practices/reducing-the-active-directory-attack-surface (accessed Oct 20, 2026).

Microsoft Learn, “Windows Server 2008 and newer domain controller returns only 5000 values in an LDAP response,” https://learn.microsoft.com/troubleshoot/windows-server/active-directory/domain-controller-returns-500-values-ldap-response (accessed Oct 20, 2026).

Microsoft Learn, “ms-DS-Group-Managed-Service-Account class,” https://learn.microsoft.com/windows/win32/adschema/c-msds-groupmanagedserviceaccount (accessed Oct 20, 2026).

Microsoft Learn, “Delegated Managed Service Accounts overview,” https://learn.microsoft.com/windows-server/identity/ad-ds/manage/delegated-managed-service-accounts/delegated-managed-service-accounts-overview (accessed Oct 20, 2026).

Microsoft, [MS-ADTS] Active Directory Technical Specification, “trustAttributes,” https://learn.microsoft.com/openspecs/windows_protocols/ms-adts/e9a2d23c-c31e-4a6f-88a0-6646fdb51a3c (accessed Oct 20, 2026).

Microsoft Learn, “netdom trust,” https://learn.microsoft.com/windows-server/administration/windows-commands/netdom-trust (accessed Oct 20, 2026).

Gitea, API specification (OpenAPI 2.0), https://gitea.com/swagger.v1.json (accessed Oct 20, 2026). Confirm field names against /api/swagger on your own instance; they vary by Gitea version.

Gitea, “API Usage,” https://docs.gitea.com/development/api-usage (accessed Oct 20, 2026).

Gitea, API specification (OpenAPI 2.0), https://gitea.com/swagger.v1.json (accessed Oct 20, 2026). Confirm field names against /api/swagger on your own instance; they vary by Gitea version.

Microsoft Learn, “Run assessments with Managed Service Accounts,” Microsoft Engage Center, https://learn.microsoft.com/services-hub/microsoft-engage-center/health/kb/kb-running-assessments-with-msas (accessed Oct 20, 2026).

Microsoft Learn, “New-ScheduledTaskPrincipal,” parameter -LogonType, https://learn.microsoft.com/powershell/module/scheduledtasks/new-scheduledtaskprincipal?view=windowsserver2025-ps, and “Manage group Managed Service Accounts,” https://learn.microsoft.com/windows-server/identity/ad-ds/manage/group-managed-service-accounts/group-managed-service-accounts/manage-group-managed-service-accounts (accessed Oct 20, 2026).

Microsoft Learn, “Set-ADForestMode,” parameter -ForestMode, https://learn.microsoft.com/powershell/module/activedirectory/set-adforestmode?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “Set-ADDomainMode,” parameter -DomainMode, https://learn.microsoft.com/powershell/module/activedirectory/set-addomainmode?view=windowsserver2025-ps (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect Sync: Attributes synchronized to Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/hybrid/connect/reference-connect-sync-attributes-synchronized (accessed Oct 20, 2026).

Microsoft Learn, “user resource type,” https://learn.microsoft.com/graph/api/resources/user?view=graph-rest-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect Sync: Attributes synchronized to Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/hybrid/connect/reference-connect-sync-attributes-synchronized (accessed Oct 20, 2026).

Microsoft Learn, “user resource type,” https://learn.microsoft.com/graph/api/resources/user?view=graph-rest-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Connect Sync: Attributes synchronized to Microsoft Entra ID,” https://learn.microsoft.com/entra/identity/hybrid/connect/reference-connect-sync-attributes-synchronized (accessed Oct 20, 2026).

Microsoft Learn, “Managing users synchronized from Active Directory Domain Services to Microsoft Entra ID with Lifecycle workflows,” https://learn.microsoft.com/entra/id-governance/lifecycle-workflow-on-premises (accessed Oct 20, 2026).

Microsoft Learn, “Conditional Access authentication strengths,” https://learn.microsoft.com/entra/identity/authentication/concept-authentication-strengths (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Graph national cloud deployments,” https://learn.microsoft.com/graph/deployments (accessed Oct 20, 2026).

Microsoft Learn, “conditionalAccessGrantControls resource type,” https://learn.microsoft.com/graph/api/resources/conditionalaccessgrantcontrols?view=graph-rest-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Configure and enable risk policies,” https://learn.microsoft.com/entra/id-protection/howto-identity-protection-configure-risk-policies (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra Conditional Access for workload identities,” https://learn.microsoft.com/entra/identity/conditional-access/workload-identity (accessed Oct 20, 2026).

Microsoft Learn, “Archive for Microsoft Entra releases and announcements” (January 2025: MSOnline and AzureAD PowerShell retirement), https://learn.microsoft.com/entra/fundamentals/whats-new-archive (accessed Oct 20, 2026).

Microsoft Learn, “Upgrade from Azure AD PowerShell to Microsoft Graph PowerShell,” https://learn.microsoft.com/powershell/microsoftgraph/migration-steps?view=graph-powershell-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Find Azure AD PowerShell and MSOnline cmdlets in Microsoft Graph PowerShell,” https://learn.microsoft.com/powershell/microsoftgraph/azuread-msoline-cmdlet-map?view=graph-powershell-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Find Azure AD PowerShell and MSOnline cmdlets in Microsoft Graph PowerShell,” https://learn.microsoft.com/powershell/microsoftgraph/azuread-msoline-cmdlet-map?view=graph-powershell-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Migrate from federation to cloud authentication,” https://learn.microsoft.com/entra/identity/hybrid/connect/migrate-from-federation-to-cloud-authentication (accessed Oct 20, 2026).

Microsoft Learn, “unifiedRoleAssignmentSchedule resource type,” https://learn.microsoft.com/graph/api/resources/unifiedroleassignmentschedule?view=graph-rest-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Get-MgRoleManagementDirectoryRoleEligibilitySchedule,” https://learn.microsoft.com/powershell/module/microsoft.graph.identity.governance/get-mgrolemanagementdirectoryroleeligibilityschedule?view=graph-powershell-1.0 (accessed Oct 20, 2026).

Microsoft Learn, “Reducing the Active Directory Attack Surface,” https://learn.microsoft.com/windows-server/identity/ad-ds/plan/security-best-practices/reducing-the-active-directory-attack-surface (accessed Oct 20, 2026).

Microsoft Learn, “Microsoft Entra audit log categories and activities,” https://learn.microsoft.com/entra/identity/monitoring-health/reference-audit-activities (accessed Oct 20, 2026).

Gitea, “API Usage,” https://docs.gitea.com/development/api-usage (accessed Oct 20, 2026).

Gitea, API specification (CreateIssueOption), https://gitea.com/swagger.v1.json (accessed Oct 20, 2026).