# H. Program Management

Modernization Workbook — Word edition

Table of Contents

# H. Program Management

The program-level artifacts that govern modernization execution at the organization scale: the capstone plan, the phased roadmap, the architecture decision log, change-management integration, and end-user enablement.

## Leaves

- H.1 Master Project Plan (capstone)

- H.2 Migration Roadmap

- H.3 Architecture Decision Records (ADRs)

- H.4 ServiceNow change / incident integration — adapter

- H.5 SAM (software asset management)

- H.6 End-user training

# The Federal Modernization Program Master Project Plan

The Federal Modernization Program Master Project Plan

Assessment Phase Through Full Modernization

The Federal Modernization Program — Capstone Planning Document

| Document ID: | FMP_013_Master_Project_Plan_v1.0 |
| --- | --- |
| Classification: | Controlled |
| Boundary: | GCC-Moderate |
| Repository: | https://github.com/WhalerMike/modernization-workbook |
| Author: | Michael — Canon Steward |
| Date: | 21 April 2026 |
| Status: | DRAFT |

Companion Document Corpus ¦ ¦ This Master Project Plan references and unifies the following twelve the Federal Modernization Program documents produced to date: ¦ > 1. AD Computer Object Conversion Guide ¦ > ¦ > 2. Git on Windows Server 2025 with IIS — Step-by-Step Implementation Guide ¦ > ¦ > 3. The Federal Modernization Program Git Server — Windows Server 2025 with IIS Implementation Guide > ¦ > 4. The Federal Modernization Program Git Infrastructure — Architecture Decision Record > ¦ > 5. The Federal Modernization Program Platform Server Build Guide — Windows Server 2025 with Gitea and IIS > ¦ > 6. The Federal Modernization Program CLI and Operations Guide > ¦ > 7. The Federal Modernization Program Active Directory Interaction Guide > ¦ > 8. The Federal Modernization Program Identity Modernization Guide > ¦ > 9. The Federal Modernization Program DNS Modernization Guide > ¦ > 10. The Federal Modernization Program Read-Only AD Assessment Guide > ¦ > 11. The Federal Modernization Program vs Microsoft Native Tools — Gap Analysis > ¦ > 12. The Federal Modernization Program PKI Modernization Guide

1. Executive Summary

The Federal Modernization Program Modernization Program transforms legacy Active Directory infrastructure into a cloud-native, governance-driven, drift-resistant operating model. The program spans five transformation pillars — Identity, Devices, DNS, PKI, and Server Management — and replaces fragile, GUI-configured infrastructure with machine-readable canonical artifacts managed through the Federal Modernization Program pipeline backed by Gitea on Windows Server 2025.

This Master Project Plan is the capstone planning document for the Federal Modernization Program corpus. It defines the full lifecycle from initial assessment through steady-state governance, organized into seven phases with 48 milestones across a 52-week execution timeline. Every phase is milestone-gated: no phase transition occurs without formal review, documented approval, and artifact commitment to the Federal Modernization Program Gitea repository.

The plan is structured around one central principle:

Core Principle: Assessment Before Action ¦ ¦ No migration activity begins until the complete Active Directory forest has been inventoried, classified, and committed to the Federal Modernization Program Gitea governance pipeline as machine-readable canonical artifacts. Every modernization plan — computer, identity, GPO, DNS, PKI — is generated from assessment data, not designed in isolation. The assessment phase produces every planning artifact that drives all subsequent phases.

Phase 1 (Assessment) is the most detailed phase in this document because it produces every planning artifact that drives all subsequent phases. The assessment generates 23 canonical deliverables spanning 12 AD domains. These deliverables feed eight modernization plans that define the exact scope, sequence, and success criteria for every action taken in Phases 2 through 6. Without a complete, committed, and approved assessment, the program cannot proceed.

The program draws its technical procedures, architectural decisions, and governance model from the twelve companion documents listed above. This plan does not replicate their content; it sequences their execution, assigns ownership, defines milestones, and provides the governance framework that ensures coordinated, traceable, and reversible modernization.

Program Timeline Summary

| Phase | Name | Duration | Weeks | Key Milestone |
| --- | --- | --- | --- | --- |
| 0 | Platform Build | 3 weeks | 1–3 | the Federal Modernization Program Gitea server operational |
| 1 | Assessment | 6 weeks | 4–9 | Full AD forest assessment committed to Gitea |
| 2 | Planning & Design | 4 weeks | 10–13 | All modernization plans approved |
| 3 | Pilot | 8 weeks | 14–21 | Pilot group validated on all five pillars |
| 4 | Scale | 12 weeks | 22–33 | Full production migration |
| 5 | Cutover | 8 weeks | 34–41 | Legacy infrastructure decommissioned |
| 6 | Steady State | Ongoing | 42+ | Continuous governance and drift detection |

[Diagram: The Federal Modernization Program Program Timeline — Gantt Overview] ¦ Seven-phase horizontal timeline showing parallel workstreams per pillar (Identity, Devices, DNS, PKI, Server), milestone diamonds at phase gates, and critical path highlighted. ¦ ¦ Diagram ID: FMP-MPP-D001 ¦ Dimensions: 780 × 320 px ¦

2. Program Governance Structure

2.1 Roles and Responsibilities

| Role | Responsibility | Person / Team |
| --- | --- | --- |
| Canon Steward | Final authority on governance artifacts, approval gates, document status transitions, Gitea repository integrity, and cross-pillar conflict resolution | [Named Individual] |
| Infrastructure Lead | Server builds, IIS reverse proxy, Gitea administration, network infrastructure, Azure Arc enrollment, hardware provisioning | [Infrastructure Team] |
| Identity Lead | Active Directory, Entra ID, Entra Connect, Conditional Access, PIM, extension attribute design, user and group migration | [Identity Team] |
| Endpoint Lead | Intune enrollment, device compliance, GPO-to-Intune policy migration, Settings Catalog configuration, dynamic group design | [Endpoint Management Team] |
| DNS Lead | AD-integrated DNS zones, Azure DNS Private Resolver, forwarding rulesets, split-brain patterns, SRV record validation | [DNS / Network Team] |
| PKI Lead | ADCS management, Cloud PKI provisioning, Entra CBA, certificate template migration, ESC vulnerability remediation, SCEP/PKCS profile design | [PKI / Security Team] |
| Security Lead | ESC remediation, Defender for Identity integration, Conditional Access policy design, security assessment triage, risk acceptance | [Security Team] |
| Project Manager | Timeline management, milestone tracking, risk register maintenance, status reporting, steering committee coordination | [Named Individual] |

2.2 Decision Framework

| Decision Type | Authority | Process |
| --- | --- | --- |
| Governance decisions (artifact status, naming, schema) | Canon Steward — sole approval | Gitea pull request with Canon Steward review required |
| Technical decisions (architecture, configuration) | Respective pillar lead with Canon Steward review | ADR committed to Gitea, 48-hour review period |
| Risk acceptance | Security Lead + Canon Steward joint approval | Risk acceptance form committed with justification |
| Schedule changes (milestone date movement) | Project Manager + Canon Steward | Schedule change request with impact analysis |
| Budget / license procurement | Canon Steward + organizational leadership | Business case document committed to Gitea |

2.3 Communication Cadence

| Meeting | Frequency | Duration | Attendees | Output |
| --- | --- | --- | --- | --- |
| Daily Standup | Daily (weekdays) | 15 min | All pillar leads | Blockers identified, today's priorities |
| Weekly Status Report | Weekly (Friday) | N/A (written) | PM authors, all review | Committed to Gitea as reports/weekly/YYYY-WNN.md |
| Biweekly Steering Committee | Every 2 weeks | 60 min | Canon Steward + all leads | Decision log, action items committed to Gitea |
| Milestone Gate Review | At each phase gate | 90 min | All roles + stakeholders | Go/No-Go decision, gate review report (Appendix D template) |

2.4 Artifact Management

All project artifacts are committed to Gitea under the Federal Modernization Program repository. The governance pipeline ensures every artifact is versioned, reviewed, and traceable.

Branch Strategy:

- main — Canonical branch. Only approved artifacts reside here. Protected: requires pull request with Canon Steward approval.

- feature/* — Work-in-progress branches for active development (e.g., feature/pki-assessment).

- release/* — Milestone snapshots frozen at phase gate approval (e.g., release/phase-1-assessment).

Naming Convention:

FMP_NNN_Short_Title_vMajor.Minor.md

Status Lifecycle:

| Status | Meaning | Transition Authority |
| --- | --- | --- |
| DRAFT | Under active authoring; may be incomplete | Author creates |
| IN_REVIEW | Pull request submitted; awaiting review | Author submits PR |
| APPROVED | Canon Steward has approved; merged to main | Canon Steward merges |
| CURRENT | Active, governing artifact | Automatic upon merge to main |
| DEPRECATED | Superseded by newer version; retained for history | Canon Steward marks |

3. Phase 0: Platform Build (Weeks 1–3)

Objective: Deploy the Federal Modernization Program platform server — Gitea on Windows Server 2025 behind IIS reverse proxy, integrated with Active Directory LDAP and Entra ID OAuth2 — establishing the canonical repository that will govern all subsequent phases.

Reference Documents: the Federal Modernization Program Platform Server Build Guide — Windows Server 2025 with Gitea and IIS (primary), the Federal Modernization Program Git Infrastructure — Architecture Decision Record, the Federal Modernization Program CLI and Operations Guide, Git on Windows Server 2025 with IIS — Step-by-Step Implementation Guide.

3.1 Phase 0 Milestone Table

| ID | Milestone | Week | Deliverable | Gate Criteria | Owner |
| --- | --- | --- | --- | --- | --- |
| M-001 | Server provisioned | W1 | Windows Server 2025 base build | Server online, domain-joined, CIS L1 hardened, Windows Update current | Infra Lead |
| M-002 | IIS + Gitea operational | W2 | Gitea running behind IIS reverse proxy on HTTPS | Clone/push/pull over HTTPS verified from workstation | Infra Lead |
| M-003 | AD LDAP auth configured | W2 | Gitea authenticating against AD via LDAPS | AD users can login; CanonStewards group has admin role | Identity Lead |
| M-004 | Entra ID OAuth2 configured | W3 | Gitea SSO via Entra ID OIDC | Entra SSO login verified; MFA enforced for all Gitea sessions | Identity Lead |
| M-005 | the Federal Modernization Program | repo mirro | red from GitHub W3 https://github.com/example | -org/fmp mirrored to Gitea All branches, tags, and full commit history | verified Canon Steward |
| M-006 | Governance hooks deployed | W3 | Pre-receive, post-receive, update hooks operational | FOUO rejection verified; branch protection enforced | Canon Steward |
| M-007 | Azure Arc enrollment | W3 | Server enrolled in Azure Arc with resource tags | Arc agent heartbeat confirmed; Azure policies | assigned Infra Lead |

3.2 Detailed Task Breakdown

M-001 — Server Provisioned (Week 1)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-001.1 | Provision VM or physical server: 4 vCPU, 8 GB RAM, 100 GB SSD, Windows Server 2025 Standard | 4h | Hardware/VM approval | Platform Server Build Guide §2 |
| T-001.2 | Join to Active Directory domain, place in designated OU, verify DNS registration | 2h | T-001.1 | Platform Server Build Guide §3 |
| T-001.3 | Apply CIS Level 1 hardening baseline, disable unnecessary services, configure Windows Firewall | 4h | T-001.2 | Platform Server Build Guide §4 |
| T-001.4 | Install Windows Updates, enable automatic update schedule, configure WSUS if applicable | 2h | T-001.3 | Platform Server Build Guide §4 |
| T-001.5 | Create D:\FMP directory structure, configure NTFS permissions for Gitea service account 1 | h T | -001.2 P | latform Server Build Guide §5 |

M-002 — IIS + Gitea Operational (Week 2)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-002.1 | Install IIS with URL Rewrite and Application Request Routing (ARR) modules | 2h | M-001 | Git on Windows Server 2025 with IIS Guide §3 |
| T-002.2 | Obtain and bind TLS certificate for git.example.internal; configure HTTPS binding on port 443 | 3h | T-002.1, internal CA or A | DCS Platform Server Build Guide §7 |
| T-002.3 | Download Gitea binary, install as Windows service, generate app.ini with PostgreSQL backend (DB_TYPE = p | ostgres, pg0 | 1.corp.contoso.com, database fm | p_gitea) 4h T-002.1 Platform Server Build Guide §6 |
| T-002.4 | Configure IIS reverse proxy (web.config) routing port 443 → Gitea localhost:3000 | 3h | T-002.2, T-002.3 | Platform Server Build Guide §8, Git Infrastructure ADR §4 |
| T-002.5 | Validate end-to-end: clone, commit, push, pull via HTTPS from remote workstation | 2h | T-002.4 | CLI and Operations Guide §3 |

M-003 — AD LDAP Auth Configured (Week 2)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-003.1 | Create LDAP bind service account in AD with read-only access to user objects | 1h | None | Platform Server Build Guide §9 |
| T-003.2 | Configure Gitea LDAP authentication source with LDAPS (port 636), base DN, and user filter | 2h | T-002.3, T-003.1 | Platform Server Build Guide §9 |
| T-003.3 | Map AD group CanonStewards to Gitea admin role via group filter | 1h | T-003.2 | Platform Server Build Guide §9 |
| T-003.4 | Test login with three AD accounts (admin, contributor, read-only) and verify role assignments | 1h | T-003.3 | Platform Server Build Guide §10 |

M-004 — Entra ID OAuth2 Configured (Week 3)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-004.1 | Register Gitea as an Enterprise Application in Entra ID; configure redirect URIs | 2h | Entra ID Global Admin access | Platform Server Build Guide §11 |
| T-004.2 | Configure Gitea OAuth2 authentication source with OIDC discovery endpoint, client ID/secret | 2h | T-004.1, T-002.3 | Platform Server Build Guide §11 |
| T-004.3 | Configure Conditional Access policy requiring MFA for Gitea app (report-only initially) | 2h | T-004.1 | Identity Modernization Guide §8 |
| T-004.4 | Validate SSO login flow, MFA prompt, and account linking between LDAP and OAuth2 identities | 2h | T-004.2, T-004.3 | Platform Server Build Guide §11 |

M-005 — the Federal Modernization Program Repo Mirrored (Week 3)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-005.1 | Create the Federal Modernization Program organization in Gitea with team structure (CanonStewar | ds, Contribu | tors, Readers) 1h | M-002 CLI and Operations Guide §4 |
| T-005.2 | Configure Gitea mirror from https://github.com/example-org/fmp with scheduled sync | 2h | T-005.1, outbound HTTPS | CLI and Operations Guide §5 |
| T-005.3 | Verify all branches, tags, and full commit history are present; validate commit count | 1h | T-005.2 | CLI and Operations Guide §5 |

M-006 — Governance Hooks Deployed (Week 3)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-006.1 | Deploy pre-receive hook: reject commits containing FOUO markings, enforce commit message format | 3h | M-005 | Platform Server Build Guide §12 |
| T-006.2 | Deploy update hook: enforce branch protection rules (main requires PR, no force push) | 2h | M-005 | Platform Server Build Guide §12 |
| T-006.3 | Deploy post-receive hook: trigger notification on merge to main, update AssessmentManifest | 2h | M-005 | Platform Server Build Guide §12 |
| T-006.4 | Test all hooks with known-good and known-bad commits; document test results | 2h | T-006.1 – T-006.3 | Platform Server Build Guide §12 |

M-007 — Azure Arc Enrollment (Week 3)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-007.1 | Install Azure Connected Machine agent on the Federal Modernization Program Git Server |  | 1h | M-001, Azure subscription AD Computer Object Conversion Guide §8 |
| T-007.2 | Apply resource tags to Arc resource (Region, Site, Department, Role = GitServer) |  | 1h T | -007.1 AD Computer Object Conversion Guide §2 |
| T-007.3 | Assign Azure Policy initiatives for Windows Server 2025 Guest Configuration | 2h | T-007.2 | AD Computer Object Conversion Guide §8 |
| T-007.4 | Verify Arc agent heartbeat, policy compliance status, and Guest Configuration reports | 1h | T-007.3 | AD Computer Object Conversion Guide §8 |

3.3 Phase 0 Exit Criteria

Phase 0 Gate Review — Go/No-Go Checklist ¦ ¦ > • Gitea web UI accessible at https://git.example.internal ¦ > ¦ > • AD LDAP and Entra ID OAuth2 authentication both operational and tested ¦ > ¦ > • the Federal Modernization Program repository fully mirrored with complete commit history from GitHub > ¦ > • Governance hooks rejecting FOUO markings and enforcing branch protection — test evidence committed ¦ > ¦ > • Azure Arc enrolled with resource tags applied and Guest Configuration policies compliant ¦ > ¦ > • Phase 0 completion report committed to Gitea at reports/phase-gates/phase-0-completion.md ¦ > ¦ > • All milestone deliverables listed in M-001 through M-007 verified and signed off by respective owner ¦

4. Phase 1: Assessment (Weeks 4–9) — Detailed

Critical Phase This is the most critical and detailed section of the entire project plan. Phase 1 produces every planning artifact that drives all subsequent phases. No migration activity begins until Phase 1 is complete and approved. The assessment covers 12 domains across the complete AD forest, generating 23 canonical deliverables that feed 8 modernization plans.

Reference Documents: the Federal Modernization Program Active Directory Interaction Guide (primary), the Federal Modernization Program Read-Only AD Assessment Guide, the Federal Modernization Program vs Microsoft Native Tools — Gap Analysis.

4.1 Assessment Scope

The assessment covers 12 domains across the complete AD forest. Each domain has a dedicated the Federal Modernization Program assessment function, a defined output artifact, and a reference to the companion document containing the detailed procedure.

| Domain | Assessment Tool | Output | Companion Document |
| --- | --- | --- | --- |
| Forest Topology | Export-FMPForestTopology F | orestTopology.json A | D Interaction Guide §3 |
| OU Hierarchy | Export-FMPOUHierarchy O | UHierarchy.json, OUTree.txt A | D Interaction Guide §4 |
| GPO Inventory | Export-FMPGPOInventory G | POInventory.json, XML reports A | D Interaction Guide §5 |
| DNS Infrastructure | Export-FMPDNSAssessment D | NSInventory.json A | D Interaction Guide §6, DNS Modernization Guide §4 |
| PKI / ADCS | Export-FMPPKIInventory P | KIInventory.json, ESCVulnerabilities.csv A | D Interaction Guide §7, PKI Modernization Guide §3 |
| Computer Objects | Export-FMPComputerInventory C | omputerInventory.json A | D Interaction Guide §8 |
| User Objects | Export-FMPUserInventory U | serInventory.json, PrivilegedUsers.csv A | D Interaction Guide §9 |
| Group Memberships | Export-FMPGroupInventory G | roupInventory.json A | D Interaction Guide §9 |
| Trust Relationships | Export-FMPTrustMap T | rustMap.json A | D Interaction Guide §10 |
| Service Accounts | Export-FMPServiceAccountInventory S | erviceAccounts.csv I | dentity Modernization Guide §6 |
| ACL / Delegation | Export-FMPACLReport O | UDelegation.json A | D Interaction Guide §11 |
| Schema Extensions | Export-FMPSchemaExtensions S | chemaExtensions.json A | D Interaction Guide §12 |

4.2 Assessment Execution Sequence

Week 4 — Pre-Assessment (Read-Only)

| Task ID | Task | Description | Hours | Reference |
| --- | --- | --- | --- | --- |
| T-4.1 | Deploy assessment workstation | Provision PAW or dedicated VM with Windows 11, domain-joined, restricted network access. Install PowerShell 7.x and Git for Windows. | 4h | Read-Only AD Assessment Guide §2 |
| T-4.2 | Install RSAT modules | Install ActiveDirectory, GroupPolicy, DnsServer, and ADCSAdministration RSAT modules. Verify module import succeeds. | 2h | Read-Only AD Assessment Guide §3 |
| T-4.3 | Run Test-FMPReadAccess E | xecute permission discovery to determine what can be assessed with current user credentials without any delegation. Document accessible vs. restricted domains. 2 | h R | ead-Only AD Assessment Guide §4 |
| T-4.4 | Execute Invoke-FMPReadOnlyAssessment R | un the master read-only orchestrator. Captures approximately 87% of total assessment value including forest topology, OU hierarchy, computer objects, user objects, group memberships, and basic GPO inventory — all without elevated permissions. 8 | h R | ead-Only AD Assessment Guide §5 |
| T-4.5 | Commit read-only assessment to Gitea | Stage all output under assessments/readonly/{domain}/{timestamp}/ and push to feature/phase1-assessment branch. Create pull request for Canon Steward review. | 2h | CLI and Operations Guide §6 |
| T-4.6 | Generate Delegation Request | From the read-only results, generate a formal delegation request documenting the specific permissions needed to assess the remaining 13%: DNS zone read, PKI CA Admin read, deleted objects read, GPO backup rights. | 3h | Read-Only AD Assessment Guide §8 |

| Milestone | ID | Gate Criteria |
| --- | --- | --- |
| Read-only assessment committed to Gitea | M-008 | Read-only assessment reviewed by Canon Steward; delegation request submitted to AD team |

Week 5 — Delegated Assessment

| Task ID | Task | Description | Hours | Reference |
| --- | --- | --- | --- | --- |
| T-5.1 | Receive delegated read access | AD team grants read-only delegated access for DNS zones, PKI certificate authority, deleted objects container, and GPO backup permissions. Verify with Test-FMPReadAccess re-run. 2 | h R | ead-Only AD Assessment Guide §8 |
| T-5.2 | Execute full DNS assessment | Run Get-FMPDNSAssessment with DnsServer module access. Enumerate all forward/reverse zones, zone types (AD-integrated, primary, stub, conditional forwarder), aging/scavenging settings, and record counts. 4 | h A | D Interaction Guide §6, DNS Modernization Guide §4 |
| T-5.3 | Execute full PKI assessment | Run Get-FMPPKIInventory with CA Admin read access. Enumerate all CAs (root, issuing, policy), certificate templates, enrollment permissions, template security descriptors, and CRL distribution points. 6 | h A | D Interaction Guide §7, PKI Modernization Guide §3 |
| T-5.4 | Execute full GPO backup | Run Backup-GPO -All to capture all GPO settings as XML. Parse XML reports with Export-FMPGPOInventory to create structured JSON with per-setting classification. 4 | h A | D Interaction Guide §5 |
| T-5.5 | Execute deleted objects enumeration | Enumerate tombstoned objects in the AD recycled objects container to identify recently deleted accounts, groups, and computer objects that may impact migration planning. | 2h | AD Interaction Guide §12 |
| T-5.6 | Commit full assessment delta to Gitea | Stage all new and updated artifacts under assessments/full/{domain}/{timestamp}/. Merge into feature/phase1-assessment branch. Update AssessmentManifest.json. | 2h | CLI and Operations Guide §6 |

| Milestone | ID | Gate Criteria |
| --- | --- | --- |
| Full assessment committed to Gitea | M-009 | Full assessment reviewed; no critical gaps remaining; all 12 domains covered |

Week 6 — Security Assessment

| Task ID | Task | Description | Hours | Reference |
| --- | --- | --- | --- | --- |
| T-6.1 | Run ESC vulnerability analysis | Execute Test-FMPESCVulnerabilities against all certificate templates. Identify ESC1 through ESC8 misconfigurations. Output ESCVulnerabilities.csv with per-template severity and remediation recommendation. 6 | h P | KI Modernization Guide §3 |
| T-6.2 | Run privileged access audit | Enumerate all accounts with AdminCount=1, Kerberoastable SPNs, unconstrained delegation, AS-REP roastable accounts, password-never-expires, and stale privileged accounts (>90 days inactive). | 4h | Identity Modernization Guide §5 |
| T-6.3 | Import Defender for Identity findings | If Microsoft Defender for Identity is deployed, export Secure Score findings and import via Import-DefenderForIdentityFindings adapter. Merge with the Federal Modernization Program findings. |  | 3h the Federal Modernization Program vs Microsoft Native Tools — Gap Analysis §7 |
| T-6.4 | Import PingCastle / Purple Knight results | If third-party AD security tools have been run, import and correlate findings with the Federal Modernization Program assessment data. Reconcile overlapping findings to eliminate duplicates. |  | 3h the Federal Modernization Program vs Microsoft Native Tools — Gap Analysis §9 |
| T-6.5 | Generate consolidated security findings report | Merge all sources (the Federal Modernization Program, Defender for Identity, PingCastle) into a single SecurityFindings.json with deduplicated, normalized findings. |  | 4h — |
| T-6.6 | Classify findings by severity | Assign each finding: Critical (blocks migration), High (must remediate before Phase 3), Medium (remediate during Phase 4), Low (accept or track). | 4h | — |
| T-6.7 | Commit security assessment to Gitea | Commit all security artifacts under assessments/security/{timestamp}/ and update AssessmentManifest.json. | 1h | CLI and Operations Guide §6 |

| Milestone | ID | Gate Criteria |
| --- | --- | --- |
| Security assessment complete, findings classified | M-010 | Critical findings identified with remediation plan drafted; High findings scheduled before Phase 3 |

Week 7 — Planning Document Generation

From the assessment data, the following eight planning documents are generated. Each planning document is machine-readable JSON, produced by a Federal Modernization Program plan generator function, and driven entirely by assessment output — not by manual design.

| Task ID | Planning Document | Description | Input Artifacts | Reference |
| --- | --- | --- | --- | --- |
| T-7.1 | ComputerModernizationPlan.json | Classify every computer object into migration path: Entra Join, Hybrid Join, Azure Arc, Retain, or Decommission. Include OS version, last logon, extension attribute assignment, and target Intune policy group. | ComputerInventory.json | AD Computer Object Conversion Guide |
| T-7.2 | IdentityModernizationPlan.json | Classify every user, group, and service account into migration path: Cloud-only, Synced, gMSA conversion, Workload Identity, or Retain. Map privileged accounts to PIM roles. | UserInventory.json, GroupInventory.json, ServiceAccounts.csv | Identity Modernization Guide |
| T-7.3 | GPOMigrationPlan.json | Decompose every GPO into individual configuration intents. Classify each intent into Intune policy type (Settings Catalog, Endpoint Security, ADMX template, custom OMA-URI, or no equivalent). Track per-intent migration status. | GPOInventory.json | AD Computer Object Conversion Guide §4 |
| T-7.4 | DNSModernizationPlan.json | Classify every DNS zone and record into migration path: Azure DNS Private Zone, Azure DNS Public Zone, Private Resolver Forwarding, Retain AD-Integrated, or Decommission. | DNSInventory.json | DNS Modernization Guide |
| T-7.5 | PKIModernizationPlan.json | Classify every certificate template into MIGRATE (Cloud PKI), BRIDGE (hybrid issuance), RETAIN (on-prem only), or RETIRE. Include ESC remediation status per template. | PKIInventory.json | PKI Modernization Guide §4 |
| T-7.6 | AttributeDesign.json | Define canonical extension attribute dimensions (Region, Site, Department, Role, Environment) and value lists. Map OU hierarchy analysis to extension attribute dimension values. Define extension attribu | te assignments. | OUHierarchy.json AD Computer Object Conversion Guide §2 |
| T-7.7 | TrustDecommissionPlan.json | Map trust reduction sequence: identify each trust, classify as essential/non-essential, define decommission prerequisites and validation steps. | TrustMap.json | Identity Modernization Guide §10 |
| T-7.8 | SecurityRemediationPlan.json | Remediation steps for every finding with assigned owner, SLA based on severity, and verification procedure. Critical/High findings must have remediation completed before Phase 3 gate. | SecurityFindings.json | PKI Modernization Guide §3, Identity Modernization Guide §5 |

| Milestone | ID | Gate Criteria |
| --- | --- | --- |
| All planning documents generated and committed to Gitea | M-011 | Eight planning documents committed under plans/ directory; all pass schema validation |

Week 8 — Planning Review and Approval

| Task ID | Task | Description | Hours |
| --- | --- | --- | --- |
| T-8.1 | Canon Steward reviews all planning documents | Full review of all eight planning documents for completeness, consistency, and governance compliance. Verify cross-references between plans are accurate. | 16h |
| T-8.2 | Pillar leads review their respective plans | Each pillar lead reviews their domain-specific plan: Identity Lead reviews Identity + Trust plans, Endpoint Lead reviews Computer + GPO plans, DNS Lead reviews DNS plan, PKI Lead reviews PKI plan. | 8h each |
| T-8.3 | Security Lead approves security remediation plan | Security Lead validates severity classifications, remediation steps, SLAs, and owner assignments. Confirms no critical findings are unaddressed. | 8h |
| T-8.4 | Steering committee approval of combined plan | Formal steering committee meeting to approve the combined assessment and planning output. Go/No-Go decision for Phase 2. | 4h |
| T-8.5 | Resolve conflicts, update plans, re-commit | Address all review comments, resolve cross-plan conflicts (e.g., PKI plan depends on Identity plan timing), update, and re-commit to Gitea. | 8h |

| Milestone | ID | Gate Criteria |
| --- | --- | --- |
| All planning documents APPROVED status | M-012 | Combined plan approved by Canon Steward and steering committee; all documents status = APPROVED |

Week 9 — Pre-Pilot Preparation

| Task ID | Task | Description | Hours | Reference |
| --- | --- | --- | --- | --- |
| T-9.1 | Identify pilot groups | Select 50–100 devices, 20–50 users per pillar, 2–3 servers, and 1–2 certificate use cases. Selection criteria: representative of environment, low-risk, willing participants. | 4h | ComputerModernizationPlan, IdentityModernizationPlan |
| T-9.2 | Create attribute-based dynamic groups for pilot sco | pe Build Entra ID dynamic groups using extension attributes to target pilot devices and users. Validate group membership accuracy. |  | 4h AD Computer Object Conversion Guide §3 |
| T-9.3 | Begin critical/high security finding remediation | Execute remediation steps for Critical and High severity findings identified in Week 6. Verify remediation with re-scan. All Critical findings must be resolved before Phase 3. | 20h | SecurityRemediationPlan.json |
| T-9.4 | Configure Intune for pilot policies | Create Intune configuration profiles and compliance policies from GPOMigrationPlan.json. Assign to pilot dynamic groups but set to Not Applicable until Phase 3. | 12h | AD Computer Object Conversion Guide §4 |
| T-9.5 | Configure Conditional Access in report-only mode | Deploy 15+ Conditional Access policies per Identity Modernization Guide in report-only mode targeting pilot users. Monitor sign-in logs for impact analysis. | 8h | Identity Modernization Guide §8 |
| T-9.6 | Provision Cloud PKI | Deploy Cloud PKI Root CA or configure BYOCA per PKI Modernization Plan. Create initial SCEP profile for pilot certificate template. | 8h | PKI Modernization Guide §5 |
| T-9.7 | Deploy Azure DNS Private Resolver | Deploy Private Resolver in hub VNet per DNS Modernization Plan. Configure forwarding rulesets for AD DNS zones. Do not enable conditional forwarding changes yet. | 6h | DNS Modernization Guide §6 |

| Milestone | ID | Gate Criteria |
| --- | --- | --- |
| Pre-pilot infrastructure ready | M-013 | Pilot scope defined; infrastructure provisioned; critical security findings remediated; Conditional Access running in report-only for 7+ days with no unexpected impact |

4.3 Assessment Phase Deliverables Summary

| Deliverable | Format | Gitea Path | Produced By | Consumed By |
| --- | --- | --- | --- | --- |
| ForestTopology.json | JSON | assessments/full/ | Invoke-FMPADAssessment A | ll planning documents |
| OUHierarchy.json | JSON | assessments/full/ | Export-FMPOUHierarchy A | ttribute Design, GPO Migration Plan |
| GPOInventory.json | JSON | assessments/full/ | Export-FMPGPOInventory G | PO Migration Plan |
| GPO XML Reports | XML | assessments/full/GPO/Reports/ | Get-GPOReport | GPO Migration Plan |
| DNSInventory.json | JSON | assessments/full/ | Export-FMPDNSAssessment D | NS Modernization Plan |
| PKIInventory.json | JSON | assessments/full/ | Export-FMPPKIInventory P | KI Modernization Plan |
| ESCVulnerabilities.csv | CSV | assessments/full/PKI/ | Test-FMPESCVulnerabilities S | ecurity Remediation Plan |
| ComputerInventory.json | JSON | assessments/full/ | Export-FMPComputerInventory C | omputer Modernization Plan |
| UserInventory.json | JSON | assessments/full/ | Export-FMPUserInventory I | dentity Modernization Plan |
| GroupInventory.json | JSON | assessments/full/ | Export-FMPGroupInventory I | dentity Modernization Plan |
| ServiceAccounts.csv | CSV | assessments/full/ | Export-FMPServiceAccountInventory I | dentity Modernization Plan |
| TrustMap.json | JSON | assessments/full/ | Export-FMPTrustMap T | rust Decommission Plan |
| OUDelegation.json | JSON | assessments/full/ | Export-FMPACLReport I | dentity Modernization Plan |
| SchemaExtensions.json | JSON | assessments/full/ | Export-FMPSchemaExtensions A | ttribute Design |
| AssessmentManifest.json | JSON | assessments/full/ | Invoke-FMPADAssessment G | overnance tracking |
| ComputerModernizationPlan.json | JSON | plans/ | Phase 1 Week 7 | Phase 3–5 |
| IdentityModernizationPlan.json | JSON | plans/ | Phase 1 Week 7 | Phase 3–5 |
| GPOMigrationPlan.json | JSON | plans/ | Phase 1 Week 7 | Phase 3–5 |
| DNSModernizationPlan.json | JSON | plans/ | Phase 1 Week 7 | Phase 3–5 |
| PKIModernizationPlan.json | JSON | plans/ | Phase 1 Week 7 | Phase 3–5 |
| AttributeDesign.json |  | JSON plans | / Phase 1 We | ek 7 Phase 2–6 |
| SecurityRemediationPlan.json | JSON | plans/ | Phase 1 Week 7 | Phase 2–5 |
| TrustDecommissionPlan.json | JSON | plans/ | Phase 1 Week 7 | Phase 5 |

5. Phase 2: Planning and Design (Weeks 10–13)

Objective: Transform assessment-driven planning documents into detailed technical designs, tested configurations, and approved blueprints ready for pilot deployment.

Reference Documents: AD Computer Object Conversion Guide, Identity Modernization Guide, DNS Modernization Guide, PKI Modernization Guide.

5.1 Phase 2 Milestones

| ID | Milestone | Week | Deliverable | Owner |
| --- | --- | --- | --- | --- |
| M-014 | extension attribute taxonomy finaliz | ed | W10 Extension attribute mapping, canonical value lists, gover | nance rules committed Identity Lead |
| M-015 | Dynamic group design complete | W10 | All dynamic group rules documented and tested in non-production | Endpoint Lead |
| M-016 | Intune policy design complete | W11 | All GPO-to-Intune policy mappings with Settings Catalog configurations | Endpoint Lead |
| M-017 | Conditional Access policy design | W11 | 15+ CA policies designed and running in report-only mode for 7+ days | Security Lead |
| M-018 | Entra Connect sync design | W12 | Filtering rules, attribute flow, sync method (PHS/PTA) documented | Identity Lead |
| M-019 | Azure DNS Private Resolver design | W12 | Hub-spoke topology, forwarding rulesets, split-brain patterns documented | DNS Lead |
| M-020 | Cloud PKI design complete | W13 | Root or BYOCA decision finalized, template migration matrix, SCEP profile designs | PKI Lead |
| M-021 | Phase 2 design review approved | W13 | All designs approved by Canon Steward and steering committee | Canon Steward |

5.2 Detailed Task Breakdown

M-014 — Extension Attribute Taxonomy (Week 10)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-14.1 | Define extension attribute dimensions from OU hierarchy analysis: Region, Site, Department, Role, En | vironment | 4h Attri | buteDesign.json AD Computer Object Conversion Guide §2 |
| T-14.2 | Map dimensions to Entra ID extension attributes (extensionAttribute1–15) | 3h | T-14.1, SchemaExtensions.json | AD Computer Object Conversion Guide §2 |
| T-14.3 | Create canonical value lists with validation rules (e.g., Region must be from approved list) | 4h | T-14.1 | AD Computer Object Conversion Guide §2 |
| T-14.4 | Define extension attribute governance rules: who can modify, approval workflow, drift detection |  | 2h T-14. | 3 CLI and Operations Guide §7 |
| T-14.5 | Commit AttributeTaxonomy.json to Gitea with APPROVED status |  | 1h T-14. | 4 — |

M-015 — Dynamic Group Design (Week 10)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-15.1 | Design dynamic group rules for each extension attribute dimension combination used in migrat | ion waves | 6h | M-014 AD Computer Object Conversion Guide §3 |
| T-15.2 | Create test dynamic groups in non-production Entra ID tenant and validate membership | 4h | T-15.1 | AD Computer Object Conversion Guide §3 |
| T-15.3 | Document group naming convention and lifecycle management procedures | 2h | T-15.1 | — |
| T-15.4 | Validate dynamic group processing time is within acceptable thresholds (<15 min refresh) | 2h | T-15.2 | — |

M-016 — Intune Policy Design (Week 11)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-16.1 | Map each GPO intent from GPOMigrationPlan.json to Settings Catalog, Endpoint Security, or ADMX template | 16h | GPOMigrationPlan.json | AD Computer Object Conversion Guide §4, Gap Analysis §4 |
| T-16.2 | Identify GPO intents with no Intune equivalent; document workarounds or acceptance decisions | 8h | T-16.1 | Gap Analysis §4 |
| T-16.3 | Build Intune configuration profiles in non-production and export as JSON | 12h | T-16.1 | AD Computer Object Conversion Guide §4 |
| T-16.4 | Create compliance policies aligned with configuration profiles | 4h | T-16.3 | AD Computer Object Conversion Guide §5 |
| T-16.5 | Commit IntunePolicy.json exports to Gitea under plans/intune/ | 2h | T-16.4 | — |

M-017 — Conditional Access Policy Design (Week 11)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-17.1 | Design 15+ Conditional Access policies covering: MFA, device compliance, app protection, location, authentication strength, sign-in risk | 12h | IdentityModernizationPlan.json | Identity Modernization Guide §8 |
| T-17.2 | Deploy all policies in report-only mode; monitor sign-in logs for 7+ days | 4h | T-17.1 | Identity Modernization Guide §8 |
| T-17.3 | Analyze report-only impact: identify users/apps that would be blocked or challenged | 4h | T-17.2 | Identity Modernization Guide §8 |
| T-17.4 | Document exception policies and break-glass accounts | 2h | T-17.3 | Identity Modernization Guide §7 |

M-018 — Entra Connect Sync Design (Week 12)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-18.1 | Define OU-based and attribute-based sync scope filtering rules from IdentityModernizationPlan.json | 4h | IdentityModernizationPlan.json | Identity Modernization Guide §3 |
| T-18.2 | Design attribute flow rules including extension attributes to Entra ID |  | 4h T-18.1 | , M-014 Identity Modernization Guide §3 |
| T-18.3 | Select sync method: Password Hash Sync (PHS) recommended, with Pass-Through Auth (PTA) as alternative | 2h | — | Identity Modernization Guide §3 |
| T-18.4 | Document staging mode deployment plan for safe initial sync | 2h | T-18.1–T-18.3 | Identity Modernization Guide §3 |

M-019 — Azure DNS Private Resolver Design (Week 12)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-19.1 | Design hub-spoke DNS topology: hub VNet with Private Resolver, spoke VNets linked to hub | 6h | DNSModernizationPlan.json | DNS Modernization Guide §6 |
| T-19.2 | Define forwarding rulesets: AD DNS zones → on-prem DCs, Azure Private Zones → resolver inbound | 4h | T-19.1 | DNS Modernization Guide §7 |
| T-19.3 | Document split-brain patterns for zones served by both on-prem and Azure DNS | 4h | T-19.2 | DNS Modernization Guide §8 |
| T-19.4 | Design monitoring and alerting for DNS resolution failures | 2h | T-19.1 | DNS Modernization Guide §10 |

M-020 — Cloud PKI Design (Week 13)

| Task | Description | Hours | Dependencies | Reference |
| --- | --- | --- | --- | --- |
| T-20.1 | Finalize Root CA decision: Cloud PKI Root vs. BYOCA (Bring Your Own CA). Document ADR. | 4h | PKIModernizationPlan.json | PKI Modernization Guide §5 |
| T-20.2 | Design SCEP profile configurations for each migrating certificate template | 8h | T-20.1 | PKI Modernization Guide §6 |
| T-20.3 | Design Entra CBA binding rules: certificate-to-user mapping, authentication strength integration | 4h | T-20.1 | PKI Modernization Guide §7 |
| T-20.4 | Document certificate lifecycle: issuance, renewal, revocation, and monitoring procedures | 4h | T-20.2 | PKI Modernization Guide §8 |
| T-20.5 | Commit all PKI design artifacts to Gitea | 1h | T-20.4 | — |

6. Phase 3: Pilot (Weeks 14–21)

Objective: Validate the complete modernization stack — Identity, Devices, DNS, PKI, and Server Management — against a representative pilot group before scaling to the full environment.

6.1 Pilot Scope Definition

| Pillar | Pilot Scope | Selection Criteria |
| --- | --- | --- |
| Devices | 50–100 devices across 2–3 sites | Mix of Windows 10/11, laptop/desktop, representative extension attribute values |
| Identity | 20–50 users across 3–4 departments | Mix of standard users, power users, and 2–3 pilot admins |
| Servers | 2–3 servers for Arc enrollment | Non-critical tier, representative OS versions |
| PKI | 1–2 certificate use cases | Wi-Fi authentication certificate and/or VPN certificate |
| DNS | Pilot sites only | Sites with both on-prem and Azure workloads |

6.2 Phase 3 Milestones

| ID | Milestone | Week | Deliverable | Owner |
| --- | --- | --- | --- | --- |
| M-022 | Entra Connect deployed | W14 | Sync operational with PHS; staging mode validated; pilot users synced | Identity Lead |
| M-023 | Pilot devices Entra-joined or hybrid-joined | W15 | 50+ devices registered with extension attributes populated in Entra ID | Endpoint Lead |
| M-024 | Intune policies assigned to pilot | W16 | GPO-equivalent policies deployed via attribute-based dynamic groups | Endpoint Lead |
| M-025 | Conditional Access enforced for pilot | W17 | MFA, device compliance, and authentication strength policies active | Security Lead |
| M-026 | PIM configured for privileged roles | W18 | All pilot admin accounts PIM-eligible; zero permanent Global Admins | Identity Lead |
| M-027 | DNS hybrid resolution validated | W19 | On-prem → Azure and Azure → on-prem resolution confirmed at pilot sites | DNS Lead |
| M-028 | Cloud PKI certificates issued to pilot | W20 | SCEP profiles deployed; Wi-Fi/VPN auth verified with Cloud PKI certificates | PKI Lead |
| M-029 | Entra CBA validated for pilot users | W20 | Certificate-based SSO working with staged rollout for pilot users | PKI Lead |
| M-030 | Arc pilot servers enrolled and compliant | W21 | Guest Configuration policies applied; Azure Policy compliance confirmed | Infra Lead |
| M-031 | Pilot success criteria met | W21 | >95% policy compliance, zero auth failures, all tests passed | PM |

6.3 Pilot Success Criteria

| Criteria | Target | Measurement | Pass/Fail Threshold |
| --- | --- | --- | --- |
| Device enrollment success rate | >98% | Intune enrollment report | <95% = FAIL |
| Policy compliance rate | >95% | Intune compliance dashboard | <90% = FAIL |
| Authentication success rate | >99% | Entra sign-in logs | <97% = FAIL |
| Certificate issuance success | >95% | Intune certificate report | <90% = FAIL |
| DNS resolution success | >99.5% | Monitoring queries (synthetic and organic) | <99% = FAIL |
| User satisfaction (survey) | >80% positive | Pilot user survey | <70% = FAIL |
| Help desk ticket volume | <5% of pilot users | Ticket tracking system | >10% = FAIL |
| Mean time to compliance | <4 hours | Intune reporting | >24 hours = FAIL |

6.4 Rollback Procedures

| Pillar | Rollback Trigger | Rollback Procedure | Recovery Time |
| --- | --- | --- | --- |
| Identity (Entra Connect) | Sync corruption, duplicate objects, authentication failures | Disable sync scheduler, restore from staging mode server, re-enable AD-only auth in Gitea. Per Identity Modernization Guide §12. | <2 hours |
| Devices (Intune) | Policy conflict causes device lockout, compliance failures >10% | Unassign Intune profiles from pilot group, re-enable GPO links for pilot OUs. Per AD Computer Object Conversion Guide §7. | <4 hours |
| Conditional Access | Legitimate users blocked, break-glass needed repeatedly | Switch all policies back to report-only mode. Per Identity Modernization Guide §8. | <30 min |
| DNS | Resolution failures >1%, SRV record lookup failures | Revert conditional forwarder changes on-prem, disable Private Resolver forwarding rules. Per DNS Modernization Guide §11. | <1 hour |
| PKI (Cloud PKI) | Certificate issuance failures, auth failures with new certs | Re-enable ADCS auto-enrollment for pilot templates, remove SCEP profiles from pilot group. Per PKI Modernization Guide §10. | <4 hours |
| Servers (Azure Arc) | Arc agent causes performance degradation, policy conflicts | Uninstall Connected Machine agent, remove Arc resource from Azure. Per AD Computer Object Conversion Guide §8. | <1 hour |

7. Phase 4: Scale (Weeks 22–33)

Objective: Extend the validated modernization stack from pilot to the full production environment through a wave-based rollout organized by extension attribute dimensions.

7.1 Scaling Strategy

- Wave-based rollout organized by extension attribute dimensions: Region → Site → Department

- 4 waves of approximately 25% scope each, 3 weeks per wave

- Each wave follows the same validation checklist proven during pilot (Section 6.3)

- Drift detection active from Wave 1 — Invoke-FMPDriftDetection runs daily against migrated scope

- Wave 1 starts with the lowest-risk region; each subsequent wave expands to higher-complexity environments

7.2 Phase 4 Milestones

| ID | Milestone | Week | Scope | Owner |
| --- | --- | --- | --- | --- |
| M-032 | Wave 1 complete (Region 1) | W24 | ~25% of devices, users, and servers migrated | All Leads |
| M-033 | Wave 2 complete (Region 2) | W27 | ~50% cumulative | All Leads |
| M-034 | Wave 3 complete (Region 3) | W30 | ~75% cumulative | All Leads |
| M-035 | Wave 4 complete (All remaining) | W33 | 100% migrated | All Leads |
| M-036 | Legacy GPO disabled for migrated OUs | W33 | No GPO links remain on migrated OUs | Endpoint Lead |
| M-037 | All dynamic groups populated and validated | W33 | extension attribute coverage = 100% | Identity Lead |

7.3 Scaling Risk Management

| Risk | Impact | Mitigation | Contingency |
| --- | --- | --- | --- |
| Wave N exposes applications not found in pilot | Authentication failures, business disruption | Pre-wave application discovery scan; Conditional Access report-only for 48h before enforcement | Exclude application from Conditional Access; add to exception policy |
| GPO-to-Intune parity gaps discovered at scale | Configuration drift, compliance failures | Maintain GPO links in parallel during wave; only unlink after 7-day compliance validation | Re-enable GPO for affected OUs; file Intune feature request |
| Dynamic group processing delays at high user counts | Policy assignment delays, enrollment gaps | Stagger extension attribute writes; monitor dynamic group processing time | Convert to assigned groups for critical policies |
| Cloud PKI capacity limits during mass certificate issuance | Certificate issuance failures, VPN/Wi-Fi disruption | Stagger SCEP profile deployment across wave days; monitor issuance rate | Throttle enrollment; extend wave duration |
| DNS split-brain inconsistencies at multi-site scale | Name resolution failures for hybrid resources | Deploy monitoring probes at each site; test forward and reverse resolution | Revert specific forwarding rules; retain AD DNS for affected zones |
| User resistance increases with scale | Help desk volume spikes, negative sentiment | Pre-wave communications, training materials, department champions | Pause wave; increase training; add support resources |
| Key personnel unavailable during critical wave | Wave delayed, knowledge gaps | Cross-train 2 people per pillar; document all procedures in Gitea | Shift wave schedule; activate backup personnel |

8. Phase 5: Cutover (Weeks 34–41)

Objective: Decommission legacy infrastructure components that have been fully replaced by modernized equivalents. Each cutover action is irreversible and requires formal gate approval.

8.1 Phase 5 Milestones

| ID | Milestone | Week | Action | Owner |
| --- | --- | --- | --- | --- |
| M-038 | ADFS decommission (if applicable) | W35 | Convert federated domains to managed; disable ADFS farm | Identity Lead |
| M-039 | ADCS issuance stopped | W36 | Auto-enrollment disabled; certificate templates locked; CA set to maintenance-only for CRL | PKI Lead |
| M-040 | AD DNS conditional forwarders migrated | W37 | All conditional forwarding via Azure DNS Private Resolver; on-prem forwarders removed | DNS Lead |
| M-041 | Legacy GPO links removed | W38 | All GPOs unlinked from all OUs; GPO objects retained for audit but non-functional | Endpoint Lead |
| M-042 | Trust relationships reduced | W39 | Non-essential trusts removed per TrustDecommissionPlan.json | Identity Lead |
| M-043 | Legacy server decommission begins | W40 | NDES servers, secondary Issuing CAs, and secondary DNS servers decommissioned | Infra Lead |
| M-044 | Cutover validation complete | W41 | All modernization plans show 100% completion in Gitea; no legacy dependencies | Canon Steward |

8.2 Cutover Validation Checklist

| # | Validation Item | Method | Owner |
| --- | --- | --- | --- |
| 1 | All user accounts synced to Entra ID with correct extension attributes | Entra ID export vs. IdentityModernizati | onPlan.json Identity Lead |
| 2 | Zero permanent Global Admin assignments | PIM role assignment report | Identity Lead |
| 3 | All Conditional Access policies in enforced mode | CA policy status report | Security Lead |
| 4 | All devices enrolled in Intune with compliant status | Intune compliance dashboard | Endpoint Lead |
| 5 | All GPO links removed from all OUs | Get-GPLink across all OUs returns empty | Endpoint Lead |
| 6 | No device receiving GPO-delivered settings | gpresult /r on sample devices returns no applied GPOs | Endpoint Lead |
| 7 | All SCEP/PKCS certificates issued by Cloud PKI | Intune certificate report — 0 ADCS issuances in last 30 days | PKI Lead |
| 8 | ADCS auto-enrollment disabled on all templates | certutil -template audit | PKI Lead |
| 9 | All ESC vulnerabilities remediated or accepted with documentation | SecurityRemediationPlan.json — all items closed | Security Lead |
| 10 | CRL distribution points still accessible for existing certificates | certutil -verify against issued certificates | PKI Lead |
| 11 | DNS resolution working for all zones via Private Resolver | nslookup/dig tests from all sites | DNS Lead |
| 12 | No conditional forwarders remaining on on-prem DNS servers | DNS server configuration audit | DNS Lead |
| 13 | SRV records for AD services still resolvable (AD remains for auth) | nslookup -type=SRV _ldap._tcp.domain | DNS Lead |
| 14 | Azure Arc enrolled for all in-scope servers | Arc resource inventory vs. ComputerModernizationPlan.json | Infra Lead |
| 15 | Guest Configuration policies compliant on all Arc servers | Azure Policy compliance dashboard | Infra Lead |
| 16 | All trusts marked for removal have been removed | TrustDecommissionPlan.json — all non-essential trusts removed | Identity Lead |
| 17 | ADFS farm disabled (if applicable) | ADFS service stopped; no federated domains remain | Identity Lead |
| 18 | Service accounts migrated to gMSA or Workload Identity | ServiceAccounts.csv — all migrated or documented exception | Identity Lead |
| 19 | Drift detection running and producing weekly reports | Gitea commit history shows weekly assessment diffs | Canon Steward |
| 20 | All planning documents updated to CURRENT status | Gitea file status audit | Canon Steward |
| 21 | Decommissioned servers removed from AD computer objects | ComputerInventory.json re-scan shows removal | Infra Lead |
| 22 | Monitoring and alerting configured for all modernized services | Alert test verification for each pillar | All Leads |
| 23 | Break-glass accounts tested and documented | Break-glass login test successful | Security Lead |
| 24 | Operational runbooks drafted for steady-state operations | Runbooks committed to Gitea | All Leads |
| 25 | Phase 5 completion report committed to Gitea | Gate review report at reports/phase-gates/phase-5-completion.md | PM |

8.3 Rollback Plan for Cutover Actions

| Cutover Action | Rollback Possibility | Procedure | Time Window |
| --- | --- | --- | --- |
| ADFS decommission | Reversible within 72h | Re-enable ADFS service; convert managed domains back to federated via PowerShell | 72 hours |
| ADCS issuance stopped | Reversible | Re-enable auto-enrollment on templates; restart CA issuance. CRL must remain valid. | Indefinite (while CA online) |
| DNS forwarder migration | Reversible | Re-create conditional forwarders on on-prem DNS servers; disable Private Resolver rules | Indefinite |
| GPO link removal | Reversible | Re-link GPOs to OUs. GPO objects retained specifically for this purpose. | Until GPO objects deleted (Phase 6+) |
| Trust removal | Requires recreation | Recreate trust with same partner domain. Requires admin access on both sides. | 4–8 hours |
| Server decommission | Requires rebuild | Re-provision from backup or rebuild from documented procedure. This is the point of no easy return. | 24–48 hours |

9. Phase 6: Steady State (Week 42+)

Objective: Operate the modernized environment under continuous governance with automated drift detection, scheduled re-assessment, and periodic access reviews — all tracked through the Federal Modernization Program Gitea pipeline.

9.1 Continuous Governance Operations

| Operation | Cadence | Tool / Process | Output |
| --- | --- | --- | --- |
| Scheduled re-assessment | Weekly | Invoke-FMPADAssessment runs as scheduled task; diffs committed to Gitea a | ssessments/weekly/{YYYY-WNN}/delta.json |
| Drift detection | Daily | Invoke-FMPDriftDetection compares current state against canonical plans G | itea issues created with assigned owner and SLA per severity |
| Compliance monitoring | Continuous | Intune compliance dashboard, Azure Policy compliance, Entra sign-in health | Monthly compliance report committed to Gitea |
| Certificate lifecycle | Daily monitoring | Cloud PKI renewal monitoring; Entra CBA binding validation | Certificate expiration alerts 30/14/7 days before expiry |
| DNS health | Continuous | SRV record validation probes; Private Resolver health checks; query analytics | DNS health dashboard; alert on resolution failure rate >0.1% |
| Access reviews | Quarterly | PIM role assignment reviews; group attestation; app consent reviews in Entra ID | Access review results committed to Gitea |

9.2 Steady State Milestones

| ID | Milestone | Cadence | Owner |
| --- | --- | --- | --- |
| M-045 | Weekly drift assessment | Weekly (automated) | Automation / Canon Steward review |
| M-046 | Monthly compliance report | Monthly | Security Lead |
| M-047 | Quarterly access review | Quarterly | Identity Lead |
| M-048 | Annual architecture review | Annual | Canon Steward |

9.3 SLA Framework for Drift Remediation

| Finding Severity | Detection SLA | Remediation SLA | Escalation |
| --- | --- | --- | --- |
| Critical | < 1 hour | < 4 hours | Canon Steward + Security Lead notified immediately |
| High | < 4 hours | < 24 hours | Pillar Lead notified within 4 hours |
| Medium | < 24 hours | < 7 days | Pillar Lead notified within 24 hours |
| Low | < 7 days | < 30 days | Tracked in Gitea issue; reviewed at weekly standup |

10. Risk Register

| Risk ID | Risk Description | Prob. | Impact | Mitigation Strategy | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | Assessment reveals undocumented AD trusts blocking migration | Medium | High | Read-only assessment (Phase 1 Week 4) identifies all trusts before any migration. TrustMap.json drives decommission plan. | Identity Lead | OPEN |
| R-002 | ESC critical findings require emergency PKI remediation before Phase 3 | High | Critical | Security assessment (Week 6) identifies all ESC1–ESC8 vulnerabilities. Critical findings remediated in Week 9 before pilot. | PKI Lead | OPEN |
| R-003 | Legacy applications dependent on NTLM authentication discovered | High | High | Application inventory during assessment; NTLM audit logs enabled in Phase 2; application exception policies in Conditional Access. | Security Lead | OPEN |
| R-004 | Entra Connect sync failures during Phase 3 | Medium | High | Deploy in staging mode first; validate sync before enabling scheduler; monitor sync errors via Entra Connect Health. | Identity Lead | OPEN |
| R-005 | Cloud PKI licensing delay | Medium | Medium | Procure Intune Suite licenses in Phase 2; validate licensing before Phase 3 pilot. | PM | OPEN |
| R-006 | DNS resolution failure during hybrid coexistence | Medium | High | Test bidirectional resolution at pilot sites; deploy synthetic monitoring probes; maintain AD DNS as fallback. | DNS Lead | OPEN |
| R-007 | User resistance to passwordless authentication | Medium | Medium | Pilot with willing early adopters; provide training materials; department champions; phased enforcement. | Identity Lead | OPEN |
| R-008 | Gitea server hardware failure (single point of failure) | Low | High | Daily backup to Azure Blob or network share; GitHub mirror as secondary source; Active-Passive replication (follow-on document P2). | Infra Lead | OPEN |
| R-009 | Azure Arc agent deployment blocked by endpoint security | Medium | Medium | Pre-approve Connected Machine agent in endpoint protection policies; test on pilot servers first. | Infra Lead | OPEN |
| R-010 | GPO-to-Intune settings not supported in Settings Catalog | High | High | Gap Analysis document identifies unsupported settings; use custom OMA-URI or ADMX ingestion; document accepted gaps. | Endpoint Lead | OPEN |
| R-011 | Certificate strong mapping failures on legacy DCs | Medium | Critical | Audit SID-based vs. explicit mapping on all templates; update mappings per PKI Modernization Guide §7 before enabling CBA. | PKI Lead | OPEN |
| R-012 | Budget constraints delaying license procurement | Medium | Medium | Submit license business case in Phase 1; obtain budget approval before Phase 2 design begins. | PM | OPEN |
| R-013 | Key personnel departure during critical phase | Low | High | Cross-train 2 people per pillar; all procedures documented in Gitea; no single-person dependencies. | PM | OPEN |
| R-014 | Regulatory audit occurs during migration window | Low | Medium | Maintain compliance documentation in Gitea with full audit trail; freeze changes during audit if required. | Security Lead | OPEN |
| R-015 | Split-brain DNS causes production outage | Low | Critical | Design split-brain patterns carefully (DNS Modernization Guide §8); test at each wave; maintain AD DNS as authoritative fallback. | DNS Lead | OPEN |
| R-016 | Dynamic group membership rules produce incorrect scope | Medium | Medium | Validate all dynamic group rules in non-production (Phase 2 M-015); monitor membership changes during scale. | Endpoint Lead | OPEN |
| R-017 | Entra CBA certificate-to-user binding breaks during migration | Medium | High | Staged CBA rollout; monitor sign-in logs for binding failures; maintain password fallback during transition. | PKI Lead | OPEN |
| R-018 | Gitea mirror sync from GitHub fails silently | Low | Low | Post-receive hook validates sync timestamp; alert if stale >24h. | Infra Lead | OPEN |
| R-019 | Schema extension conflicts block extension attribute assignment |  |  | Low Medium SchemaExtensions.json assessment identifies in-use extension attributes; select unused attributes for exten | sion attributes. | Identity Lead OPEN |
| R-020 | ADFS decommission breaks legacy application authentication | Medium | High | Inventory all ADFS relying party trusts before decommission; migrate each to Entra ID Enterprise App; 72h rollback window. | Identity Lead | OPEN |
| R-021 | Assessment workstation compromised with sensitive AD data | Low | Medium | Use PAW with restricted network access; encrypt assessment output; destroy workstation after Phase 1. | Security Lead | OPEN |
| R-022 | Pilot user survey returns negative results | Low | Low | Conduct mid-pilot check-in at Week 18; address concerns before end-of-pilot survey. | PM | OPEN |

11. Dependency Map

[Diagram: The Federal Modernization Program Milestone Dependency Network] ¦ Directed acyclic graph showing milestone-to-milestone dependencies. Critical path highlighted in blue: M-001 → M-002 → M-005 → M-008 → M-009 → M-011 → M-012 → M-022 → M-023 → M-024 → M-031 → M-032 → M-035 → M-044. ¦ ¦ Diagram ID: FMP-MPP-D002 ¦ Dimensions: 780 × 450 px ¦

11.1 Milestone Dependency Table

| Milestone | Depends On | Blocks |
| --- | --- | --- |
| M-001 (Server provisioned) | — | M-002, M-007 |
| M-002 (IIS + Gitea) | M-001 | M-003, M-004, M-005 |
| M-003 (AD LDAP auth) | M-002 | M-005 |
| M-004 (Entra ID OAuth2) | M-002 | M-006 |
| M-005 (Repo mirrored) | M-002, M-003 | M-006, M-008 |
| M-006 (Governance hooks) | M-005, M-004 | M-008 |
| M-007 (Azure Arc) | M-001 | M-030 |
| M-008 (Read-only assessment) | M-006 | M-009 |
| M-009 (Full assessment) | M-008 | M-010, M-011 |
| M-010 (Security assessment) | M-009 | M-011 |
| M-011 (Planning docs generated) | M-009, M-010 | M-012 |
| M-012 (Planning docs approved) | M-011 | M-013, M-014 – M-021 |
| M-013 (Pre-pilot ready) | M-012 | M-022 |
| M-014 (extension attribute taxonomy | ) | M-012 M-015, M-018 |
| M-015 (Dynamic groups) | M-014 | M-016, M-023 |
| M-016 (Intune policy design) | M-015 | M-024 |
| M-017 (Conditional Access) | M-012 | M-025 |
| M-018 (Entra Connect design) | M-014 | M-022 |
| M-019 (DNS Private Resolver) | M-012 | M-027 |
| M-020 (Cloud PKI design) | M-012, M-010 | M-028 |
| M-021 (Phase 2 approved) | M-014 – M-020 | M-022 |
| M-022 (Entra Connect deployed) | M-018, M-021 | M-023 |
| M-023 (Pilot devices joined) | M-015, M-022 | M-024 |
| M-024 (Intune policies assigned) | M-016, M-023 | M-025, M-031 |
| M-025 (CA enforced) | M-017, M-024 | M-031 |
| M-026 (PIM configured) | M-022 | M-031 |
| M-027 (DNS validated) | M-019 | M-031 |
| M-028 (Cloud PKI certs issued) | M-020 | M-029, M-031 |
| M-029 (Entra CBA validated) | M-028 | M-031 |
| M-030 (Arc servers compliant) | M-007 | M-031 |
| M-031 (Pilot success) | M-024 – M-030 | M-032 |
| M-032 (Wave 1) | M-031 | M-033 |
| M-033 (Wave 2) | M-032 | M-034 |
| M-034 (Wave 3) | M-033 | M-035 |
| M-035 (Wave 4) | M-034 | M-036, M-037, M-038 |
| M-036 (GPO disabled) | M-035 | M-041 |
| M-037 (Dynamic groups 100%) | M-035 | M-044 |
| M-038 (ADFS decommission) | M-035 | M-044 |
| M-039 (ADCS stopped) | M-035 | M-043 |
| M-040 (DNS forwarders migrated) | M-035 | M-043 |
| M-041 (GPO links removed) | M-036 | M-043 |
| M-042 (Trusts reduced) | M-035 | M-044 |
| M-043 (Server decommission) | M-039, M-040, M-041 | M-044 |
| M-044 (Cutover validated) | M-037 – M-043 | M-045 |
| M-045 – M-048 | M-044 | — |

11.2 Critical Path

The critical path through the project is:

M-001 → M-002 → M-005 → M-006 → M-008 → M-009 → M-011 → M-012 → M-014 → M-015 → M-016 → M-023 → M-024 → M-031 → M-032 → M-033 → M-034 → M-035 → M-044

Parallelizable Milestones • Phase 0: M-003 (AD LDAP) and M-004 (Entra OAuth2) can run in parallel after M-002. M-007 (Arc) can run in parallel with M-002–M-006. • Phase 2: M-017 (Conditional Access) and M-019 (DNS Private Resolver) can run in parallel with the M-014 → M-015 → M-016 identity/device track. M-020 (Cloud PKI) runs in parallel but depends on M-010 (security assessment) for ESC remediation status. • Phase 3: M-026 (PIM), M-027 (DNS), M-028 (Cloud PKI), and M-030 (Arc) can run in parallel after their respective Phase 2 designs are complete. • Phase 5: M-038 (ADFS), M-039 (ADCS), M-040 (DNS), M-041 (GPO), and M-042 (Trusts) can all execute in parallel after Wave 4 completion. • Key dependency: PKI always depends on Identity — certificate templates require user/device objects to be synced and mapped before CBA can be validated.

[Diagram: Phase Transition Flow] Flowchart showing the seven phases as sequential blocks with gate review diamonds between each phase. Each gate diamond shows the Go/No-Go decision with criteria summary. Parallel pillar workstreams shown within each phase block. Diagram ID: FMP-MPP-D003 ¦ Dimensions: 780 × 280 px ¦

12. Budget and Resource Estimate

12.1 License Requirements

| License | Required For | Phase Needed | Quantity Basis |
| --- | --- | --- | --- |
| Microsoft Entra ID P2 | PIM, Identity Protection, Access Reviews, Conditional Access (risk-based) | Phase 2 | Per user (all synced users) |
| Microsoft Intune Plan 1 | Device management, compliance policies, configuration profiles | Phase 2 | Per device (all enrolled devices) |
| Microsoft Intune Suite (includes Cloud PKI) | Cloud PKI certificate issuance, SCEP/PKCS profiles | Phase 3 | Per device (Cloud PKI scope) |
| Microsoft Defender for Identity | AD security posture assessment, threat detection, lateral movement path analysis | Phase 1 | Per user (all AD users) |
| Azure Arc (Server) | Server management, Guest Configuration, Azure Policy for on-prem servers | Phase 3 | Per server |
| Azure DNS Private Resolver | Hybrid DNS resolution between on-prem and Azure | Phase 3 | Per instance (min. 2 endpoints) |

12.2 Infrastructure Requirements

| Resource | Specification | Phase | Cost Estimate |
| --- | --- | --- | --- |
| The Federal Modernization Program Git Se | rver (Windows Server 2025) 4 vCPU, 8 GB RAM, 100 G | B SSD | Phase 0 Hardware/VM cost (existing infra or ~$200/mo VM) |
| Assessment Workstation (PAW) | 2 vCPU, 4 GB RAM, 50 GB SSD | Phase 1 | Hardware/VM cost (temporary — decommission after Phase 1) |
| Entra Connect Server | 4 vCPU, 8 GB RAM, per Microsoft sizing guidance | Phase 3 | Hardware/VM cost |
| Azure DNS Private Resolver | 2 endpoints minimum (inbound + outbound) | Phase 3 | Azure consumption (~$400/mo per endpoint) |
| Log Analytics Workspace | Per-GB ingestion for Entra, Intune, Arc telemetry | Phase 3 | Azure consumption (varies by volume) |
| Azure Blob Storage (Gitea backups) | LRS, Cool tier, ~50 GB projected | Phase 0 | Azure consumption (~$1/mo) |

12.3 People Requirements

| Role | FTE Estimate | Duration | Phase(s) |
| --- | --- | --- | --- |
| Canon Steward | 0.5 FTE | 52 weeks + ongoing | All |
| Infrastructure Lead | 1.0 FTE | Weeks 1–41 | Phase 0–5 |
| Identity Lead | 1.0 FTE | Weeks 4–41 | Phase 1–5 |
| Endpoint Lead | 1.0 FTE | Weeks 10–41 | Phase 2–5 |
| DNS Lead | 0.5 FTE | Weeks 4–41 | Phase 1–5 |
| PKI Lead | 0.5 FTE | Weeks 4–41 | Phase 1–5 |
| Security Lead | 0.5 FTE | Weeks 4–52+ | Phase 1–6 |
| Project Manager | 0.5 FTE | 52 weeks | All |
| Total | 5.5 FTE |  |  |

13. Copilot Code Integration — Proposed Next Steps

This section defines how Copilot Code should proceed to operationalize this Master Project Plan. Each sprint produces committed, tested PowerShell modules and configuration artifacts that directly enable phase execution.

13.1 Immediate Actions (Sprint 1 — Next 2 Weeks)

| # | Deliverable | Description | Source Document |
| --- | --- | --- | --- |
| 1 | FMPADAssessment.psm1 P | owerShell module implementing all assessment functions: Export-FMPForestTopology, Export-FMPOUHierarchy, Export-FMPGPOInventory, Export-FMPComputerInventory, Export-FMPUserInventory, Export-FMPGroupInventory, Export-FMPTrustMap, Export-FMPACLReport, Export-FMPSchemaExtensions AD Interac | tion Guide |
| 2 | FMPReadOnlyAssessment.psm1 M | odule implementing Test-FMPReadAccess and Invoke-FMPReadOnlyAssessment master orchestrator for non-delegated assessment Rea | d-Only AD Assessment Guide |
| 3 | FMPPKIAssessment.psm1 M | odule implementing Export-FMPPKIInventory and Test-FMPESCVulnerabilities (ESC1–ESC8 detection) PKI | Modernization Guide |
| 4 | FMPDNSAssessment.psm1 M | odule implementing Export-FMPDNSAssessment (zone enumeration, record inventory, aging analysis) DN | S Modernization Guide |
| 5 | Invoke-FMPFullAssessment M | aster orchestrator calling all assessment modules, generating AssessmentManifest.json, and staging output for Gitea commit A | ll assessment guides |
| 6 | app.ini (Gitea configuration) | Complete Gitea configuration file with LDAP, OAuth2, repository settings, and governance parameters | Platform Server Build Guide |
| 7 | web.config (IIS reverse proxy) | IIS URL Rewrite / ARR configuration for HTTPS reverse proxy to Gitea | Platform Server Build Guide |
| 8 | Git hooks (pre-receive, post-receive, update) | All three governance hooks implementing FOUO rejection, branch protection, and notification | Platform Server Build Guide §12 |

13.2 Short-Term Actions (Sprint 2–3 — Weeks 3–6)

| # | Deliverable | Description | Source Document |
| --- | --- | --- | --- |
| 1 | Import-GPOAnalyticsReport adapter | Imports GPO Analytics results from Intune portal and correlates with GPOInventory.json | Gap Analysis §9 |
| 2 | Import-DefenderForIdentityFindings adapter | Imports Defender for Identity Secure Score findings and normalizes to the Federal Modernization | Program finding format Gap Analysis §7 |
| 3 | New-FMPComputerModernizationPlan C | onsumes ComputerInventory.json; classifies each object into migration path A | D Computer Object Conversion Guide |
| 4 | New-FMPIdentityModernizationPlan C | onsumes UserInventory.json + GroupInventory.json; classifies identities into migration path I | dentity Modernization Guide |
| 5 | New-FMPGPOMigrationPlan C | onsumes GPOInventory.json; decomposes GPOs into intents with per-intent Intune mapping A | D Computer Object Conversion Guide §4 |
| 6 | New-FMPDNSModernizationPlan C | onsumes DNSInventory.json; classifies zones and records into migration path D | NS Modernization Guide |
| 7 | New-FMPPKIModernizationPlan C | onsumes PKIInventory.json; classifies templates into MIGRATE/BRIDGE/RETAIN/RETIRE P | KI Modernization Guide §4 |
| 8 | New-FMPAttributeDesign | Consumes OUHierarchy.json + SchemaExtensions.json; generates extensio | n attribute dimension design AD Computer Object Conversion Guide §2 |
| 9 | Invoke-FMPDriftDetection S | cheduled task scripts for daily drift detection against canonical plans C | LI and Operations Guide |

13.3 Medium-Term Actions (Sprint 4–6 — Weeks 7–12)

| # | Deliverable | Description | Source Document |
| --- | --- | --- | --- |
| 1 | Intune policy templates | Settings Catalog JSON exports generated from GPOMigrationPlan output | AD Computer Object Conversion Guide |
| 2 | Conditional Access policy templates | 15+ CA policy JSON templates for import via Graph API | Identity Modernization Guide §8 |
| 3 | Azure DNS Private Resolver deployment scripts | ARM/Bicep templates for hub VNet, resolver, endpoints, and forwarding rulesets | DNS Modernization Guide §6 |
| 4 | Cloud PKI provisioning scripts | Graph API scripts for Cloud PKI root/issuing CA creation and SCEP profile deployment | PKI Modernization Guide §5 |
| 5 | the Federal Modernization Program Governance Das | hboard HTML/Quarto rendering pipeline producing drift, compliance, and SLA | dashboards from Gitea data All guides |

13.4 Module Architecture

D:\FMP\Modules\ ├── FMPADAssessment\ │ ├── FMPADAssessment.psd1 │ └── FMPADAssessment.psm1 ├── FMPReadOnlyAssessment\ │ ├── FMPReadOnlyAssessment.psd1 │ └── FMPReadOnlyAssessment.psm1 ├── FMPPKIAssessment\ │ ├── FMPPKIAssessment.psd1 │ └── FMPPKIAssessment.psm1 ├── FMPDNSAssessment\ │ ├── FMPDNSAssessment.psd1 │ └── FMPDNSAssessment.psm1 ├── FMPIdentityAssessment\ │ ├── FMPIdentityAssessment.psd1 │ └── FMPIdentityAssessment.psm1 ├── FMPImportAdapters\ │ ├── FMPImportAdapters.psd1 │ └── FMPImportAdapters.psm1 ├── FMPPlanGenerators\ │ ├── FMPPlanGenerators.psd1 │ └── FMPPlanGenerators.psm1 └── FMPDriftDetection\ ├── FMPDriftDetection.psd1 └── FMPDriftDetection.psm1

14. Follow-On Document Roadmap

The following documents are identified as necessary to complete the Federal Modernization Program corpus beyond the 12 existing companion documents. Priority reflects execution dependency.

| Priority | Document Title | Purpose | Dependency | Target Phase |
| --- | --- | --- | --- | --- |
| P1 | the Federal Modernization Program Conditi | onal Access Policy Library 15+ policy templates with JSON export, grant/session controls, named locations, and authentic | ation strength definitions Identity | Modernization Guide Phase 2 |
| P1 | the Federal Modernization Program Intune | Policy Templates Settings Catalog configurations mapped from GPO analysis, with per-platform profiles and comp | liance policy pairings AD Comput | er Object Conversion Guide Phase 2 |
| P1 | the Federal Modernization Program PowerSh | ell Module Reference Combined API reference for all the Federal Modernization Program modules — parameter docume | ntation, examples, pipeline integratio | n All assessment guides Phase 1 |
| P2 | the Federal Modernization Program Active- | Passive Replication Guide Git server replication, backup strategy, and disaster recovery for Gitea on Windows Server | Platform | Server Build Guide Phase 0 |
| P2 | the Federal Modernization Program Quarto | Pipeline Integration Guide Documentation build pipeline from Gitea webhooks to rendered HTML/PDF output | Platform | Server Build Guide Phase 0 |
| P2 | the Federal Modernization Program Azure A | rc Policy Library Guest Configuration policies for Windows Server 2025 with compliance baselines | AD Comput | er Object Conversion Guide Phase 3 |
| P2 | the Federal Modernization Program Governa | nce Dashboard Design HTML/Quarto dashboard specification for drift detection, compliance, and SLA visualization | All guide | s Phase 6 |
| P3 | the Federal Modernization Program Disaste | r Recovery Playbook Full DR procedures for all modernized services including Gitea, Entra Connect, Cloud PKI, DNS | All guide | s Phase 5 |
| P3 | the Federal Modernization Program Trainin | g Guide — End Users Passwordless enrollment, self-service password reset, new authentication workflows, device en | rollment Identity | Modernization Guide Phase 4 |
| P3 | the Federal Modernization Program Runbook | — Operations Day-to-day operational procedures for steady-state governance including incident response | All guide | s Phase 6 |

15. Companion Document Cross-Reference Matrix

This matrix shows which existing the Federal Modernization Program companion documents are referenced in each project phase. ✓ indicates the document contains procedures or specifications executed during that phase.

| Document | Ph 0 | Ph 1 | Ph 2 | Ph 3 | Ph 4 | Ph 5 | Ph 6 | Primary Milestones |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD Computer Object Conversion Guide | ✓ | ✓ | ✓ | ✓ | ✓ |  |  | M-007, M-011, M-014–M-016, M-023–M-024 |
| Git on Windows Server 2025 with IIS Guide | ✓ |  |  |  |  |  |  | M-002 |
| The Federal Modernization Program Git Server Imple | mentation G | uide | **✓* | * |  |  |  | M-002, M-003 |
| The Federal Modernization Program Git Infrastructu | re ADR |  | **✓* | * |  |  |  | M-002 |
| Platform Server Build Guide | ✓ |  |  |  |  |  |  | M-001–M-006 |
| The Federal Modernization Program CLI and Operatio | ns Guide |  | **✓* | * **✓* | * |  |  | ✓ M-005–M-006, M-008–M-009, M-045 |
| The Federal Modernization Program AD Interaction G | uide |  |  | **✓* | * |  |  | ✓ M-008–M-011, M-045 |
| Identity Modernization Guide |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | M-010–M-012, M-017–M-018, M-022, M-025–M-026, M-038, M-042 |
| DNS Modernization Guide |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | M-009, M-011, M-019, M-027, M-040, M-045 |
| Read-Only AD Assessment Guide |  | ✓ |  |  |  |  |  | M-008 |
| The Federal Modernization Program vs Microsoft Nat | ive Tools - | – Gap Anal | ysis | **✓* | * **✓* | * |  | M-010, M-016 |
| PKI Modernization Guide |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | M-009–M-011, M-020, M-028–M-029, M-039, M-045 |

Appendix A — Complete Milestone Register

| ID | Milestone Name | Phase | Week | Owner | Dependencies | Gate Criteria | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| M-001 | Server provisioned | 0 | W1 | Infra Lead | — | Server online, domain-joined, hardened | PLANNED |
| M-002 | IIS + Gitea operational | 0 | W2 | Infra Lead | M-001 | Clone/push/pull over HTTPS verified | PLANNED |
| M-003 | AD LDAP auth configured | 0 | W2 | Identity Lead | M-002 | AD users can login, CanonStewards = admin | PLANNED |
| M-004 | Entra ID OAuth2 configured | 0 | W3 | Identity Lead | M-002 | Entra SSO verified, MFA enforced | PLANNED |
| M-005 | the Federal Modernization Program re | po mirrored |  | 0 | W3 Canon | Steward M-002, M-003 All branches, tags, history verified | PLANNED |
| M-006 | Governance hooks deployed | 0 | W3 | Canon Steward | M-005, M-004 | FOUO rejection and branch protection verified | PLANNED |
| M-007 | Azure Arc enrollment | 0 | W3 | Infra Lead | M-001 | Arc agent heartbeat, policies assigned | PLANNED |
| M-008 | Read-only assessment committed | 1 | W4 | Identity Lead | M-006 | Read-only assessment reviewed, delegation request submitted | PLANNED |
| M-009 | Full assessment committed | 1 | W5 | Identity Lead | M-008 | All 12 domains assessed, no critical gaps | PLANNED |
| M-010 | Security assessment complete | 1 | W6 | Security Lead | M-009 | Findings classified, remediation plan drafted | PLANNED |
| M-011 | Planning docs generated | 1 | W7 | All Leads | M-009, M-010 | 8 planning documents pass schema validation | PLANNED |
| M-012 | Planning docs approved | 1 | W8 | Canon Steward | M-011 | Steering committee approval; all docs APPROVED | PLANNED |
| M-013 | Pre-pilot infrastructure ready | 1 | W9 | All Leads | M-012 | Pilot scope defined, infrastructure provisioned, critical security remediated | PLANNED |
| M-014 | extension attribute taxonomy finaliz | ed |  | 2 | W10 Identity | Lead M-012 Extension attribute mapping committed | PLANNED |
| M-015 | Dynamic group design complete | 2 | W10 | Endpoint Lead | M-014 | All rules tested in non-production | PLANNED |
| M-016 | Intune policy design complete | 2 | W11 | Endpoint Lead | M-015 | All GPO-to-Intune mappings documented | PLANNED |
| M-017 | Conditional Access design | 2 | W11 | Security Lead | M-012 | 15+ policies in report-only for 7+ days | PLANNED |
| M-018 | Entra Connect sync design | 2 | W12 | Identity Lead | M-014 | Filtering, attribute flow, sync method documented | PLANNED |
| M-019 | DNS Private Resolver design | 2 | W12 | DNS Lead | M-012 | Hub-spoke topology and forwarding rulesets documented | PLANNED |
| M-020 | Cloud PKI design complete | 2 | W13 | PKI Lead | M-012, M-010 | Root/BYOCA decided, template matrix, SCEP designs | PLANNED |
| M-021 | Phase 2 design review approved | 2 | W13 | Canon Steward | M-014–M-020 | All designs approved | PLANNED |
| M-022 | Entra Connect deployed | 3 | W14 | Identity Lead | M-018, M-021 | Sync operational with PHS, staging mode validated | PLANNED |
| M-023 | Pilot devices joined | 3 | W15 | Endpoint Lead | M-015, M-022 | 50+ devices registered with extension attributes | PLANNED |
| M-024 | Intune policies assigned to pilot | 3 | W16 | Endpoint Lead | M-016, M-023 | GPO-equivalent policies via dynamic groups | PLANNED |
| M-025 | Conditional Access enforced | 3 | W17 | Security Lead | M-017, M-024 | MFA, compliance, auth strength active | PLANNED |
| M-026 | PIM configured | 3 | W18 | Identity Lead | M-022 | All admins PIM-eligible, zero permanent GA | PLANNED |
| M-027 | DNS hybrid resolution validated | 3 | W19 | DNS Lead | M-019 | Bidirectional resolution confirmed | PLANNED |
| M-028 | Cloud PKI certs issued to pilot | 3 | W20 | PKI Lead | M-020 | SCEP deployed, Wi-Fi/VPN auth verified | PLANNED |
| M-029 | Entra CBA validated | 3 | W20 | PKI Lead | M-028 | Certificate-based SSO working | PLANNED |
| M-030 | Arc pilot servers compliant | 3 | W21 | Infra Lead | M-007 | Guest Configuration compliant | PLANNED |
| M-031 | Pilot success criteria met | 3 | W21 | PM | M-024–M-030 | >95% compliance, zero auth failures | PLANNED |
| M-032 | Wave 1 complete | 4 | W24 | All Leads | M-031 | ~25% migrated, validation passed | PLANNED |
| M-033 | Wave 2 complete | 4 | W27 | All Leads | M-032 | ~50% cumulative | PLANNED |
| M-034 | Wave 3 complete | 4 | W30 | All Leads | M-033 | ~75% cumulative | PLANNED |
| M-035 | Wave 4 complete | 4 | W33 | All Leads | M-034 | 100% migrated | PLANNED |
| M-036 | Legacy GPO disabled | 4 | W33 | Endpoint Lead | M-035 | No GPO links to migrated OUs | PLANNED |
| M-037 | Dynamic groups 100% | 4 | W33 | Identity Lead | M-035 | extension attribute coverage = 100% | PLANNED |
| M-038 | ADFS decommissioned | 5 | W35 | Identity Lead | M-035 | Federated domains converted to managed | PLANNED |
| M-039 | ADCS issuance stopped | 5 | W36 | PKI Lead | M-035 | Auto-enrollment disabled, templates locked | PLANNED |
| M-040 | DNS forwarders migrated | 5 | W37 | DNS Lead | M-035 | All forwarding via Private Resolver | PLANNED |
| M-041 | GPO links removed | 5 | W38 | Endpoint Lead | M-036 | All GPOs unlinked | PLANNED |
| M-042 | Trusts reduced | 5 | W39 | Identity Lead | M-035 | Non-essential trusts removed | PLANNED |
| M-043 | Legacy servers decommissioned | 5 | W40 | Infra Lead | M-039–M-041 | NDES, Issuing CA, secondary DNS offline | PLANNED |
| M-044 | Cutover validation complete | 5 | W41 | Canon Steward | M-037–M-043 | All plans show 100% completion | PLANNED |
| M-045 | Weekly drift assessment | 6 | W42+ | Automation | M-044 | Weekly diff committed to Gitea | PLANNED |
| M-046 | Monthly compliance report | 6 | W42+ | Security Lead | M-044 | Report committed monthly | PLANNED |
| M-047 | Quarterly access review | 6 | W42+ | Identity Lead | M-044 | PIM + group attestation complete | PLANNED |
| M-048 | Annual architecture review | 6 | W42+ | Canon Steward | M-044 | Architecture review report committed | PLANNED |

Appendix B — Assessment Phase Week-by-Week Calendar

This Gantt-style table shows every task across Weeks 4–9 with parallel tracks for each assessment domain. █ = Active task, ░ = Dependency wait.

| Track / Task | W4 Mon–Tue | W4 Wed–Fri | W5 | W6 | W7 | W8 | W9 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Setup | T-4.1, T-4.2 |  |  |  |  |  |  |
| Read-Only Assessment |  | T-4.3, T-4.4 |  |  |  |  |  |
| Commit & Delegation Request |  | T-4.5, T-4.6 |  |  |  |  |  |
| DNS Assessment |  |  | T-5.2 |  |  |  |  |
| PKI Assessment |  |  | T-5.3 |  |  |  |  |
| GPO Assessment |  |  | T-5.4 |  |  |  |  |
| Deleted Objects |  |  | T-5.5 |  |  |  |  |
| ESC Vulnerability Analysis |  |  |  | T-6.1 |  |  |  |
| Privileged Access Audit |  |  |  | T-6.2 |  |  |  |
| Third-Party Imports |  |  |  | T-6.3, T-6.4 |  |  |  |
| Security Findings Report |  |  |  | T-6.5–T-6.7 |  |  |  |
| Computer Modernization Plan |  |  |  |  | T-7.1 |  |  |
| Identity Modernization Plan |  |  |  |  | T-7.2 |  |  |
| GPO Migration Plan |  |  |  |  | T-7.3 |  |  |
| DNS / PKI / Attribute Plans |  |  |  |  |  | T-7 | .4–T-7.6 |
| Trust / Security Plans |  |  |  |  | T-7.7–T-7.8 |  |  |
| Canon Steward Review |  |  |  |  |  | T-8.1 |  |
| Pillar Lead Reviews |  |  |  |  |  | T-8.2–T-8.3 |  |
| Steering Committee Approval |  |  |  |  |  | T-8.4–T-8.5 |  |
| Pilot Group Selection |  |  |  |  |  |  | T-9.1–T-9.2 |
| Security Remediation |  |  |  |  |  |  | T-9.3 |
| Pre-Pilot Provisioning |  |  |  |  |  |  | T-9.4–T-9.7 |

Appendix C — RACI Matrix

R = Responsible (does the work), A = Accountable (owns the outcome), C = Consulted, I = Informed.

| Activity | Canon Steward | Infra Lead | Identity Lead | Endpoint Lead | DNS Lead | PKI Lead | Security Lead | PM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Server provisioning (Phase 0) | I | R/A | C | I | I | I | C | I |
| IIS + Gitea deployment | A | R | C | I | I | I | I | I |
| AD LDAP / Entra OAuth2 auth | A | C | R | I | I | I | C | I |
| Governance hooks deployment | R/A | C | I | I | I | I | C | I |
| Read-only AD assessment | A | C | R | C | C | C | C | I |
| Full AD assessment (delegated) | A | C | R | C | R | R | C | I |
| Security assessment | A | I | C | I | I | C | R | I |
| Planning document generation | A | I | R | R | R | R | R | I |
| Planning review / approval | R/A | C | C | C | C | C | C | C |
| extension attribute taxonomy desig | n | A | I | R | C | I | I | I I |
| Intune policy design | A | I | C | R | I | I | C | I |
| Conditional Access design | A | I | C | C | I | I | R | I |
| Entra Connect deployment | A | C | R | I | I | I | C | I |
| DNS Private Resolver deployment | A | C | I | I | R | I | I | I |
| Cloud PKI deployment | A | C | C | C | I | R | C | I |
| Pilot execution | A | R | R | R | R | R | R | R |
| Wave-based scaling | A | R | R | R | R | R | C | R |
| Legacy decommission | R/A | R | R | R | R | R | C | I |
| Cutover validation | R/A | C | C | C | C | C | C | R |
| Drift detection (steady state) | A | C | C | C | C | C | R | I |
| Quarterly access reviews | A | I | R | I | I | I | C | I |
| Risk register maintenance | C | C | C | C | C | C | C | R/A |
| Milestone tracking / reporting | I | I | I | I | I | I | I | R/A |

Appendix D — Phase Gate Review Template

This template is used for every phase gate review. Copy this template and complete it for each gate decision. Commit the completed review to Gitea at reports/phase-gates/phase-N-gate-review.md.

| Field | Value |
| --- | --- |
| Gate Review Title | Phase [N] → Phase [N+1] Gate Review |
| Date | [YYYY-MM-DD] |
| Attendees | [List all attendees and roles] |
| Review Chair | Canon Steward |

Agenda

- Phase [N] objective review — 5 min

- Milestone completion status — 15 min

- Deliverable checklist walkthrough — 20 min

- Risk register updates — 10 min

- Open issues and blockers — 15 min

- Go/No-Go discussion — 15 min

- Decision and action items — 10 min

Deliverable Checklist

| # | Deliverable | Status | Gitea Path | Verified By |
| --- | --- | --- | --- | --- |
| 1 | [Deliverable name] | [ ] Complete [ ] Partial [ ] Blocked | [path] | [name] |
| 2 | [Deliverable name] | [ ] Complete [ ] Partial [ ] Blocked | [path] | [name] |
| 3 | [Deliverable name] | [ ] Complete [ ] Partial [ ] Blocked | [path] | [name] |

Go/No-Go Criteria

| Criterion | Required? | Met? | Evidence |
| --- | --- | --- | --- |
| All mandatory milestones complete | Yes | [ ] Yes [ ] No | [Link to milestone evidence] |
| All critical/high risks mitigated or accepted | Yes | [ ] Yes [ ] No | [Link to risk register] |
| All deliverables committed to Gitea with APPROVED status | Yes | [ ] Yes [ ] No | [Gitea branch/commit hash] |
| No unresolved blockers | Yes | [ ] Yes [ ] No | [Issue tracker] |
| Stakeholder sign-off obtained | Yes | [ ] Yes [ ] No | [Sign-off record] |

Decision Record

| Field | Value |
| --- | --- |
| Decision | [ ] GO — Proceed to Phase [N+1] [ ] NO-GO — Remain in Phase [N] [ ] CONDITIONAL GO — Proceed with conditions |
| Conditions (if applicable) | [List conditions that must be met within specified timeframe] |
| Decision Authority | Canon Steward: [Name] — [Signature/Date] |

Action Items

| # | Action | Owner | Due Date | Status |
| --- | --- | --- | --- | --- |
| 1 | [Action description] | [Name] | [Date] | OPEN |
| 2 | [Action description] | [Name] | [Date] | OPEN |

Appendix E — Glossary

| Term | Definition |
| --- | --- |
| ADCS | Active Directory Certificate Services — Microsoft's on-premises PKI platform for issuing and managing digital certificates. |
| ADFS | Active Directory Federation Services — on-premises federation service for SSO; being replaced by Entra ID in cloud-modern architectures. |
| ADR | Architecture Decision Record — a document capturing a significant architectural decision, its context, and consequences. |
| ADMX Ingestion | The process of importing Group Policy ADMX templates into Intune for policy configuration on cloud-managed devices. |
| ARR | Application Request Routing — an IIS module enabling reverse proxy and load balancing functionality. |
| AS-REP Roasting | An attack technique exploiting accounts that do not require Kerberos pre-authentication to extract password hashes. |
| Azure Arc | Microsoft service that extends Azure management and governance to on-premises and multi-cloud servers. |
| BYOCA | Bring Your Own Certificate Authority — a Cloud PKI deployment model where an existing on-premises root CA signs the cloud issuing CA certificate. |
| Canon / Canonical | In the Federal Modernization Program context, the authoritative, approved version of a governance artifact committed to the main branch of Gitea. |
| Canon Steward | The individual with final authority over the Federal Modernization Program governance artifacts, repository integrity, and phase gate approvals. |
| CBA | Certificate-Based Authentication — Entra ID feature enabling passwordless authentication using X.509 certificates. |
| CIS L1 | Center for Internet Security Level 1 benchmark — a security hardening baseline for Windows Server. |
| Cloud PKI | Microsoft Intune Cloud PKI — a cloud-native certificate authority included in the Intune Suite for issuing SCEP/PKCS certificates. |
| Conditional Access | Entra ID policy engine that enforces access controls based on user, device, location, risk, and application context. |
| CRL | Certificate Revocation List — a list of certificates that have been revoked before their expiration date. |
| Drift Detection | The automated process of comparing current infrastructure state against canonical governance artifacts to identify unauthorized or unplanned changes. |
| Entra Connect | Microsoft identity synchronization service (formerly Azure AD Connect) that syncs on-premises AD identities to Entra ID. |
| Entra ID | Microsoft Entra ID (formerly Azure Active Directory) — Microsoft's cloud identity and access management service. |
| ESC1–ESC8 | Escalation vulnerability classes (ESC1 through ESC8) in Active Directory Certificate Services, as documented by SpecterOps. Each class represents a distinct misconfiguration pattern that could allow privilege escalation. |
| Gitea | A lightweight, self-hosted Git service used as the Federal Modernization Program governance repository platform. |
| gMSA | Group Managed Service Account — an AD account type that provides automatic password management for service accounts. |
| GPO | Group Policy Object — an AD mechanism for applying configuration settings to computers and users within an OU scope. |
| Guest Configuration | An Azure Policy feature (via Azure Arc) that audits and enforces OS-level settings on servers. |
| Hybrid Join | A device registration state where a device is joined to both on-premises AD and Entra ID simultaneously. |
| IIS | Internet Information Services — Microsoft's web server platform used as the reverse proxy for Gitea in the Federal Modernization Program architecture. |
| Intune | Microsoft Intune — a cloud-based endpoint management service for device configuration, compliance, and application management. |
| Kerberoasting | An attack technique that exploits Kerberos service tickets to extract service account password hashes. |
| LDAPS | LDAP over SSL/TLS — the encrypted version of the Lightweight Directory Access Protocol used for AD authentication. |
| NDES | Network Device Enrollment Service — an ADCS role service enabling SCEP certificate enrollment for network devices. |
| OIDC | OpenID Connect — an authentication protocol built on OAuth 2.0, used for Entra ID SSO integration with Gitea. |
| OMA-URI | Open Mobile Alliance Uniform Resource Identifier — a custom Intune policy format for settings not available in the Settings Catalog. |
| PAW | Privileged Access Workstation — a hardened workstation used for security-sensitive administrative tasks. |
| PHS | Password Hash Synchronization — an Entra Connect feature that syncs a hash of the on-premises AD password hash to Entra ID. |
| PIM | Privileged Identity Management — an Entra ID feature providing just-in-time, time-bound, and approval-based activation of privileged roles. |
| PKCS | Public Key Cryptography Standards — a certificate enrollment protocol used by Intune for certificate deployment. |
| Private Resolver | Azure DNS Private Resolver — a cloud-native DNS forwarding service enabling hybrid DNS resolution between on-premises and Azure networks. |
| PTA | Pass-Through Authentication — an Entra Connect feature that validates passwords directly against on-premises AD without syncing hashes. |
| RSAT | Remote Server Administration Tools — Windows management tools for administering AD, DNS, ADCS, and other server roles remotely. |
| SCEP | Simple Certificate Enrollment Protocol — a protocol for automated certificate enrollment, used by Intune for device certificate deployment. |
| Settings Catalog | The modern Intune policy configuration surface that provides granular, per-setting control equivalent to Group Policy. |
| SLA | Service Level Agreement — a defined target for detection and remediation timeframes, used in the Federal Modernization Program drift remediation framework. |
| SPN | Service Principal Name — a Kerberos identifier for a service instance, relevant for Kerberoasting risk assessment. |
| SRV Record | A DNS record type used by AD for service location (e.g., domain controller discovery via _ldap._tcp). |
| Strong Mapping | A certificate-to-identity binding method required by Microsoft's KB5014754 enforcement for certificate-based authentication against AD. |
| **The Federal Modernizatio | n Program** Unified Infrastructure Administration and Operations — the governance framework and toolset for managing AD modernization as code. |
| Workload Identity | Microsoft Entra Workload Identity — cloud-native identity for applications and services, replacing traditional service accounts. |

FMP_013_Master_Project_Plan_v1.0 | Classification: Controlled | Boundary: GCC-Moderate
Generated 21 April 2026 | Canon Steward: Michael | Repository: https://github.com/WhalerMike/modernization-workbook
Status: DRAFT — Pending Canon Steward review and steering committee approval

## Compliance Amendment — Control Traceability and Risk Register (PL-2, RA-3)

### Milestone-to-control-family traceability (PL-2)

Each program milestone is mapped to the NIST 800-53 control families it advances, so that program progress is traceable to control coverage. This traceability complements the SSP (FMP_185), which holds the authoritative per-control disposition; the program plan references control families at the milestone level.

### Risk register (RA-3)

The program maintains a risk register recording identified program and security risks, their likelihood/impact rating, owner, mitigation, and status. Security risks with residual exposure are cross-referenced to POA&M items (FMP_189); the register is reviewed at each phase gate per RA-3.