# Chapter 09 — Migration Roadmap: Phased Plan, Gates, Rollback

Seven phases, five parallel workstreams, named gates, deterministic rollback

2026-04-24

Table of contents

# Chapter 09 — Migration Roadmap: Phased Plan, Gates, Rollback

Seven phases, five parallel workstreams, named gates, deterministic rollback

Figure 9.1 — 52-week modernization program with seven phases, five parallel workstreams, and six named gates

Figure 9.1 — 52-week modernization program with seven phases, five parallel workstreams, and six named gates

The program claim

Every modernization this series describes is achievable in a 52-week program with five parallel workstreams (identity, policy, services, compute, access) and seven named gates. The roadmap is not a consulting slideware pattern; it is a PR-reviewable document in Gitea, updated weekly, with gate criteria that are mechanical to evaluate. This chapter is how you sequence the chapters 01-08 work into a governed program that actually ships.

## The program shape

A full Client-Server-to-Hybrid-Cloud modernization has two defining properties:

- Parallel, not sequential. Identity, policy, services, compute, and access work in parallel streams. Waiting for one to finish before starting the next doubles the program duration and produces worse outcomes.

- Gated, not open-ended. Each phase has explicit entry and exit criteria. A phase cannot start until the prior phase’s exit gate clears. A phase cannot exit until its own criteria are green.

Total realistic duration for a mid-size federal agency (5,000–50,000 users, 500–5,000 servers): ~52 weeks, matching the Posted Master Project Plan. Larger agencies extend; smaller agencies compress. The phase structure doesn’t change with scale — only the per-phase duration does.

## The seven phases

Migration roadmap timeline diagram showing six phases (Phase 0 Discovery…

### Phase 0 — Pre-flight (weeks 1-4)

Goal. Produce the canonical planning artifacts and stand up the platform server.

Entry criteria (to start Phase 0): - Executive sponsor named. - Canon Steward appointed. - Platform-server hardware or VM provisioned. - AD read-only service account delegated.

Work in Phase 0: - Build the platform server (Chapter 01). Wall-clock: 1-2 weeks. - Run the Tier-B AD assessment (Chapter 02). Wall-clock: 1 week. - Author the initial OrgPath codebook (MOD_A). Wall-clock: 1 week. - Stand up Gitea canonical repository with baseline canon files. - Confirm Entra + Intune + Arc tenant access with least-privilege service principals.

Exit gate (Gate G0 — Ready to Plan): - [ ] Platform server operational (Chapter 01 validation passed). - [ ] Assessment run committed to Gitea. - [ ] Draft OrgPath codebook in Gitea, steward-approved. - [ ] Canon registry (MOD_A..Z index) in place. - [ ] No open P1 findings from assessment.

### Phase 1 — Foundation (weeks 5-8)

Goal. Put identity-substrate primitives in place before anything else moves.

Workstream outputs: - Identity. Dynamic groups for Enterprise-level branches (OrgTree-Enterprise-Users, OrgTree-IT-Users, etc.). Administrative Units for Tier-1 and selected Tier-2 scopes. - Policy. Enterprise CA baseline (CA-100 series): MFA required for all users, legacy auth blocked, break-glass carve-outs. - Services. IPAM (DM_010) stood up with partial coverage — enough to tag the platform server and Tier-0 infrastructure. - Compute. Platform server Entra-registered; select server pilots Arc-connected. - Access. Platform-SSO configured; FIDO2 registration available for Tier-0 admins.

Exit gate (Gate G1 — Foundation Complete): - [ ] Enterprise dynamic groups + AUs created and drift-clean. - [ ] CA-100 enterprise baseline enforced; no MFA-exempt users. - [ ] IPAM covers at least Tier-0 infrastructure. - [ ] Drift engine reports zero findings across foundation scope. - [ ] Break-glass accounts vaulted in CyberArk.

### Phase 2 — Pilot Division (weeks 9-16)

Goal. Run one division through the full transformation as a learning exercise, proving the pattern before general rollout.

Typical pilot division: IT (highest tolerance for disruption, most engaged with modernization).

Workstream outputs for pilot: - Identity. Pilot division OrgPath fully populated; dynamic groups live; AUs scoped; role assignments delegated. - Policy. Division-scoped CA (CA-200 series) + Intune configuration + compliance policies applied. 3-4 GPOs retired. - Services. Pilot division DNS zones migrated. DHCP scopes re-homed. IPAM populated for division address space. - Compute. Pilot PCs transition (greenfield via Autopilot for new hardware; reset-and-re-enroll for refreshable legacy; hybrid for the rest). Pilot servers Arc-connected. - Access. Division users configured for CBA (where CAC holders exist); SASE ZTNA in place for division apps.

Exit gate (Gate G2 — Pilot Clean): - [ ] Pilot division MOD_M drift zero for 14 consecutive days. - [ ] Pilot division has zero AD-only users, zero Hybrid Joined PCs that aren’t scheduled for full cut. - [ ] Pilot ATO boundary re-evaluated; no new findings. - [ ] Retrospective complete; lessons-learned doc committed. - [ ] Per-phase runbook updates committed based on pilot experience.

### Phase 3 — General Rollout (weeks 17-36)

Goal. Scale the pattern to every remaining division.

This is the longest phase. Duration scales with division count: budget ~2-3 weeks per division, running 2-3 divisions in parallel. Large agencies may overlap divisions heavily; small agencies may run strictly sequentially.

Workstream cadence: - Weekly — a steering-committee review of active divisions. Each division reports green/yellow/red against its rollout plan. - Per division — 4-phase sub-pattern: plan, pilot within division, general-availability to the full division, drift-clean hold. - Parallel — Chapters 04-08 content flows for each division concurrently; canon is shared.

Exit gate (Gate G3 — Rollout Complete): - [ ] Every in-scope division has passed its division-level exit gate. - [ ] Every HR-listed employee has a valid OrgPath. - [ ] Every user PC is Entra Joined or in a documented exception. - [ ] Every server is Arc-connected or in a documented exception. - [ ] Drift engine reports zero cross-division drift.

### Phase 4 — Legacy Retirement (weeks 37-44)

Goal. Systematically retire legacy infrastructure: GPOs, OU security groups, AD-integrated DNS, AD-joined DHCP, ADCS smart-card logon configuration, SPN-bound legacy apps.

Retirement is governed: each artifact has a retirement plan with its own entry/exit criteria, and the retirement action is a Plan-stage action with explicit steward approval.

Retirement sequence (typical): 1. Retire redundant GPOs (GPOs migrated to Intune). 2. Retire OU-based security groups (membership superseded by dynamic groups). 3. Retire AD-integrated DNS zones one at a time. 4. Retire AD-joined DHCP authority. 5. Retire ADCS smart-card logon GPO configuration. 6. Retire remaining AD-bound SPNs (application-by-application).

Exit gate (Gate G4 — Legacy Quiet): - [ ] No active GPOs other than the minimum Kerberos-island set. - [ ] No AD-based dynamic / static-membership security groups in active use. - [ ] Zero AD-integrated DNS zones. - [ ] ADCS retained only for issuance, not for smart-card logon. - [ ] SPN map shows all migrated/retired/islanded — no unresolved SPNs. - [ ] AD authentication rate < 5% of peak-migration rate (most auth has moved to Entra).

### Phase 5 — AD DS Retirement (weeks 45-48)

Goal. Shut down Active Directory Domain Services.

This is the shortest phase of the program because the work was done in Phases 0-4. Phase 5 is the mechanical teardown.

Sequence: 1. Freeze AD changes (canon change protocol enforcement). 2. Final forest assessment + evidence packet. 3. Demote non-FSMO DCs. 4. Transfer FSMO roles to the designated survivor (if any — some agencies retain a Kerberos island). 5. Demote remaining DCs (or isolate if Kerberos island retained). 6. Decommission VMs + retire forest objects in backup. 7. Final provenance commit: “forest X retired on date Y per evidence packet Z.”

Exit gate (Gate G5 — AD Retired): - [ ] DCs decommissioned or explicitly retained as documented Kerberos island. - [ ] Evidence packet committed to Gitea + SIEM. - [ ] No live production dependency on AD authentication.

### Phase 6 — Steady State (week 49+)

Goal. Operate the modernized environment under canon governance.

Steady state is the permanent post-modernization state. It has properties:

- Assessments run nightly (Chapter 02).

- Plans generated and authorized on change-driven and scheduled cadences (Chapter 03).

- Drift detected + resolved within MOD_Q SLAs.

- Evidence packets emitted per delivery.

- Continuous monitoring feeds FedRAMP ConMon + SCuBA pipelines.

- Canon changes flow via PR per MOD_V.

Exit criteria: none. Phase 6 continues indefinitely. Periodic retrospectives (quarterly) confirm the canon matches agency intent.

## The five parallel workstreams

During Phases 2-4, five workstreams run in parallel with explicit coordination points:

| Workstream | Lead | Chapter | Key artifacts |
| --- | --- | --- | --- |
| Identity | Identity Architect | 04 | OrgPath codebook, dynamic groups, AUs |
| Policy | Security Engineer | 05 | Intune configs, CA policies, Arc Guest Config |
| Services | Network Engineer | 06 | DNS, DHCP, IPAM adapters |
| Compute | Endpoint Admin + Server Eng | 07 | Device enrollments, Arc projections |
| Access | Identity + Security jointly | 08 | SASE, CBA, PAM, MFA |

Workstreams are not independent. Every week, a cross-workstream sync identifies the per-division blockers and resequences work where dependencies exist (e.g., compute migration can’t proceed in a division until its CA policies are in place).

## Gate criteria — mechanical, not subjective

Every gate criterion in this chapter is mechanically evaluable from Gitea canon + drift-engine reports. Examples:

- “Zero drift for 14 consecutive days” → MOD_M report filtered by scope + date range.

- “Every HR-listed employee has a valid OrgPath” → SQL-like query against the canonical user table.

- “Every user PC is Entra Joined” → device inventory query.

Gates are never passed on executive signature alone. The engine reports green; the steward concurs; the PR merges. A gate that the engine cannot evaluate is a gate that needs a better criterion.

## Rollback triggers

Every phase has defined rollback triggers — conditions that halt progress and revert to the prior phase’s state. Triggers are not subjective; they are thresholded.

| Trigger | Scope | Action |
| --- | --- | --- |
| MOD_M drift > threshold X for > 24 hours | phase-wide | Halt phase; investigate; no new deliveries until clean |
| CA policy blocks > Y% of legitimate sign-ins | enterprise | Revert CA policy; investigate; authorize replacement |
| Drift engine itself fails to report | platform | Escalate per MOD_Q; halt all phase work |
| Evidence packet fails signature validation | any delivery | Halt; forensic investigation; restore from last known-good |
| SLA-breach on P1 finding | any scope | Escalate per MOD_Q Tier 1; steward + sponsor notified |

Rollback is operationally expensive, so the gate design is meant to prevent the need for it. Pilot phases catch what would otherwise become rollback events later.

## Decision authority at each gate

Not every gate is a Canon Steward decision. The program defines decision authority per gate:

| Gate | Authority | Backup |
| --- | --- | --- |
| G0 — Ready to Plan | Canon Steward | Executive Sponsor |
| G1 — Foundation Complete | Canon Steward | — |
| G2 — Pilot Clean | Canon Steward + Executive Sponsor | — |
| G3 — Rollout Complete | Executive Sponsor + Steering Committee | — |
| G4 — Legacy Quiet | Canon Steward | Executive Sponsor |
| G5 — AD Retired | Executive Sponsor + CIO | — |
| Division-level exit (G3 sub-gate) | Division Lead + Canon Steward | — |

Gate authority is recorded in the Gitea PR that merges the gate decision. Disputed gates escalate per MOD_Q.

## Common failure modes

Across federal agencies that have run variants of this program, five failure modes recur. UIAO’s structure is designed to pre-empt each:

- Half-finished identity. Pattern: rollout begins, 30% of users have OrgPath, HR connector breaks, project stalls. Mitigation: Gate G1 requires HR connector operational before rollout.

- Unscoped CA policy. Pattern: broad “require MFA” policy deployed; edge cases block operationally critical sign-ins. Mitigation: Chapter 05’s OrgPath-scoped + pilot-group-first pattern.

- DNS left for “phase 2.” Pattern: identity moves, DNS stays AD-integrated, AD can’t actually retire. Mitigation: Chapter 06’s insistence that DNS+DHCP+IPAM migrate together.

- Hybrid Joined permanence. Pattern: devices become Hybrid Joined and stay that way indefinitely. Mitigation: Chapter 07’s rule that Hybrid Join is a transition state, with drift-engine monitoring of time-in-state.

- Evidence-less migration. Pattern: changes happen via ad-hoc admin actions; FedRAMP audit can’t produce provenance. Mitigation: Chapter 03’s plan-based delivery — every change has provenance by construction.

## The week-by-week cadence

For the steering committee, the cadence is:

- Monday — workstream leads update status (green/yellow/red).

- Tuesday — cross-workstream dependency sync.

- Wednesday — canon changes + plan reviews merge to Gitea.

- Thursday — plan deliveries scheduled (typically off-peak).

- Friday — evidence packet + drift-engine review; retrospective on the week.

Monthly: gate-criterion reviews against the phase schedule. Red status across two consecutive weeks escalates to the executive sponsor.

## What finishing looks like

In week 49 (Phase 6 steady state), the program meeting looks like this:

- Drift-engine report: zero findings.

- Nightly plan run: zero actions.

- Evidence packets: fully signed, shipped to SIEM + ConMon.

- ServiceNow tickets: routine operational only; no P1 findings.

- Audit posture: ATO package refreshed; continuous-monitoring feed live; 3PAO relationship quarterly.

- Canon: one PR merged this week for a Policy library refinement; otherwise stable.

The program is not “done” — steady state is the operational mode — but the modernization is complete. The agency runs governed; AD is gone; the canon is the operational truth.

## Cross-references

- Posted: UIAO Master Project Plan — Assessment Phase Through Full Modernization (14,051 words) — 7-phase, 48-milestone, 52-week capstone plan.

- Canon: MOD_F Migration Runbook · MOD_Q SLA Escalation Playbooks · MOD_V Canonical Contributor Workflow.

- Customer Documents: program management.

Next: Chapter 10 — Leadership Takeaway: Instruments vs. Orchestra